**STANDARD PROCUREMENT DOCUMENT**

**Request for Proposals**

**Works and Operation Service**

**Design, build and operation of**

***[water treatment plant (WTP)/ wastewater treatment plant (WWTP)]***

**(Single-stage Request for Proposals, after Initial Selection)**

(where the Bank’s Disqualification mechanism for non-compliance with SEA/SH obligations applies)



**July 2023**

This document is subject to copyright.

This document may be used and reproduced for non-commercial purposes only. Any commercial use, including without limitation reselling, charging to access, redistribute, or for derivative works such as unofficial translations based on this document is not allowed.

**Revisions**

**July 2023**

This revision **consolidates** what was in separate SPDs i.e. pre-ESF and ESF respectively, with relevant parts marked to guide application.

This revision requires that the successful proposer shall submit the **Beneficial Ownership Disclosure Form** in accordance with the requirements of the RFP.

Further, this revision includes provisions to manage cyber security risks, to apply for contracts that have been assessed to present potential or actual cyber security risks.

**January 2021**

This revision incorporates provisions on disqualification of contractors, and their proposed subcontractor/s as applicable, from being awarded Bank financed contracts. The provisions on disqualification for procurement of Works using this SPD apply to contracts under Projects assessed as high risk for Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH).

**December 2019**

SEA (Sexual Exploitation and Assault) has been replaced with SEA (Sexual Exploitation and Abuse) and SH (Sexual Harassment) as appropriate.

Editorial enhancements have also been made.

**Preface**

The SPD is applicable to the procurement of Works and Operation Service (Design, Build and Operate) of Water Treatment Plant (WTP) and Wastewater Treatment Plant (WWTP) funded by IBRD or IDA financed projects whose Legal Agreement makes reference to the *Procurement Regulations for IPF Borrowers July 2016* as amended from time to time.

This SPD shall be used for international competitive procurement, after Initial Selection, using a single stage Request for Proposals (RFP) selection method. If as result of the Project Procurement Strategy for Development (PPSD), a two-stage process would be more appropriate, then the corresponding SPD for a two-stage process should be applied. Both SPDs assume that an initial selection has been carried out, which should normally be the case for an RFP selection method. If the PPSD for justified reasons (in specific circumstances) has not identified the need for initial selection, then the relevant provisions of these SPDs should be modified accordingly.

This SPD, with some adaption, could be used on projects with water and wastewater networks and related facilities. A separate Standard Initial Selection Document for Design and Build has been issued together with this SPD.

The Conditions of Contract are the “General Conditions” which form part of the “Conditions of Contract for Design, Build and Operate Projects (“Gold book”) First edition 2008” published by the Federation Internationale Des Ingenieurs – Conseils (FIDIC) and the “Particular Conditions” to be used by Borrowers when applying these “General Conditions.” An original copy of the FIDIC publication i.e. “Conditions of Contract for Design, Build and Operate Projects” must be obtained from FIDIC.

This revision **consolidates** what was in separate SPDs i.e. pre-ESF and ESF respectively, with relevant parts marked to guide application.

The SPD includes mandatory requirements that the successful proposer shall submit the **Beneficial Ownership Disclosure Form** in accordance with the requirements of the RFP.

Further, this revision includes provisions to manage cyber security risks, to apply for contracts that have been assessed to present potential or actual cyber security risks.

It is important that, as part of procurement planning, the Employer considers the potential benefits, limitations, risks and attributes of a Design, Build and Operate approach and makes an informed decision as to whether the use of design, build and operate will benefit the subject contract. Due attention should be given to the efficiency and capacity of the Employer’s procurement and contract administration arrangements, the potential response of the market, estimated total time required for the Employer to carry out the procurement process, as well as the Employer’s existing technical capability and any professional assistance required.

Some of the benefits of Design, Build and Operate approach include: (i) single point of responsibility; the design, the construction and the operations are performed by the same contractor, (ii) access to operations and maintenance expertise, (iii) stronger incentives to deliver a reliable and durable plant because the Contractor would carry the financial consequences of poor design and workmanship and of selecting and installing poor quality equipment, (iv) better value for money in the long term because the contract is awarded to the Proposer offering the lowest combined capital and operating cost (unlike a design-build which is awarded on the basis of lowest initial capital cost), and (v) superior incentives for innovation: for example the contractor may be able to develop a better design as a result of value engineering and having regard for the operational as well as construction costs of the Works.

Some of the limitations of the Design Build Operate approach relative to having separate contracts for design and build (or of having a single design-build contract) include: (i) the Employer not having the capacity to evaluate objectively and properly the differences in solutions proposed by Proposers (the risk of which can be reduced by ensuring that the evaluation committee has relevant expertise), (ii) the Employer may lose some control of the design process: typically (but not always) the DBO contractor is given flexibility in the selection of suitable process technologies, (iii) the Employer loses direct control over operations and maintenance activities, and (iv) there may be a loss of future flexibility as the Employer is bound into a long term relationship with the Contractor.

Notwithstanding that the Contractor is responsible for the design of the Works, the Employer should carry out appropriate front-end tasks to enable the Employer to: (i) develop a realistic understanding of the contract’s scope and costs; (ii) furnish Proposers with information that they can reasonably rely upon in establishing their price and other commercial decisions; and (iii) evaluate and compare the Proposals on a common basis as specified in the RFP. Such tasks may include, as appropriate, specifying performance/functional/basic structural requirements, terms of contractual conditions, as well as necessary geotechnical/environmental investigations, permits acquisition, etc.

Guidance to this SPD can be found at <http://www.worldbank.org/en/projects-operations/products-and-services/brief/procurement-new-framework#SPD> and have been developed to assist Employers and IBRD and IDA staff in preparing DBO projects for WTPs and WWTPs, recognizing that they may be unfamiliar with this approach and related issues. The Guidelines have annexed to them templates for Employer’s Requirements for each of Water and for Wastewater Treatment Plants.

This SPD applies to projects funded by International Bank for Reconstruction and Development (IBRD) and the International Development Association (IDA) where the Legal Agreement makes reference to the Procurement Regulations.

To obtain further information on procurement under World Bank funded projects or for question regarding the use of this SPD, contact:

Chief Procurement Officer

The World Bank

1818 H Street, NW

Washington, D.C. 20433 U.S.A.

pfquestions@worldbank.org

<http://www.worldbank.org>

Standard Procurement Document

**Summary**

**Specific Procurement Notice**

**Specific Procurement Notice - Request for Proposal (RFP) to Initially Selected Proposers**

This SPD covers a single stage, two envelope process following the Initial Selection of Proposers. The template attached is the Specific Notice of Procurement for Request for Proposals to Initially Selected Proposers for simultaneous submission of Technical and Financial Proposals in two separate envelopes.

**PART 1 – REQUEST FOR PROPOSAL PROCEDURES**

**Section I** – **Instructions to Proposers (ITP)**

 This Section provides relevant information to help Proposers prepare their Proposals. It is based on a single- stage procurement process. Information is also provided on the submission, opening, and evaluation of Proposals and on the award of Contracts. **Section I contains provisions that are to be used without modification.**

**Section II** – **Proposal Data Sheet (PDS)**

 This Section consists of provisions that are specific to each procurement and that supplement the information or requirements included in Section I, Instructions to Proposers.

**Section III** – **Evaluation and Qualification Criteria**

This Section specifies the methodology that will be used to determine the Most Advantageous Proposal.

**Section IV** – **Proposal Forms**

 This Section contains the forms which are to be completed by the Proposer and submitted as part of the Proposal.

**Section V** – **Eligible Countries**

 This Section contains information regarding eligible countries.

**Section VI** – **Fraud and Corruption**

This section includes the Fraud and Corruption provisions which apply to this Request for Proposal process.

**PART 2 – EMPLOYER’S REQUIREMENTS**

**Section VII** – **Employer’s Requirements**

This section shall set out a description of the functional and/or performance specification of the works to be designed and constructed. It shall present, as appropriate, a statement of the required standards for materials, plant, supplies, and workmanship to be provided. The Employer Requirements shall also include the environmental and social (ES) requirements.

**PART 3 – CONDITIONS OF CONTRACT AND CONTRACT FORMS**

**Section VIII** – **General Conditions (GC)**

General Conditions (GC) refer to the “General Conditions” which form part of the Conditions of Contract for Design, Build and Operate Projects first edition 2008 published by the Federation Internationale Des Ingénieurs – Conseils (FIDIC).

**Section IX** – **Particular Conditions of Contract (PC)**

 This Section includes particular conditions of the contract consisting of: Part A- Contract Data; Part B -Special Provisions, PART C – Fraud and Corruption; and PART D – Environmental and Social (ES) Reporting Metrics for Progress Reports. The contents of this Section modify or supplement the General Conditions and shall be prepared by the Employer.

**Section X** – **Contract Forms**

 This Section contains the Letter of Acceptance, Contract Agreement and other relevant forms.

**Notice of Request for Proposals**

**Request for Proposals**

**Works and Operation Service**

**(Design, Build and Operation)**

**of *[WTP/ WWTP]***

**(After Initial Selection)**

**Employer:** *[insert the name of the Employer’s agency]*

**Project:***[insert name of project]*

**Contract title:** *[insert the name of the contract]*

**Country:** *[insert country where RFP is issued]*

**Loan No. /Credit No. / Grant No.:** *[insert reference number for loan/credit/grant]*

**RFP No:** *[insert RFP reference number from Procurement Plan]*

**Issued on:** *[insert date when RFP is issued to the market]*

To: *[Proposer’s name and address]*

Dear Ladies and/or Gentlemen,

1. The *[insert name of Borrower/Beneficiary/Recipient] [has received/has applied for/intends to apply for]* financing from the World Bank toward the cost of the *[insert name of project or grant]*, and intends to apply part of the proceeds toward payments under the contract [[1]](#footnote-1)for *[insert title of contract]*[[2]](#footnote-2). *[Insert if applicable:* “For this contract, the Borrower shall process the payments using the Direct Payment disbursement method, as defined in the World Bank’s Disbursement Guidelines for Investment Project Financing.”]
2. The *[insert name of implementing agency]* now invites sealed Proposals from the following initially selected eligible Applicants for *[insert brief description of Works and Operation Service]*[[3]](#footnote-3).

*[Insert names of initially selected Applicants]*

1. The procurement will be conducted through international competitive procurement using Request for Proposals (RFP) as specified in the World Bank’s “[Procurement](http://www.worldbank.org/html/opr/procure/guidelin.html) Regulations for IPF Borrowers” *[insert date of applicable Procurement Regulations edition as per legal agreement]* (“Procurement Regulations”), and is open to all initially selected eligible Proposers.
2. Initially selected eligible Proposers may obtain further information from *[insert name of implementing* agency*, insert name and e-mail of officer in charge][[4]](#footnote-4)* and inspect the RFP Document during office hours *[insert office hours if applicable i.e. 0900 to 1700 hours]* at the address given below *[state address at the end of this RFP]* [[5]](#footnote-5).
3. The RFP Document in [*insert name of language*] may be purchased by initially selected eligible Proposers upon the submission of a written application to the address below and upon payment of a nonrefundable fee[[6]](#footnote-6) of *[insert amount in Borrower’s currency or in a convertible currency]*. The method of payment will be *[insert method of payment]*.[[7]](#footnote-7) The document will be sent by *[insert delivery procedure]*.[[8]](#footnote-8)
4. A single-stage, two envelope RFP process will be used, and the Proposal will consist of (i) the Technical Part, without any reference to prices; and (ii) the Finnacial Part, as detailed in the RFP Document. The Technical and Financial Parts of the proposals shall be submitted simultaneously in two separate sealed envelopes.
5. The Proposal, both the Technical Part and the Financial Part, must be delivered to the address below *[state address at the end of this RFP]*[[9]](#footnote-9) on or before *[insert time and date].* Electronic Procurement will *[will not]* be permitted. Late Proposals will be rejected. The Technical Part of the Proposals will be publicly opened in the presence of the Proposers’ designated representatives and anyone who chooses to attend at the address below *[state address at the end of this RFP]* on *[insert time and date]*.The Financial Part shall remain unopened and will be held in safe custody of the Employer until the second public opening of the Financial Part, following the evaluation of the Technical Part of the Proposals.
6. All Proposals must be accompanied by a *[insert “Proposal Security” or “Proposal-Securing Declaration,” as appropriate]* of *[insert amount and currency in case of a Proposal Security[[10]](#footnote-10).*
7. All Proposals must be accompanied by a Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Declaration.
8. Please confirm receipt of this letter immediately in writing by electronic mail or fax. If you do not intend to submit proposal, we would appreciate being so notified in writing at your earliest opportunity.
9. Attention is drawn to the Procurement Regulations requiring the Borrower to disclose information on the successful Proposer’s beneficial ownership, as part of the Contract Award Notice, using the Beneficial Ownership Disclosure Form as included in the RFP document.
10. The address (es) referred to above is (are): *[insert detailed address (es)]*

*[Insert name of office]*

*[Insert name of officer and title]*

*[Insert postal address and/or street address, postal code, city and country]*

*[Insert telephone number, country and city codes]*

*[Insert facsimile number, country and city codes]*

*[Insert email address]*

*[Insert web site address]*

**Request for Proposals**

**Works and Operation Service**

**(Design, build and operation)**

**of *[WTP/ WWTP]***

**(Single--stage RFP after Initial Selection)**

**Procurement of:**

***[****Insert identification of the Works and Operation Services]* **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Employer:** *[insert the name of the Employer’s agency]*

**Project:***[insert name of project]*

**Contract title:** *[insert the name of the contract]*

**Country:** *[insert country where RFP is issued]*

**Loan No. /Credit No. / Grant No.:** *[insert reference number for loan/ credit/ grant]*

**RFP No:** *[insert RFP reference number from Procurement Plan]*

**Issued on:** *[insert date when RFP is issued to the market]*

**Table of Content**

[PART 1 – Request for Proposal Procedures 3](#_Toc135385778)

[Section I – Instructions to Proposers (ITP) 4](#_Toc135385779)

[Section II – Proposal Data Sheet (PDS) 37](#_Toc135385780)

[Section III – Evaluation and Qualification Criteria 49](#_Toc135385781)

[Section IV – Proposal Forms 57](#_Toc135385782)

[Section V – Eligible Countries 116](#_Toc135385783)

[Section VI – Fraud and Corruption 117](#_Toc135385784)

[PART 2 – Employer’s Requirements 119](#_Toc135385785)

[Section VII – Employer’s Requirements 120](#_Toc135385786)

[PART 3 – Conditions of Contract and Contract Forms 139](#_Toc135385787)

[Section VIII – General Conditions (GC) 140](#_Toc135385788)

[Section IX – Particular Conditions (PC) 141](#_Toc135385789)

[Section X – Contract Forms 209](#_Toc135385790)

PART 1 – Request for Proposal Procedures

Section I – Instructions to Proposers (ITP)

**Table of Content**

[A. General 6](#_Toc135488313)

[1. Scope of Proposal 6](#_Toc135488314)

[2. Source of Funds 7](#_Toc135488315)

[3. Fraud and Corruption 7](#_Toc135488316)

[4. Eligible Proposers 8](#_Toc135488317)

[5. Eligible Materials, Equipment, and Services 11](#_Toc135488318)

[B. Contents of RFP Document 11](#_Toc135488319)

[6. Sections of RFP Document 11](#_Toc135488320)

[7. Clarification of RFP Document, Site Visit, Pre-Proposal Meeting 12](#_Toc135488321)

[8. Amendment of RFP Document 13](#_Toc135488322)

[9. Cost of Proposals 13](#_Toc135488323)

[10. Contacting the Employer 13](#_Toc135488324)

[11. Language of Proposals 13](#_Toc135488325)

[C. Preparation of Proposals 13](#_Toc135488326)

[12. Documents Comprising the Proposal 13](#_Toc135488327)

[13. Letter of Proposal, and Schedules 15](#_Toc135488328)

[14. Alternative Technical Proposals 15](#_Toc135488329)

[15. Proposal Prices 16](#_Toc135488330)

[16. Proposal Currencies 17](#_Toc135488331)

[17. Documents Establishing the Qualification of the Proposer 17](#_Toc135488332)

[18. Documents Establishing Conformity of the Works 18](#_Toc135488333)

[19. Securing the Proposal 18](#_Toc135488334)

[20. Period of Validity of Proposals 20](#_Toc135488335)

[21. Format and Signing of Proposal 21](#_Toc135488336)

[D. Submission of Proposals 21](#_Toc135488337)

[22. Submission, Sealing and Marking of Proposals 21](#_Toc135488338)

[23. Deadline for Submission of Proposals 22](#_Toc135488339)

[24. Late Proposals 23](#_Toc135488340)

[25. Withdrawal, Substitution, and Modification of Proposals 23](#_Toc135488341)

[E. Opening of Technical Parts of Proposals 24](#_Toc135488342)

[26. Opening of Technical Part by Employer 24](#_Toc135488343)

[F. Evaluation of Proposals – General Provisions 25](#_Toc135488344)

[27. Confidentiality 25](#_Toc135488345)

[28. Clarification of Proposals 25](#_Toc135488346)

[29. Deviations, Reservations, and Omissions 26](#_Toc135488347)

[G. Evaluation of Technical Parts of Proposals 26](#_Toc135488348)

[30. Determination of Responsiveness of Technical Parts 26](#_Toc135488349)

[31. Evaluation of Technical Parts 27](#_Toc135488350)

[32. Evaluation of Proposer’s Qualification 27](#_Toc135488351)

[33. Notification of evaluation of Technical Parts 27](#_Toc135488352)

[H. Opening of Financial Parts 28](#_Toc135488353)

[34. Public Opening of Financial Parts when BAFO or negotiations do not apply 28](#_Toc135488354)

[35. Opening of Financial Parts when BAFO or negotiations apply 29](#_Toc135488355)

[I. Evaluation of Financial Part 29](#_Toc135488356)

[36. Nonmaterial Nonconformities 29](#_Toc135488357)

[37. Arithmetic Correction 30](#_Toc135488358)

[38. Conversion to Single Currency 30](#_Toc135488359)

[39. Margin of Preference 30](#_Toc135488360)

[40. Evaluation Process Financial Parts 31](#_Toc135488361)

[41. Abnormally Low Proposals 31](#_Toc135488362)

[42. Unbalanced or Front Loaded Proposals 32](#_Toc135488363)

[J. Evaluation of Combined Technical and Financial Part 32](#_Toc135488364)

[43. Evaluation of Combined Technical and Financial Parts 32](#_Toc135488365)

[44. Best and Final Offer (BAFO) 32](#_Toc135488366)

[45. Most Advantageous Proposal (MAP) 33](#_Toc135488367)

[46. Negotiations 33](#_Toc135488368)

[47. Employer’s Right to Accept Any Proposal, and to Reject Any or All Proposals 33](#_Toc135488369)

[48. Standstill Period 33](#_Toc135488370)

[49. Notification of Intention to Award 33](#_Toc135488371)

[K. Award of Contract 34](#_Toc135488372)

[50. Award Criteria 34](#_Toc135488373)

[51. Notification of Award 34](#_Toc135488374)

[52. Debriefing by the Employer 35](#_Toc135488375)

[53. Signing of Contract 35](#_Toc135488376)

[54. Performance Security 36](#_Toc135488377)

[55. Procurement Related Complaint 36](#_Toc135488378)

# Section I – Instructions to Proposers

 A. General

|  |  |
| --- | --- |
| 1. Scope of Proposal
 | * 1. The Employer, as specified **in the PDS**, issues this Request for Proposals (RFP) Document for the design, build and operation of the Works as specified in Section VII, Employer’s Requirements. The name, identification and number of lots (contracts) of this RFP are specified **in the PDS.**
	2. Unless otherwise stated, throughout this RFP Document definitions and interpretations shall be as prescribed in the Section VIII, General Conditions.
	3. Throughout this RFP Document:
		1. the term **“in writing”** means communicated in written form (e.g. by mail, e-mail, fax, including if specified **in the PDS**, distributed or received through the electronic-procurement system used by the Employer) with proof of receipt;
		2. if the context so requires, “singular” means “plural” and vice versa;
		3. **“Day”** means calendar day, unless otherwise specified as **“Business Day”.** A Business Day is any day that is an official working day of the Borrower. It excludes the Borrower’s official public holidays;
		4. **“Operation Service”** means the operation and maintenance of the Works as provided under the Contract;
		5. **“Works”** refers to Works, subject of this request for proposals document, to be designed and built under the Contract;
		6. **“ES”** means environmental and social (including Sexual Exploitation and Abuse (SEA), and Sexual Harassment (SH));
		7. **“Sexual Exploitation and Abuse” “(SEA)”** means the following:

**Sexual Exploitation** is defined as any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another. **Sexual Abuse** is defined as the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions; * + 1. **“Sexual Harassment” “(SH)”** is defined as unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature by the Contractor’s Personnel with other Contractor’s or Employer’s Personnel;
		2. **“Contractor’s Personnel”** is as defined in Sub-Clause 1.1.21 of the General Conditions; and
		3. **“Employer’s Personnel”** is as defined in Sub-Clause 1.1.34 of the General Conditions.

A non-exhaustive list of (i) behaviors which constitute SEA and (ii) behaviors which constitute SH is attached to the Code of Conduct form in Section IV. |
| 1. Source of Funds
 | * 1. The Borrower or Recipient (hereinafter called “Borrower”) indicated **in the PDS** has applied for or received financing (hereinafter called “funds”) from the International Bank for Reconstruction and Development or the International Development Association (hereinafter called “the Bank”) in an amount specified **in the PDS** toward the project named **in the PDS**. The Borrower intends to apply a portion of the funds to eligible payments under the contract(s) for which this RFP Document is issued.
	2. Payments by the Bank will be made only at the request of the Borrower and upon approval by the Bank in accordance with the terms and conditions of the Loan (or other financing) Agreement between the Borrower and the Bank (hereinafter called the Loan Agreement), and will be subject in all respects to the terms and conditions of that Loan (or other financing) Agreement. The Loan (or other financing) Agreement prohibits a withdrawal from the loan account for the purpose of any payment to persons or entities, or for any import of equipment, materials or any other goods, if such payment or import is prohibited by a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations. No party other than the Borrower shall derive any rights from the Loan (or other financing) Agreement or have any claim to the proceeds of the Loan (or other financing).
 |
| 1. Fraud and Corruption
 | * 1. The Bank requires compliance with the Bank’s Anti-Corruption Guidelines and its prevailing sanctions policies and procedures as set forth in the WBG’s Sanctions Framework, as set forth in Section VI.
	2. In further pursuance of this policy, Proposers shall permit and shall cause their agents (where declared or not), subcontractors, sub-consultants, service providers, suppliers, and personnel, to permit the Bank to inspect all accounts, records and other documents relating to any initial selection process, prequalification process, bid submission, proposal submission and contract performance (in the case of award), and to have them audited by auditors appointed by the Bank.
 |
| 1. Eligible Proposers
 | * 1. A Proposer may be a firm that is a private entity, a state-owned enterprise or institution subject to **ITP 4.6,** or any combination of such entities in the form of a joint venture (JV) under an existing agreement or with the intent to enter into such an agreement supported by a letter of intent. In the case of a joint venture, all members shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms. The JV shall nominate a Representative (Lead Member) who shall have the authority to conduct all business for and on behalf of any and all the members of the JV during the RFP process and, in the event the JV is awarded the Contract, during contract execution. Unless specified **in the PDS**, there is no limit on the number of members in a JV. If specified **in the PDS**, the JV may form an SPV to enter into the Contract and the minimum level of total paid up share capital, lock-in periods for members maintaining their shares and extent to which members can dilute their shareholding shall be as specified **in the PDS**.
	2. A Proposer shall not have a conflict of interest. Any Proposer found to have a conflict of interest shall be disqualified. A Proposer may be considered to have a conflict of interest for the purpose of this RFP process, if the Proposer:
		1. directly or indirectly controls, is controlled by or is under common control with another Proposer; or
		2. receives or has received any direct or indirect subsidy from another Proposer; or
		3. has the same legal representative as another Proposer; or
		4. has a relationship with another Proposer, directly or through common third parties, that puts it in a position to influence the Proposal of another Proposer, or influence the decisions of the Employer regarding this RFP process; or
		5. any of its affiliates participates as a consultant in the preparation of the Employer’s Requirements for the Works that are the subject of the Proposal; or
		6. or any of its affiliates has been hired (or is proposed to be hired) by the Employer or Borrower as the Employer’s Representative for the Contract implementation; or
		7. would be providing goods, works, or non-consulting services resulting from or directly related to consulting services for the preparation or implementation of the project specified **in the PDS ITP 2.1** that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm; or
		8. has a close business or family relationship with a professional staff of the Borrower (or of the project implementing agency, or of a recipient of a part of the loan) who: (i) are directly or indirectly involved in the preparation of the RFP Document or specifications of the Contract, and/or the Proposal evaluation process of such Contract; or (ii) would be involved in the implementation or supervision of such Contract unless the conflict stemming from such relationship has been resolved in a manner acceptable to the Bank throughout the RFP process and execution of the Contract.
	3. A firm that is a Proposer (either individually or as a JV member) shall not participate in more than one Proposal, except for permitted alternative Proposals. This includes participation as a subcontractor in other Proposals. Such participation shall result in the disqualification of all Proposals in which the firm is involved. A firm that is not a Proposer or a JV member may participate as a subcontractor in more than one Proposal.
	4. A Proposer may have the nationality of any country, subject to the restrictions pursuant to **ITP 4.8.** A Proposer shall be deemed to have the nationality of a country if the Proposer is constituted, incorporated or registered in and operates in conformity with the provisions of the laws of that country, as evidenced by its articles of incorporation (or equivalent documents of constitution or association) and its registration documents, as the case may be. This criterion also shall apply to the determination of the nationality of proposed sub-contractors or sub-consultants for any part of the Contract including related Services.
	5. A Proposer that has been sanctioned by the Bank, pursuant to the Bank’s Anti-Corruption Guidelines, and in accordance with its prevailing sanctions policies and procedures as set forth in the World Bank Group’s Sanctions Framework as described in Section VI paragraph 2.2 d., shall be ineligible to be initially selected for, prequalified for, bid for, submit proposal for, or be awarded a Bank-financed contract or benefit from a Bank-financed contract, financially or otherwise, during such period of time as the Bank shall have determined. The list of debarred firms and individuals is available at the electronic address specified **in the PDS**.
	6. Proposers that are state-owned enterprises or institutions in the Employer’s Country may be eligible to compete and be awarded a Contract(s) only if they can establish, in a manner acceptable to the Bank, that they (i) are legally and financially autonomous (ii) operate under commercial law, and (iii) are not under supervision of the Employer.
	7. A Proposer shall not be under suspension from submitting proposals by the Employer as the result of the operation of a Bid or Proposal–Securing Declaration.
	8. Firms and individuals may be ineligible if so indicated in Section V and (a) as a matter of law or official regulations, the Borrower’s country prohibits commercial relations with that country, provided that the Bank is satisfied that such exclusion does not preclude effective competition for the supply of goods or the contracting of works or services required; or (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s country prohibits any import of goods or contracting of works or services from that country, or any payments to any country, person, or entity in that country. When the procurement is implemented across jurisdictional boundaries (and more than one country is a Borrower, and is involved in the procurement), then exclusion of a firm or individual on the basis of **ITP 4.8 (a)** above by any country may be applied to that procurement across other countries involved, if the Bank and the Borrowers involved in the procurement agree.
	9. A Proposer shall provide such documentary evidence of eligibility satisfactory to the Employer, as the Employer shall reasonably request.
	10. A firm that is under a sanction of debarment by the Borrower from being awarded a contract is eligible to participate in this procurement, unless the Bank, at the Borrower’s request, is satisfied that the debarment; (a) relates to fraud or corruption, and (b) followed a judicial or administrative proceeding that afforded the firm adequate due process.
 |
| 1. Eligible Materials, Equipment, and Services
 | * 1. The materials, equipment and services to be supplied under the Contract may have their origin in any country subject to the restrictions specified in Section V, Eligible Countries, and all expenditures under the Contract will not contravene such restrictions. At the Employer’s request, Proposers may be required to provide evidence of the origin of materials, equipment and services.
 |

B. Contents of RFP Document

|  |  |
| --- | --- |
| 1. Sections of RFP Document
 | * 1. The RFP Document consists of Parts 1, 2, and 3, which include all the sections indicated below, and should be read in conjunction with any Addenda issued in accordance with **ITP 8**:

**PART 1 Request for Proposal Procedures**Section I - Instructions to Proposers (ITP)Section II - Proposal Data Sheet (**PDS**)Section III - Evaluation and Qualification Criteria Section IV - Proposal FormsSection V - Eligible CountriesSection VI - Fraud and Corruption**PART 2 Employer’s Requirements**Section VII - Employer’s Requirements **PART 3 Conditions of Contract and Contract Forms**Section VIII - General Conditions Section IX - Particular Conditions Section X - Contract Forms* 1. The Specific Procurement Notice, Notice of Request for Proposals (RFP) issued by the Employer, is not part of this RFP Document.
	2. Unless obtained directly from the Employer, the Employer is not responsible for the completeness of the document, responses to requests for clarification, the Minutes of the pre-Proposal meeting (if any), or Addenda to the RFP Document in accordance with **ITP 8**. In case of any contradiction, documents obtained directly from the Employer shall prevail.
	3. The Proposer is expected to examine all instructions, forms, terms, and specifications in the RFP Document and to furnish with its Proposal all information or documentation as is required by the RFP Document.
 |
| 1. Clarification of RFP Document, Site Visit, Pre-Proposal Meeting
 | * 1. A Proposer requiring any clarification of the RFP Document shall contact the Employer in writing at the Employer’s address specified **in the PDS** or raise its enquiries during the pre-Proposal meeting if provided for in accordance with **ITP 7.4**. The Employer will respond to any request for clarification, provided that such request is received prior to the deadline for submission of Proposals within a period specified **in the PDS.** The Employer shall forward copies of its response to all Proposers who have acquired the RFP Document in accordance with **ITP 6.3**, including a description of the inquiry but without identifying its source. If so specified **in the PDS**, the Employer shall also promptly publish its response at the web page identified **in the PDS**. Should the Employer deem it necessary to amend the RFP Document as a result of a request for clarification, it shall do so following the procedure under **ITP 8**.
	2. The Proposer is advised to visit and examine the Site of the Works and its surroundings and obtain for itself on its own responsibility all information that may be necessary for preparing the Proposal and entering into a contract. The costs of visiting the site shall be at the Proposer’s own expense.
	3. The Proposer and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Proposer, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection.
	4. The Proposer’s designated representative is invited to attend a pre-Proposal meeting and/or a site visit, if provided for **in the PDS**. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. Nonattendance at the pre-Proposal meeting will not be a cause for disqualification of a Proposer.
	5. The Proposer is requested to submit any questions in writing, to reach the Employer not later than one week before the meeting.
	6. Minutes of the pre-Proposal meeting, including the text of the questions raised without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Proposers who have acquired the RFP Document in accordance with **ITP 6.3**. Any modification to the RFP Document that may become necessary as a result of the pre-Proposal meeting shall be made by the Employer exclusively through the issue of an Addendum pursuant to **ITP 8** and not through the minutes of the pre-Proposal meeting.
 |
| 1. Amendment of RFP Document
 | * 1. At any time prior to the deadline for submission of Proposals, the Employer may amend the RFP Document by issuing addenda.
	2. Any addendum issued shall be part of the RFP Document and shall be communicated in writing to all who have obtained the RFP Document from the Employer in accordance with **ITP 6.3.** The Employer shall also promptly publish the addendum on the Employer’s web page in accordance with **ITP 7.1.**
	3. To give prospective Proposers reasonable time in which to take an addendum into account in preparing their Proposals, the Employer may, at its discretion, extend the deadline for the submission of Proposals, pursuant to **ITP 23.2.**
 |
| 1. Cost of Proposals
 | * 1. The Proposer shall bear all costs associated with the preparation and submission of its Proposal, and the Employer will in no case be responsible or liable for those costs.
 |
| 1. Contacting the Employer
 | * 1. From the time of Proposal opening to the time of Contract award, if any Proposer wishes to contact the Employer on any matter related to the Proposal, it should do so in writing.
	2. If a Proposer tries to directly influence the Employer or otherwise interfere in the Proposal evaluation process and the Contract award decision, its Proposal may be rejected.
 |
| 1. Language of Proposals
 | * 1. Unless otherwise specified **in the PDS**, the Proposal prepared by the Proposer and all correspondence and documents related to the Proposal exchanged by the Proposer and the Employer shall be written in the English Language, or, **if the PDS** so provides, in either one of two languages specified there. Any printed literature furnished by the Proposer as part of its Proposal may be in a language not specified **in the PDS,** as long as such literature is accompanied by a translation of its pertinent passages into the language of the Proposal, in which case, for purposes of interpretation of the Proposal, the translation shall govern.
 |

C. Preparation of Proposals

|  |  |
| --- | --- |
| 1. Documents Comprising the Proposal
 | * 1. The Proposal shall comprise two Parts, namely the Technical Part and the Financial Part. These two Parts shall be submitted simultaneously in two separate sealed envelopes (single-stage, two-envelope RFP process). One envelope shall contain only information relating to the Technical Part and the other, only information relating to the Financial Part. These two envelopes shall be enclosed in a separate sealed outer envelope marked “Original Proposal”.
	2. The Technical Part of the Proposal submitted by the Proposer shall comprise the following:
1. **Letter of Proposal** - Technical Part, prepared in accordance with **ITP 13**;
2. **Security**: Proposal Security or Proposal-Securing declaration, in accordance with **ITP 19**;
3. **Alternative Proposal** - Technical Part, if permissible in accordance with **ITP 14**;
4. written confirmation authorizing the signatory of the Proposal to commit the Proposer, in accordance with **ITP 21.1;**
5. documentary evidence that the Proposer continues to be eligible and qualified to perform the contract if its Proposal is accepted;
6. documentary evidence in accordance with **ITP 18** that the Works offered by the Proposer conform to the RFP Document;
7. method statements, equipment, personnel, schedule and any other information as stipulated in Section IV, Proposal Forms;
8. Details of any departures in their Technical Part from the RFP docuemnts;
9. in the case of a Technical Part submitted by a JV, JV agreement, or letter of intent to enter into a JV including a draft agreement, indicating at least the parts of the Works to be executed by the respective partners;
10. list of subcontractors, in accordance with **ITP 18.3**;
11. Sexual Exploitation and Abuse (SEA), and/or Sexual Harassment (SH) Declaration using the form included in Section IV, Proposal Forms; and
12. any other document required **in the PDS**.
	1. The Financial Part of the Proposal submitted by the Proposer shall comprise the following:
13. **Letter of Proposal -** Financial Part prepared in accordance with **ITP 13**;
14. **Schedule of Rates and Prices (if any):** completed in accordance with **ITP 15** and **ITP 16**;
15. **Alternative Proposal – Financial Part:** if permissible in accordance with **ITP 14**;
16. **Financial Disclosure:** The Proposer shall furnish in the Letter of Proposal information on commissions and gratuities, if any, paid or to be paid to agents or any other party relating to this Proposal; and
17. **Other:** any other document required **in the PDS**.
	1. The Technical Part shall not include any financial information related to the Proposal price. Where material financial information related to the Proposal price is contained in the Technical Part, the Proposal shall be declared non-responsive.
	2. The Proposer shall furnish in the Letter of Proposal: Technical Part three names of the potential Dispute Adjudication Board (DAB) members and attach their curriculum vitae. The list of potential DAB members proposed by the Employer (Contract Data 20.3) and by the Proposer (Letter of Proposal) shall be subject to Bank’s No-objection.
 |
| 1. Letter of Proposal, and Schedules
 | * 1. The Proposer shall complete the Letter of Proposal – Technical Part and Letter of Proposal - Financial Part using the relevant forms furnished in Section IV, Proposal Forms. The forms must be completed without any alterations to the text, and no substitutes shall be accepted except as provided under **ITP 21.3**. All blank spaces shall be filled in with the information requested.
 |
| 1. Alternative Technical Proposals
 | * 1. Alternative Proposal - Technical Part: the Proposer wishing to offer alternative technical Proposal shall (i) document that the proposed technical alternatives are to the benefit of the Employer, that they fulfill the principal objectives of the contract, and that they meet the basic performance and technical criteria specified in the RFP Documents; and (ii) further provide all information necessary for a complete technical evaluation of the alternative by the Employer, including as relevant drawings, design calculations, technical specifications, and proposed construction methodology and other relevant details.
	2. Alternative Proposal - Financial Part: The Proposer submitting alternative technical Proposal shall provide all information necessary for a complete financial evaluation of the alternative by the Employer, including breakdown of prices relevant to the offered technical alternative and in the manner and detail called for in the Schedule of Rates and Prices (if any) incuded in Section IV – Proposal Forms**.**
	3. Only the technical alternatives, if any, of the Proposer with the Most Advantageous Proposal conforming to the basic performance and technical criteria specified in the RFP Documents shall be considered by the Employer.
 |
| 1. Proposal Prices
 | * 1. Unless otherwise **specified in the PDS,** Proposers shall quote for the entire Works and Operation Service on a “single responsibility” basis such that the total lump sum Proposal price, subject to any adjustments in accordance with the Contract, covers all the Contractor’s obligations mentioned in or to be reasonably inferred from the RFP Document in respect of the design, manufacture, including procurement and subcontracting (if any), delivery, construction and completion of the Works and operation and maintenance of the Works as set out in the Conditions. This includes all requirements under the Contractor’s responsibilities for testing, pre-commissioning and commissioning (as applicable) of the Works and, where so required by the RFP Document, the acquisition of all permits, approvals and licenses, etc.; the operation, maintenance and training services and such other items and services as may be specified in the RFP Document, all in accordance with the requirements of the General Conditions.
	2. Proposers shall give a breakdown of the prices in the manner and detail called for in the Schedule of Priced Activities and Sub-activities included in Section IV, Proposal Forms with further breakdown prices for sub activities, as appropriate. The total of the prices of the items in the Schedule of Priced Activities is the Proposer’s offer to complete the works on a “single responsibility” basis. The cost of any items that the Proposer may have omitted is deemed to be included in the price of other items in the Schedule of Priced Activities and Sub-activities and will not be paid for separately by the Employer.
	3. The prices shall be either fixed or adjustable as specified **in the PDS**.
	4. In the case of **Fixed Price**, prices quoted by the Proposer shall be fixed during the Proposer’s performance of the contract and not subject to variation on any account. A Proposal submitted with an adjustable price quotation will be treated as non-responsive and rejected.
	5. In the case of **Adjustable Price**, prices quoted by the Proposer shall be subject to adjustment during performance of the contract to reflect changes in the cost elements in accordance with the procedures specified in the corresponding Appendix to the Contract Agreement. A Proposal submitted with a fixed price quotation will not be rejected, but the price adjustment will be treated as zero. Proposers are required to indicate the source of labor and material indices in the corresponding Form in Section IV, Proposal Forms.
	6. If so indicated in **ITP 1.1**, Proposals are being invited for individual lots (contracts) or for any combination of lots (packages). Proposers wishing to offer any price reduction (discount) for the award of more than one Contract shall specify in their Letter of Proposal the price reductions applicable to each package, or alternatively, to individual Contracts within the package, and the manner in which the price reductions will apply. **However, discounts on the condition of award of more that one contract will not be considered for Proposal evaluation purpose.**
	7. Proposers wishing to offer any unconditional discount shall specify in their Letter of Proposal the offered discounts and the manner in which price discounts will apply.
	8. All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of Proposals, shall be included in the Proposal price submitted by the Proposer.
 |
| 1. Proposal Currencies
 | * 1. The currency (ies) of the Proposal and the currency (ies) of payments shall be the same and shall be as specified **in the** **PDS**.
	2. Proposers may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements, and to substantiate that the amounts included in the Schedule of Priced Activities and Sub-activities and shown in the Schedule of Adjustment Data in the Appendix to the Proposal are reasonable, in which case a detailed breakdown of the foreign currency requirements shall be provided by Proposers.
 |
| 1. Documents Establishing the Qualification of the Proposer
 | * 1. In accordance with Section III, Evaluation and Qualification Criteria, to establish that the Proposer continues to meet the qualification criteria used at the time of Initial Selection, the Proposer shall provide updated information on any assessed aspect that changed from that time including on Sexual Exploitation and Abuse (SEA) / Sexual Harassment (SH) disqualification status.
	2. If a margin of preference applies as specified in accordance with **ITP 39.1**, domestic Proposers, individually or in joint ventures, applying for eligibility for domestic preference shall supply all information required to satisfy the criteria for eligibility specified in accordance with **ITP 39.1**.
	3. Any change in the structure or formation of a Proposer after being initially selected and invited to submit Proposals (including, in the case of a JV, any change in the structure or formation of any member and also including any change in any Specialized Subcontractor) shall be subject to the written approval of the Employer prior to the deadline for submission of Proposals. Such approval shall be denied if (i) a Proposer proposes to associate with a disqualified Proposer or in case of a disqualified joint venture, any of its members; (ii) as a consequence of the change, the Proposer no longer substantially meets the qualification criteria set forth in the Initial Selection Documents Section or (iii) no longer continues to be in the list of Initially Selected Proposers as a result of the Employer’s re-evaluation of the Application in accordance with criteria specified in the Initial Selection Documents; or (iv) in the opinion of the Employer, the change may result in a substantial reduction in competition. Any such change should be submitted to the Employer not later than fourteen (14) days after the Notice of Request for Proposals.
 |
| 1. Documents Establishing Conformity of the Works
 | * 1. Pursuant to **ITP 12.2 (f),** the Proposer shall furnish, as part of its Proposal documents establishing the conformity to the RFP Documents of the Works that the Proposer proposes to design and build under the Contract.
	2. The documentary evidence of the conformity of the Works and Operation Service with the RFP documents may be in the form of literature, drawings and data, and shall include:
		+ - 1. the documents specified in Section IV (Proposal Forms)- Technical Proposal;
				2. detailed description of the essential technical and functional / performance characteristics of the proposed Works, in response to the Employer’s Requirements; and
				3. adequate evidence demonstrating the substantial responsiveness of the Works and the Operation Service to the Employer’s Requirements. Proposers shall note that standards for workmanship, materials and equipment designated by the Employer in the RFP Document are intended to be descriptive (establishing standards of quality and performance) only and not restrictive. The Proposer may substitute alternative standards, in its technical Proposal, provided that it demonstrates to the Employer’s satisfaction that the substitutions are substantially equivalent or superior to the standards designated in the Performance / Functional requirements specified by the Employer.
	3. The Proposer shall be responsible for ensuring that any proposed subcontractor complies with the requirements of **ITP 4**, and that any Works to be provided by the subcontractor comply with the requirements of **ITP 5** and **ITP 18.1.**
 |
| 1. Securing the Proposal
 | * 1. The Proposer shall furnish as part of its Proposal, either a Proposal-Securing Declaration or a Proposal Security as specified **in the PDS**, in original form and, in the case of a Proposal Security, in the amount and currency specified **in the PDS**.
	2. A Proposal-Securing Declaration shall use the form included in Section IV, Proposal Forms.
	3. If a Proposal Security is specified pursuant to **ITP 19.1**, the Proposal security shall be a demand guarantee in any of the following forms at the Proposer’s option:
	4. an unconditional guarantee issued by a bank or a non-bank financial institution (such as an insurance, bonding or surety company);
	5. an irrevocable letter of credit;
	6. a cashier’s or certified check; or
	7. another security indicated **in the PDS**,

from a reputable source from an eligible country. If an unconditional guarantee is issued by a non-bank financial institution located outside the Employer’s Country the issuing non-bank financial institution shall have a correspondent financial institution located in the Employer’s Country to make it enforceable unless the Employer has agreed in writing, prior to Proposal submission, that a correspondent financial institution is not required.* 1. In the case of a bank guarantee, the Proposal Security shall be submitted either using the Proposal Security Form included in Section IV, Proposal Forms or in another substantially similar format approved by the Employer prior to Proposal submission. In either case, the form must include the complete name of the Proposer. The Proposal Security shall be valid for twenty-eight days (28) beyond the original date of expiry of the Proposal validity, or beyond any extended date if requested under r **ITP 20.2.**
	2. If a Proposal Security or a Proposal-Securing Declaration is specified pursuant to **ITP 19.1**, any Proposal not accompanied by a substantially responsive Proposal Security or Proposal-Securing Declaration shall be rejected by the Employer as non-responsive.
	3. If a Proposal Security is specified in accordance with **ITP 19.1**, the Proposal Security of the Proposers shall be returned as promptly as possible once the successful Proposer has signed the Contract, furnished the required Performance Security, and if required **in the PDS**, the Environmental and Social (ES) Performance Security.
	4. The Proposal Security may be forfeited:
1. if a Proposer withdraws its Proposal prior to the expiry date of the Proposal validity specified by the Proposer on the Letter of Proposal or any extended date provided by the Proposer; or
2. if the successful Proposer fails to:
	1. sign the Contract in accordance with **ITP 53**; or
	2. furnish a Performance Security and if required **in the PDS**, the Environmentaland Social (ESHS) Performance Security, in accordance with **ITP 54.**
	3. The Proposal Security or the Proposal-Securing Declaration of a JV shall be in the name of the JV that submits the Proposal. If the JV has not been legally constituted into a legally enforceable JV at the time of submission of Proposals, the Proposal Security or the Proposal-Securing Declaration shall be in the names of all future members as named in the letter of intent referred to in **ITP 4.1.**
	4. If a Proposal Security is not required **in the PDS**, and:
		* + 1. if a Proposer withdraws its Proposal prior to the expiry date of the Proposal validity specified by the Proposer on the Letter of Proposal or any extended date provided by the Proposer; or
				2. if the successful Proposer fails to:
3. sign the Contract in accordance with **ITP 53;** or
4. furnish a performance security and if required **in the PDS**, the Environmental and Social(ES) Performance Security, in accordance with **ITP 54**,

the Employer may, if provided for **in the PDS**, declare the Proposer disqualified to be awarded a contract by the Employer for a period of time as stated **in the PDS**. |
| 1. Period of Validity of Proposals
 | * 1. Proposals shall remain valid until the date specified **in the** **PDS** or any extended date if amended by the Employer in accordance with ITP 8. A Proposal that is not valid until the date specified **in the PDS,** or any extended date if amended by the Employer in accordance with ITP 8, shall be rejected by the Employer as nonresponsive.
	2. In exceptional circumstances, prior to the date of expiry of the Proposal validity, the Employer may request that the Proposers extend the date of of validity until a specified date. The request and the responses to the request shall be made in writing. A Proposer may refuse the request without risking execution of the Proposal-Securing Declaration or forfeiting the Proposal Security. Except as provided in **ITP 20.3**, a Proposer agreeing to the request will not be required or permitted to modify its Proposal, but will be required to ensure that the Proposal Security is extended for a correspondingly longer period, pursuant to **ITP 19.4**.
	3. In the case of fixed price contracts, if the award is delayed by a period exceeding fifty-six (56) days beyond the date of expiry of the Proposal validity specified in accordance with ITP 20.1, the contract price will be adjusted as specified **in the PDS**. Proposal evaluation will be based on the Proposal prices without taking into consideration the above correction.
 |
| 1. Format and Signing of Proposal
 | * 1. The original and all copies of the Proposal, each consisting of the documents listed in **ITP 12**, shall be typed or written in indelible ink and shall be signed by a person or persons duly authorized to sign on behalf of the Proposer. The authorization must be in writing as specified **in the PDS**, and included in the Proposal pursuant to **ITP 12.2(d).** The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the Proposal where entries or amendments have been made shall be signed or initialed by the person signing the Proposal.
	2. In case the Proposer is a JV, the Proposal shall be signed by an authorized representative of the JV on behalf of the JV, and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives.
	3. The Proposal shall contain no interlineations, erasures, or overwriting, except to correct errors made by the Proposer, in which case such corrections shall be initialed by the person or persons signing the Proposal.
	4. The Proposer shall furnish in the Proposal Submission Form (Section IV) information regarding commissions or gratuities, if any, paid or to be paid to agents relating to this procurement and to the execution of the Contract should the Proposer be successful.
 |

D. Submission of Proposals

|  |  |
| --- | --- |
| 1. Submission, Sealing and Marking of Proposals
 | * 1. Unless the **PDS** states that Proposals are to be submitted electronically the following procedures shall apply.
		+ - 1. The Proposer shall deliver the Proposal in two separate, sealed envelopes. One envelope containing the Technical Part and the other the Financial Part. These two envelopes shall be enclosed in a sealed outer envelope and clearly marked “Proposal - Original”.
				2. In addition, the Proposer shall prepare copies of the Proposal, in the number specified **in the PDS**. Copies of the Technical Part shall be placed in a separate sealed envelope marked “Copies: Technical Part”. Copies of the Financial Part shall be placed in a separate sealed envelope marked “Copies: Financial Part”. The Proposer shall place both of these envelopes in a separate, sealed outer envelope marked “Proposal - Copies”. In the event of any discrepancy between the original and the copies, the original shall prevail.
				3. If alternative Proposals are permitted in accordance with **ITP 14**, the alternative Proposals shall be submitted as follows: the original of the alternative Proposal Technical Part shall be placed in a sealed envelope marked “Alternative Proposal – Technical Part” and the Financial Part shall be placed in a sealed envelope marked “Alternative Proposal – Financial Part” and these two separate sealed envelopes then enclosed within a sealed outer envelope marked “Alternative Proposal – Original”, the copies of the alternative Proposal will be placed in separate sealed envelopes marked “Alternative Proposal – Copies Of Technical Part”, and “Alternative Proposal – Copies Of Financial Part” and enclosed in a separate sealed outer envelope marked “Alternative Proposal - Copies”
	2. The inner and outer envelopes shall:
		+ - 1. bear the name and address of the Proposer;
				2. be addressed to the Employer, at the address given **in the PDS** for **ITP 23.1**; and
				3. bear the Contract(s) name, the Invitation for Proposals (RFP) title and number, as specified **in the PDS** for **ITP 1.1**, and the statement “Do Not Open Before [time and date],” to be completed with the time and date specified **in the PDS** for **ITP 23.1**.
	3. If the outer envelope is not sealed and marked as required by **ITP 22.1** and **ITP 22.2,** the Employer will assume no responsibility for the Proposal’s misplacement or premature opening.
 |
| 1. Deadline for Submission of Proposals
 | * 1. Proposals must be received by the Employer at the address specified, and no later than the time and date specified, **in the PDS**. Proposers have the option of submitting their Proposals electronically if specified **in the PDS**.
	2. The Employer may, at its discretion, extend the deadline for submission of Proposals by amending the RFP Documents in accordance with **ITP 8.3**, in which case all rights and obligations of the Employer and Proposers will thereafter be subject to the deadline as extended.
 |
| 1. Late Proposals
 | * 1. The Employer shall not consider any Proposal that arrives after the deadline for submission of Proposals, in accordance with **ITP 23.** Any Proposal received by the Employer after the deadline for submission of Proposals shall be declared late, rejected, and returned unopened to the Proposer.
 |
| 1. Withdrawal, Substitution, and Modification of Proposals
 | * 1. A Proposer may withdraw, substitute, or modify its Proposal after it has been submitted, and before the deadline for submission of Proposals, by sending a written notice, duly signed by an authorized representative, including a copy of the authorization in accordance with **ITP 21.1**, (except that withdrawal notices do not require copies). The corresponding substitution or modification of the Proposal must accompany the respective written notice. All notices must be:
		+ - 1. prepared and submitted in accordance with **ITP 21** and **ITP 22** (except that withdrawals notices do not require copies), and in addition, the respective envelopes shall be clearly marked “Withdrawal,” “Substitution, (“Technical Part” and/or “Financial Part”)” “Modification (“Technical Part” and/or “Financial Part”);” and
				2. received by the Employer prior to the deadline prescribed for submission of Proposals, in accordance with **ITP 23**.
 |

E. Opening of Technical Parts of Proposals

|  |  |
| --- | --- |
| 1. Opening of Technical Part by Employer
 | * 1. Except as in the cases specified in **ITP 24 and ITP 25**, the Employer shall conduct the Technical Part opening in public, in the presence of Proposers` designated representatives and anyone who chooses to attend, and at the address, date and time specified **in the PDS**. Any specific electronic Proposal opening procedures, if permitted, shall be as specified **in the PDS**.
	2. First, the written notice of withdrawal in the envelopes marked “Withdrawal” shall be opened and read out and the envelope with the corresponding Proposal shall not be opened, but returned to the Proposer. No Proposal withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at Proposal opening.
	3. Next, envelopes marked “Substitution” shall be opened and read out and exchanged with the corresponding Technical Part being substituted, and the substituted Proposal shall not be opened, but returned to the Proposer. No Proposal substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at Proposal opening.
	4. Next, envelopes marked “Modification” shall be opened and read out with the corresponding Proposal. No Proposal modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at Proposal opening.
	5. Next, all other envelopes marked “Technical Part” shall be opened one at a time. All envelopes marked “Financial Part” shall remain sealed and kept by the Employer in safe custody until they are opened, at a later public opening, following the evaluation of the Technical Part of the Proposals. On opening the Technical Part envelopes, the Employer shall read out: the name of the Proposer and whether there is a modification; the presence or absence of a Proposal securityor a Proposal-Securing Declaration; and other details as the Employer, at its discretion, may consider appropriate.
	6. Only Technical Parts of Proposals and Alternative Proposal - Technical Parts that are opened and read out at Proposal opening shall be considered further. At the Proposal opening the Employer shall neither discuss the merits of any Proposal nor reject any Proposal (except for late Proposals, in accordance with **ITP 24.1**).
	7. The Employer shall prepare a record of the Technical Parts of public opening that shall include, as a minimum: the name of the Proposer and whether there is a withdrawal, substitution, or modification. The Proposers’ representatives who are present shall be requested to sign the record. The omission of a Proposer’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Proposers who submitted Proposals in time, and posted online when electronic procurement is permitted.
 |

F. Evaluation of Proposals – General Provisions

|  |  |
| --- | --- |
| 1. Confidentiality
 | * 1. Information relating to the evaluation of the Technical Part shall not be disclosed to Proposers or any other persons not officially concerned with the RFP process until the notification of evaluation of the Technical Part in accordance with **ITP 33**. Information relating to the evaluation of the Financial Part, the evaluation of combined Technical Part and Financial Part, and the recommendation of contract award shall not be disclosed to Proposers or any other persons not officially concerned with such process until the Notification of Intention to Award the Contract is transmitted to Proposers in accordance with ITP 49.1.
	2. Information relating to the evaluation of the Financial Part and recommendation of contract award, shall not be disclosed to Proposers or any other persons not officially concerned with the RFP process until the Notification of Intention to Award the Contract is transmitted to all Proposers in accordance with **ITP 49**.
	3. Any effort by a Proposer to influence the Employer in the evaluation of the Proposals may result in the rejection of its Proposal.
	4. Notwithstanding **ITP 27.1 and ITP 27.2**, from the time of Proposal opening to the time of Contract award, if any Proposer wishes to contact the Employer on any matter related to the RFP process, it should do so in writing.
 |
| 1. Clarification of Proposals
 | * 1. To assist in the examination, evaluation, and comparison of the Proposals, and qualification of the Proposers, the Employer may, at its discretion, ask any Proposer for a clarification of its Proposal. Any clarification submitted by a Proposer that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing.
	2. If a Proposer does not provide clarifications of its Proposal by the date and time set in the Employer’s request for clarification, its Proposal may be rejected.
 |
| 1. Deviations, Reservations, and Omissions
 | * 1. During the evaluation of Proposals, the following definitions apply:
		+ - 1. “Deviation” is a departure from the requirements specified in the RFP document;
				2. “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the RFP document; and
				3. “Omission” is the failure to submit part or all of the information or documentation required in the RFP document.
 |

G. Evaluation of Technical Parts of Proposals

|  |  |
| --- | --- |
| 1. Determination of Responsiveness of Technical Parts
 | * 1. The Employer will examine the Technical Parts, including any alternatives submitted by Proposers, to determine whether they are complete, have been properly signed, and are generally in order.
	2. The Employer’s determination of a Technical Part’s substantial responsiveness is to be based on the contents of the Proposal itself. For purposes of this determination, a substantially responsive Proposal is one that materially conforms to the requirements of the RFP Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that:
		+ - 1. if accepted, would:
1. affect in any substantial way the scope, quality, or performance of the Works specified in the Contract; or
2. limit in any substantial way, inconsistent with the RFP Document, the Employer’s rights or the Proposer’s obligations under the proposed Contract; or
	* + - 1. if rectified, would unfairly affect the competitive position of other Proposers presenting substantially responsive Proposals.
	1. Provided that a Technical Part is substantially responsive, the Employer may waive any nonmaterial nonconformity in the Proposal.
	2. Provided that a Proposal is substantially responsive, the Employer may request that the Proposer submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Proposal related to documentation requirements.
 |
| 1. Evaluation of Technical Parts
 | * 1. The Employer’s evaluation of technical proposals will be carried out as specified in Section III, Evaluation and Qualification Criteria.
	2. The scores to be given to technical factors and sub factors are specified **in the PDS**.
 |
| 1. Evaluation of Proposer’s Qualification
 | * 1. The Employer shall determine to its satisfaction that, on the basis of updated documentary evidence submitted in accordance with **ITP 12.2 (e),** andSection III- Evaluation and Qualification Criteria, the Proposer continues to be qualified to satisfactorily perform the Contract.
	2. Prior to Contract award, the Employer will verify that the successful Proposer (including each member of a JV) is not disqualified by the Bank due to noncompliance with contractual SEA/SH prevention and response obligations. The Employer will conduct the same verification for each subcontractor proposed by the successful Proposer. If any proposed subcontractor does not meet the requirement, the Employer will require the Proposer to propose a replacement subcontractor.
	3. Only Proposals that are both substantially responsive to the RFP document and are qualified shall have their envelopes marked “Financial Part” opened at the second public opening.
 |
| 1. Notification of evaluation of Technical Parts
 | * 1. Following the completion of the evaluation of the Technical Parts of Proposals, the Employer shall make the following notifications:
		+ - 1. Notify in writing those Proposers whose Proposals were considered substantially non-responsive to the requirements in the RFP, advising them of the following information:
		1. the grounds on which their Technical Part has been considered to be non-responsive;
		2. their envelope marked “Financial Part” will be returned to them unopened after the completion of the Proposal evaluation process and the signing of the Contract;
			+ 1. simultaneously, notify in writing those Proposers whose Proposals were considered substantially responsive to the requirements in the RFP, advising them that their Proposal has been evaluated as substantially responsive to the RFP; and
				2. notify all Proposers in accordance with the one of following two options:
1. Option 1: when **BAFO or Negotiations is not to be applied,** the date, time and location of the public opening of the envelopes marked ‘Financial Part”, or;
2. Option 2: when BAFO or Negotiations apply as specified **in the PDS ITP 44** and **ITP 46** respectively, that: (i) the envelopes marked ‘Financial Part’ will not be opened in public, but in the presence of a Probity Assurance Provider (Probity Auditor) appointed by the Employer, and that (ii) the announcement of the names of the Proposers whose Financial Parts will be opened and the total Proposal prices will be deferred to the time that the Notification of Intention to Award the contract is issued.
 |

H. Opening of Financial Parts

|  |  |
| --- | --- |
| 1. Public Opening of Financial Parts when BAFO or negotiations do not apply
 | * 1. When BAFO or negotiations do not apply as specified **in the PDS**, the Financial Parts will be opened in public by the Employer in the presence of Proposers, or their designated representatives, and anyone else who chooses to attend. The opening date shall be no less than ten (10) Business Days from the date of notification of the results of the technical evaluation, described in ITP 33.1. However, if the Employer receives a complaint on the results of the technical evaluation within the ten (10) Business Days, the opening date shall be subject to ITP 55.1. Each envelope marked “Financial Part” shall be inspected to confirm that it has remained sealed and unopened. These envelopes shall then be opened by the Employer. The Employer shall read out the names of each Proposer, the technical score, the total Proposal prices, per lot (contract) if applicable, including any discounts, the presence or absence of a Proposal Security or Proposal-Securing Declaration, if required and any other details as the Employer may consider appropriate. Only discounts read out at the public opening shall be considered for evaluation. The Letter of Proposal - Financial Part and the Schedule of Rates and Prices (if any) are to be initialed by representatives of the Employer attending the public opening in the manner specified **in the PDS**.
	2. The Employer shall prepare a record of the Financial Part of the Proposal opening that shall include, as a minimum:
		+ - 1. the name of the Proposers whose Financial Part was opened;
				2. the Proposal prices, per lot (contract) if applicable, including any discounts.
	3. The Proposers whose envelopes marked “Financial Part” have been opened, or their representatives who are present, shall be requested to sign the record. The omission of a Proposer’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Proposers.
 |
| 1. Opening of Financial Parts when BAFO or negotiations apply
 | * 1. When, as specified **in the PDS**, BAFO or negotiations apply the Financial Parts will not be opened in public, and will be opened in the presence of a Probity Assurance Provider appointed by the Employer.
	2. At the opening each of the envelopes marked “Financial Part” shall be inspected to confirm that they have remained sealed and unopened. These envelopes shall then be opened by the Employer. The Employer shall record the names of each Proposer, and the total Proposal prices and any other details as the Employer may consider appropriate. The Letter of Proposal - Financial Part and the Schedule of Rates and Prices (if any) are to be initialed by representatives of the Employer attending the public opening and by the Probity Assurance Provider.
	3. The Employer shall prepare a record of the opening of the Financial Part envelopes that shall include, as a minimum:
		+ - 1. the name of the Proposers whose Financial Part was opened;
				2. the Proposal prices including any discounts. And
				3. the Probity Assurance Provider’s report of the opening of the Financial Part.
	4. The Probity Assurance Provider shall sign the record. The contents of the envelopes marked ‘Financial Part’ and the record of the opening shall be kept in safe custody by the Employer and not disclosed to anyone until the time of the transmission of the Notification of Intention to Award the contract.
 |

I. Evaluation of Financial Part

|  |  |
| --- | --- |
| 1. Nonmaterial Nonconformities
 | * 1. Provided that a Proposal is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Proposal Price. To this effect, the Proposal Price shall be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component by adding the average price of the item or component quoted by substantially responsive Proposers. If the price of the item or component cannot be derived from the price of other substantially responsive Proposers, the Employer shall use its best estimate.
 |
| 1. Arithmetic Correction
 | * 1. The Employer shall correct arithmetical errors on the following basis:
		+ - 1. **Priced Sub-activity Schedule:** where there are errors between the total of the amounts given under the column for Sub-activity Price and the amount given under the total for the Sub-activity, the former shall prevail and the latter will be corrected accordingly;
				2. **Priced Activity Schedule:** where there are errors between the total of the amounts given under the column for the Activity Price and the amount given under the total price of Activities, the former shall prevail and the latter will be corrected accordingly;
				3. where there are errors between the total of the amounts in the Priced Sub-activity Schedule and the corresponding amount in the Priced Activity Schedule, the former shall prevail and the latter will be corrected accordingly;
				4. **Grand Summary:** where there are errors between the total price of Activities in the Schedule of Priced Activities and the amount given in Grand Summary, the former shall prevail and the latter will be corrected accordingly; and
				5. if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) to (d) above.
	2. A Proposer shall be requested to accept the correction of arithmetical errors. Failure to accept the correction in accordance with **ITP 37.1** shall result in the rejection of the Proposal.
 |
| 1. Conversion to Single Currency
 | * 1. For evaluation and comparison purposes, the currency (ies) of the Proposal shall be converted into a single currency as specified **in the PDS.**
 |
| 1. Margin of Preference
 | * 1. Unless otherwise specified **in the** **PDS,** a margin of preference for domestic Proposers[[11]](#footnote-11) shall not apply.
 |
| 1. Evaluation Process Financial Parts
 | * 1. To evaluate each Proposal’s Financial Part, the Employer shall consider the following:
		+ - 1. the Proposal price, excluding provisional sums and the provision, if any, for contingencies in the Schedule of Rates and Prices (if any);
				2. price adjustment for correction of arithmetic errors in accordance with **ITP 37.1**;
				3. price adjustment due to discounts offered in accordance with **ITP 15.7**;
				4. price adjustment due to quantifiable nonmaterial nonconformities in accordance with **ITP 36.1**;
				5. converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with **ITP 38.1**; and
				6. any additional evaluation factors indicated **in the PDS** and detailed in Section III, Evaluation and Qualification Criteria.
	2. If price adjustment is allowed in accordance with **ITP 15.5**, the estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in Proposal evaluation.
	3. If this RFP allows Proposers to quote separate prices for different lots (contracts), each lot will be evaluated separately to determine the Most Advantageous Proposal using the methodology specified in Section III, Evaluation and Qualification Criteria. **Discounts that are conditional on the award of more than one lot, or slice shall not be considered for Proposal evaluation.**
 |
| 1. Abnormally Low Proposals
 | * 1. An Abnormally Low Proposal is one where the Proposal price, in combination with other elements of the Proposal, appears so low that it raises material concerns as to the capability of the Proposer to perform the Contract for the offered Proposal Price.
	2. In the event of identification of a potentially Abnormally Low Proposal, the Employer shall seek written clarifications from the Proposer, including detailed price analyses of its Proposal price in relation to the subject matter of the contract, scope, proposed methodology, schedule, allocation of risks and responsibilities and any other requirements of the RFP Document.
	3. After evaluation of the price analyses, in the event that the Employer determines that the Proposer has failed to demonstrate its capability to perform the Contract for the offered Proposal Price, the Employer shall reject the Proposal.
 |
| 1. Unbalanced or Front Loaded Proposals
 | * 1. If the Proposal that is evaluated as the lowest evaluated cost is, in the Employer’s opinion, seriously unbalanced or front loaded the Employer may require the Proposer to provide written clarifications. Clarifications may include detailed price analyses to demonstrate the consistency of the Proposal prices with the scope of the Works, proposed methodology, schedule and any other requirements of the RFP Document.
	2. After the evaluation of the information and detailed price analyses presented by the Proposer, the Employer may:
		+ - 1. accept the Proposal, or
				2. if appropriate, require that the total amount of the Performance Security be increased, at the expense of the Proposer, to a level not exceeding twenty percent (20%) of the Contract Price; or
				3. reject the Proposal.
 |

J. Evaluation of Combined Technical and Financial Part

|  |  |
| --- | --- |
| 1. Evaluation of Combined Technical and Financial Parts
 | * 1. The Employer’s evaluation of responsive Proposals will take into account technical factors, in addition to cost factors in accordance with Section III Evaluation and Qualification Criteria. The weight to be assigned for the Technical factors and cost is specified **in the PDS**. The Employer will rank the proposals based on the evaluated Proposal score (B).
 |
| 1. Best and Final Offer (BAFO)
 | * 1. After completion of the combined technical and financial evaluation of proposals, if specified **in the PDS**, the Employer may invite those Proposers to submit their BAFOs. The procedure for submitting BAFOs will be specified **in the PDS**. BAFO is a final opportunity for Proposers to improve their Proposals without changing the specified business function and performance requirements in accordance with the RFP Documents. Proposers are not obliged to submit a BAFO. Where BAFO is used there will be no negotiation after BAFO.
	2. BAFO will apply a two envelope procurement process. The submission of BAFOs, opening of the Technical Parts and Financial Parts and the evaluation of Proposals will follow the procedures described for the Technical, Financial and Combined evaluation above, as appropriate.
 |
| 1. Most Advantageous Proposal (MAP)
 | * 1. The Most Advantageous Proposal is the Proposal of the Proposer that meets the Qualification Criteria, and whose Proposal has been determined to be:
		+ - 1. substantially responsive to the RFP; and
				2. the best evaluated Proposal i.e. the highest scoring Proposal, in the combined technical and financial evaluation.
 |
| 1. Negotiations
 | * 1. If specified **in the PDS**, the Employer may conduct negotiations following the evaluation of Proposals and before the final contract award. The procedure of the negotiations will be specified **in the PDS**.
	2. Negotiations shall be held in the presence of Probity Assurance Provider appointed by the Employer.
	3. Negotiations may address any aspect of the contract so long as they do not change the specified business function and performance requirements.
	4. The Employer may negotiate first with the Proposer that has the Most Advantageous Proposal. If the negotiations are unsuccessful the Employer may negotiate with the Proposer that has the next best Most Advantageous Proposal, and so on down the list until a successful negotiated outcome is achieved.
 |
| 1. Employer’s Right to Accept Any Proposal, and to Reject Any or All Proposals
 | * 1. The Employer reserves the right to accept or reject any Proposal, and to annul the RFP process and reject all Proposals at any time prior to contract award, without thereby incurring any liability to Proposers. In case of annulment, all Proposals submitted and specifically, Proposal securities shall be promptly returned to the Proposers.
 |
| 1. Standstill Period
 | * 1. The Contract shall not be awarded earlier than the expiry of the Standstill Period. The Standstill Period shall be ten (10) Business Days unless extended in accordance with **ITP 52**. The Standstill Period commences the day after the date the Employer has transmitted to each Proposer (that has not already been notified that it has been unsuccessful) the Notification of Intention to Award the Contract. Where only one Proposal is submitted, or if this contract is in response to an emergency situation recognized by the Bank, the Standstill Period shall not apply.
 |
| 1. Notification of Intention to Award
 | * 1. The Employer shall send to each Proposer (that has not already been notified that it has been unsuccessful) the Notification of Intention to Award the Contract to the successful Proposer. The Notification of Intention to Award shall contain, at a minimum, the following information:
		+ - 1. the name and address of the Proposer submitting the successful Proposal;
				2. the Contract price of the successful Proposal;
				3. the total combined score of the successful Proposal;
				4. the names of all Proposers who submitted Proposals, and their Proposal prices as readout and as evaluated prices and technical score;
				5. a statement of the reason(s) the Proposal (of the unsuccessful Proposer to whom the notification is addressed) was unsuccessful;
				6. the expiry date of the Standstill Period; and
				7. instructions on how to request a debriefing or submit a complaint during the standstill period.
 |

K. Award of Contract

|  |  |
| --- | --- |
| 1. Award Criteria
 | * 1. Subject to **ITP 47.1***,* the Employer shall award the Contract to the Proposer with the Most Advantageous Proposal, provided that the Proposer is determined to be eligible and qualified to perform the Contract satisfactorily.
 |
| 1. Notification of Award
 | * 1. Prior to the date of expiry of the Proposal validity, and upon expiry of the Standstill Period, specified in **ITP 48.1** or any extension thereof, and upon satisfactorily addressing any complaint that has been filed within the Standstill Period, the Employer shall notify the successful Proposer, in writing, that its Proposal has been accepted. The notification of award (hereinafter and in the Conditions of Contract and Contract Forms called the “Letter of Acceptance”) shall specify the sum that the Employer will pay the Contractor in consideration of the execution of the Contract (hereinafter and in the Conditions of Contract and Contract Forms called “the Contract Price”).
	2. Within ten (10) Business days from the transmission of the Letter of Acceptance, the Employer shall publish the Contract Award Notice which shall contain, at a minimum, the following information:
		+ - 1. name and address of the Employer;
				2. name and reference number of the contract being awarded, and the selection method used;
				3. names of all Proposers that submitted Proposals, and their Proposal prices as read out at Proposal opening, and as evaluated;
				4. name of Proposers whose Proposals were rejected and the reasons for their rejection;
				5. the name of the successful Proposer, the final total contract price, the contract duration and a summary of its scope; and
				6. successful Proposer’s Beneficial Ownership Disclosure Form.
	3. The Contract Award Notice shall be published on the Employer’s website with free access if available, or in at least one newspaper of national circulation in the Employer’s Country, or in the official gazette. The Employer shall also publish the contract award notice in UNDB online.
	4. Until a formal contract is prepared and executed, the Letter of Acceptance shall constitute a binding Contract.
 |
| 1. Debriefing by the Employer
 | * 1. On receipt of the Borrower’s Notification of Intention to Award referred to in **ITP 49**, an unsuccessful Proposer has three (3) Business Days to make a written request to the Employer for a debriefing. The Employer shall provide a debriefing to all unsuccessful Proposers whose request is received within this deadline.
	2. Where a request for debriefing is received within the deadline, the Employer shall provide a debriefing within five (5) Business Days, unless the Employer decides, for justifiable reasons, to provide the debriefing outside this timeframe. In that case, the standstill period shall automatically be extended until five (5) Business Days after such debriefing is provided. If more than one debriefing is so delayed, the standstill period shall not end earlier than five (5) Business Days after the last debriefing takes place. The Employer shall promptly inform, by the quickest means available, all Proposers of the extended standstill period.
	3. Where a request for debriefing is received by the Employer later than the three (3)-Business Day deadline, the Employer should provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of Public Notice of Award of contract. Requests for debriefing received outside the three (3)-day deadline shall not lead to extension of the standstill period.
	4. Debriefings of unsuccessful Proposers may be done in writing or verbally. The Proposers shall bear their own costs of attending such a debriefing meeting.
 |
| 1. Signing of Contract
 | * 1. The Employer shall send to the successful Proposer the Letter of Acceptance including the Contract Agreement and a request to submit the Beneficial Ownership Disclosure Form providing additional information on its beneficial ownership. The Beneficial Ownership Disclosure Form shall be submitted within eight (8) Business Days of receiving this request.
	2. The successful Proposer shall sign, date and return to the Employer, the Contract Agreement within twenty-eight (28) days of its receipt.
 |
| 1. Performance Security
 | * 1. Within twenty-eight (28) days of the receipt of the Letter of Acceptance from the Employer, the successful Proposer shall furnish the Performance Security and if required **in the PDS**, the Environmental and Social (ES) Performance Security, in accordance with the General Conditions, subject to **ITP 42.2 (b),** using the Performance Security and ES Performance Security Forms included in Section X, Contract Forms, or another form acceptable to the Employer. If the performance security furnished by the successful Proposer is in the form of a bond, it shall be issued by a bonding or insurance company that has been determined by the successful Proposer to be acceptable to the Employer. A foreign institution providing a bond shall have a correspondent financial institution located in the Employer’s Country, unless the Employer has agreed in writing that a correspondent financial institution is not required.
	2. Failure of the successful Proposer to submit the above-mentioned Performance Security and if required **in the PDS**, the Environmental and Social (ES) Performance Security, or sign the Contract shall constitute sufficient grounds for the annulment of the award and forfeiture of the Proposal security. In that event the Employer may award the Contract to the Proposer with the next Most Advantageous Proposal.
	3. If permitted in the PDS and the Proposer has requested to form an SPV, the Proposer shall form the SPV and provide within twenty-eight (26) days of receipt of the Letter of Acceptance from the Employer a certified copy of its constituent documents and evidence of its shareholding structure including the articles of association and shareholder agreement (if any).
 |
| 1. Procurement Related Complaint
 | * 1. The procedures for making a Procurement-related Complaint are as specified **in the PDS**.
 |

Section II – Proposal Data Sheet (PDS)

The following specific data for the proposed Works shall complement, supplement, or amend the provisions in the Instructions to Proposers (ITP). Whenever there is a conflict, the provisions herein shall prevail over those in ITP.

*[Where an e-procurement system is used, modify the relevant parts of the* ***PDS*** *accordingly to reflect the e-procurement process]*

*[Instructions for completing the Proposal Data Sheet are provided, as needed, in the notes in italics mentioned for the relevant ITP]*

|  |  |
| --- | --- |
| **ITP Reference** | **A. General** |
| **ITP 1.1** | The reference number of the Request for Proposals is: ***[insert reference number of the Request for Proposals]*** The Employer is: ***[insert name of the Employer]*** The name of the RFP is: ***[insert name of the RFP]*** The number and identification of lots (contracts)comprising this RFP is: **[*insert number and identification of lots (contracts)]***  |
| **ITP 2.1** | The Borrower is: ***[insert name of the Borrower and statement of relationship with the Employer, if different from the Borrower. This insertion should correspond to the information provided in the Invitation for Proposals]***  |
| **ITP 2.1** | Loan or Financing Agreement amount: ***[insert US$ equivalent]***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_The name of the Project is: ***[insert name of the project]***  |
| **ITP 1.3 (a)** | *[delete if not applicable]*“**Electronic – Procurement System**The Employer shall use the following electronic-procurement system to manage this procurement process:*[insert name of the e-system and url address or link]*The electronic-procurement system shall be used to manage the following aspects of the Procurement process:*[insert aspects e.g. issuing RFP, submissions of Proposals, opening of Proposals]”* |
| **ITP 4.1**  | Maximum number of members in the JV shall be: ***[insert a number]*** *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* |
| **ITP 4.1** | The Proposer is permitted to form an SPV ***[yes/ no]***Maximum number of members in the SPV shall be the same as the maximum number of members in the JV If the Contractor is an SPV, it shall be bound to maintain its share capital at a minimum level of *[insert percentage]* of the total paid up share capital of the SPV. The share capital may be increased without the Employer’s prior approval but a written notice of information shall be sent to the Employer. Any reduction of the SPV’s share capital shall be subject to the prior written consent of the Employer. |
| ITP 4.5 | A list of debarred firms and individuals is available on the Bank’s external website: <http://www.worldbank.org/debarr.> |
| **B. RFP Document** |
| **ITP 7.1** | For **Clarification of Proposal purposes** only, the Employer’s address is:***[Insert the corresponding information as required below. This address may be the same as or different from that specified under provision ITP 23.1 for Proposal submission]***Attention: *[****insert full name of person, if applicable****]*Address: *[****insert street address and number****]*Floor/ Room number*: [****insert floor and room number, if applicable****]*City:*] [****insert name of city or town****]*ZIP Code:[***insert postal (ZIP) code, if applicable****]*Country: *[****insert name of country****]*Telephone: *[****insert telephone number, including country and city codes****]*Facsimile number: *[****insert fax number, including country and city code****s]*Electronic mail address: *[****insert email address, if applicable****]*Requests for clarification should be received by the Employer no later than: ***[insert no. of days].*** |
| **ITP 7.1**  | Web page: *[****in case used, identify the widely used website or electronic portal of free access where RFP process information is published****]*   |
| **ITP 7.4** | A Pre-Proposal meeting\_\_\_\_\_\_\_\_\_ take place at the following date, time and place:Date: Time: Place: A site visit conducted by the Employer ***\_\_\_\_\_\_\_\_\_\_\_ [insert “shall be” or “shall not be”]*** organized.*[A pre-proposal meeting/site visit is highly recommended for such single- stage RFP process. In a single stage process, unlike a two stage, Proposers and the Employer do not have the opportunity to carry out a dialogue at the end of the first stage. A comprehensive pre-proposal meeting/site visit could help the Proposers to better understand the requirements and site conditions. This would also be an opportunity for the Borrower to get feedback on its requirements and amendments if required.]* |
| **C. Preparation of Proposals** |
| **ITP 11.1** | The language of the Proposal is: ***[insert “English” or” Spanish” or “French”]****.* ***[Note: In addition to the above language, and if agreed with the Bank, the Employer has the option to issue translated versions of the RFP Document in another language which should either be: (a) the national language of the Employer; or (b) the language used nation-wide in the Employer’s Country for commercial transactions. In such case, the following text shall be added:]******“In addition, the RFP Document is translated into the [insert national or nation-wide used] language [if there are more than one national or nation-wide used language, add “and in the \_\_\_\_\_\_\_\_\_\_\_\_” [insert the second national or nation-wide language].******Proposals shall have the option to submit their Proposal in any one of the languages stated above. Proposers shall not submit Proposals in more than one language.]”***All correspondence exchange shall be in \_\_\_\_\_\_\_\_\_\_\_\_ language.Language for translation of supporting documents and printed literature is \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_. ***[specify one language]****.* |
| **ITP 12.2 (l)** | The Proposer shall submit with its Proposal the following additional documents:***[list any additional document not already listed in ITP 12.2 that must be submitted with the Proposal]*** ***The list of additional documents shall include the following:]*****Code of Conduct for Contractor’s Personnel (ES)** The Proposer shall submit its Code of Conduct that will apply to Contractor’s Personnel (as defined in Sub-Clause 1.1.21 of the General Conditions of Contract), to ensure compliance with the Contractor’s Environmental and Social (ES) obligations under the Contract. The Proposer shall use for this purpose the Code of Conduct form provided in Section IV. No substantial modifications shall be made to this form, except that the Proposer may introduce additional requirements, including as necessary to take into account specific Contract issues/risks. *[If the contract has been assessed to present potential or actual cyber security risks, the method statement, risk assessment and management plans must also be required to include method statement, management strategies, implementation plans and innovations to manage cyber security risks. Further, if there is assessed supply chain risk, the method statement must be required to include  method statement to manage supply chain risks.]* |
| **ITP 12.3 (e)** | The Proposer shall submit with its Proposal the following additional documents:***[list any additional document not already listed in ITP 12.3 that must be submitted with the Financial Proposal]’ otherwise state ‘none’.*** |
| **ITP 14.1** | Alternative Proposals ***[insert “shall be” or “shall not be”]\_\_\_\_\_\_\_*** considered. ***[If alternatives shall be considered, the methodology shall be defined in Section III – Evaluation and Qualification Criteria.*** |
| **ITP 15.1** | * + - * 1. *[if there are specific circumstances, where only certain components of the Works are to be on single responsibility basis and/ or if there are components of the Works to be provided under the responsibility of the Employer, the following text may be used, and parts of the RFP document (such as the Employer’s requirements, Proposal submission forms) modified to accommodate this requirement; otherwise delete:*

“Proposers shall propose for the following component of the Works on a single responsibility basis:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ **and/or**The following components of the Works will be provided under the responsibility of the Employer”*]**[Design and Build- Works are normally contracted on the basis of single responsibility basis and this RFP- SPD is designed for that purpose. It is not recommended to dilute the single responsibility approach unless there are justifiable reasons.]** + - * 1. *[the Contract Price shall be a lump sum amount, subject to any adjustments, in accordance with the Contract. However, if any part of the Works is to be paid according to quantity supplied or work done, the provisions for measurement and evaluation shall be as stated in the Particular Conditions of Contract- Part B- Sub-Clause 14.1.*

*If not applicable, delete this 15.1(b). If applicable state*: “The parts of the Works for which payment will be made on the basis of measurement are specified in \_\_\_\_\_\_. The method for determining the payment for these parts of the Works is also specified in Sub-Clause 14.1 of the Particular Conditions of Contract- Part B”*]* |
| **ITP 15.3** | The prices quoted by the Proposer ***[insert “shall “or “shall not”] \_\_\_\_\_\_\_\_\_\_\_*** be subject to adjustment during the performance of the Contract. |
| **ITP 16.1** | The currency(ies) of the Proposal and the payment currency(ies) shall be in accordance with Alternative \_\_\_\_\_\_\_\_\_ as described below:**Alternative A (Proposers to quote entirely in local currency):**(a) The prices shall be quoted by the Proposer in the Schedules of Priced Activities and Sub-activities entirely in ***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_[Insert the name of the currency of the Employer’s Country,]*** and further referred to as “the local currency”. A Proposer expecting to incur expenditures in other currencies for inputs to the Works supplied from outside the Employer’s country (referred to as “the foreign currency requirements”) shall indicate in the Appendix to Proposal - Table C, the percentage(s) of the Proposal Price (excluding Provisional Sums), needed by the Proposer for the payment of such foreign currency requirements, limited to no more than three foreign currencies.(b) The rates of exchange to be used by the Proposer in arriving at the local currency equivalent and the percentage(s) mentioned in (a) above shall be specified by the Proposer in the Appendix to Proposal - Table C, and shall apply for all payments under the Contract so that no exchange risk will be borne by the successful Proposer.**Alternative B (Proposers allowed to quote in local and foreign currencies):**(a) The prices shall be quoted by the Proposer in the Schedules of Priced Activities and Sub-activities separately in the following currencies:1. for those inputs to the Works that the Proposer expects to supply from within the Employer’s country, in ***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_[Insert the name of the currency of the Employer’s Country],*** and further referred to as “the local currency”; and
2. for those inputs to the Works that the Proposer expects to supply from outside the Employer’s country (referred to as “the foreign currency requirements”), in up to any three foreign currencies.
 |
| **ITP 19** | ***[If a Proposal Security shall be required, a Proposal-Securing Declaration shall not be required, and vice versa.]***A *Proposal Security* ***[insert “shall be” or “shall not be”]*** required. A Proposal-Securing Declaration ***[insert “shall be” or “shall not be”]*** required.If a Proposal Security shall be required, the amount and currency of the Proposal Security shall be ***[If a Proposal Security is required, insert amount and currency of the Proposal Security. Otherwise insert “Not Applicable”.]******[In case of lots, please insert amount and currency of the Proposal Security for each lot]******[Note: Proposal Security is required for each lot as per amounts indicated against each lot. Proposers have the option of submitting one Proposal Security for all lots (for the combined total amount of all lots) for which Proposals have been submitted, however if the amount of Proposal Security is less than the total required amount, the Employer will determine for which lot or lots the Proposal Security amount shall be applied.]******[The following provision should be included and the required corresponding information inserted only if a Proposal security is not required under provision ITP 19.1 and the Employer wishes to declare the Proposer ineligible for a period of time should the Proposer perform the actions mentioned in provision ITP 19.9. Otherwise omit.]***If the Proposer performs any of the actions prescribed in ITP 19.9 (a) or (b), the Borrower will declare the Proposer ineligible to be awarded contracts by the Employer for a period of \_\_\_\_\_\_ years ***[insert period of time]****,*starting from the date the Proposer performs any of the actions.  |
| **ITP 19.3 (d)** | Other types of acceptable securities: ***[Insert names of other acceptable securities. Insert “None” if no Proposal Security is required under provision ITP 19.1 or if Proposal Security is required but no other forms of Proposal securities besides those listed in ITP 19.3 (a) through (c) are acceptable*.*]*** |
| **ITP 20.1** | The Proposal shall be valid until\_\_\_\_\_\_\_\_***[insert day, month and year].******[insert day, month and year, taking into account reasonable time needed to complete the proposal evaluation, obtain necessary approvals and the Bank’s No-objection (if subject to prior review).] [To minimize the risk of errors by Proposers, the proposal validity period is a specific date and not linked to the deadline for submission of proposals. As stated in ITP 20.1, if there is a need to extend the date, for example because the proposal submission deadline is significantly extended by the Employer, the revised proposal validity date shall be specified in accordance with ITP 8]*** |
| **ITP 20.3** | The Proposal price shall be adjusted by the following factor(s): \_\_\_\_\_\_\_\_ ***[The local currency portion of the Contract price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.]*** |
| **ITP 21.1** | The written confirmation of authorization to sign on behalf of the Proposer shall consist of: ***[insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the Proposal].***  |
| **D. Submission of Proposals** |
| **ITP 22.1(b)** | In addition to the original of the Proposal, the number of copies is: ***[insert number of copies]***  |
| **ITP 23.1**  | For **Proposal submission purposes** only, the Employer’s address is: ***[This address may be the same as or different from that specified under provision ITP 7.1 for clarifications]***Attention: *[****insert full name of person, if applicable]*** Street Address: *[****insert street address and number****]* Floor/Room number: *[****insert floor and room number, if applicable****]* City: ***[insert name of city or town]*** ZIP Code: ***[insert postal (ZIP) code, if applicable]*** Country: *[****insert name of country****]* **The deadline for Proposal submission is:**Date: ***[insert day, month, and year, e.g. 15 June, 2020]*** Time: ***[insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.]******[The date and time should be the same as those provided in the Notice of Request for Proposals, unless subsequently amended pursuant to ITP 23.2]*** |
| **ITP 23.1** | Proposers \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[insert “shall” or “shall not”]*** have the option of submitting their Proposals electronically.***[The following provision should be included, and the required corresponding information inserted only if Proposers have the option of submitting their Proposals electronically. Otherwise omit.]***The electronic Proposal submission procedures shall be: ***[insert a description of the electronic Proposal submission procedures.]*** |
| **E. Opening of TECHNICAL PARTS of PROPOSALS** |
| **ITP 26.1**  | The Proposal opening shall take place at:Street Address: ***[insert street address and number]*** Floor/Room number: ***[insert floor and room number, if applicable]*** City: ***[insert name of city or town]*** Country:***[insert name of country]*** Date: ***[insert day, month, and year, e.g. 15 June, 2020]*** Time: ***[Insert time, and identify if a.m. or p.m. e.g. 10:30 a.m.] [Date and time should be the same as those given for the deadline for submission of Proposals in ITP 23.1]*** |
| **ITP 26.1** | ***[The following provision should be included, and the required corresponding information inserted only if Proposers have the option of submitting their Proposals electronically. Otherwise omit.]***The electronic Proposal opening procedures shall be: ***[insert a description of the electronic Proposal opening procedures.]*** |
| **G. Evaluation of Technical Parts of Proposals** |
| **ITP 31.2** |

|  |
| --- |
| The technical factors and sub-factors, and the corresponding weights in % are: [If the contract has been assessed to present potential or actual cyber security risks, the risk assessment and proposed management plans technical factor must be required to include, among other key risks, method statement, management strategies, implementation plans and innovations to manage cyber security risks. Similarly if there are assessed supply chain risks, the risk assessment and proposed management plan must include proposed supply chain risks management plans.] |
| **Technical Factor** | **weight in percentage**[insert weight in %] |
| 1. to what extent the Proposed Works exceed the Employer’s Requirement
 |  |
| 1. Design Proposal
 |  |
| 1. Construction Management strategy;
 |  |
| 1. Method Statements for key construction activities
 |  |
| 1. Code of Conduct
 |  |
| 1. Design Build Work Program
 |  |
| 1. Operation Service Proposal
 |  |
| 1. Design Build Site organization, team composition, qualifications and experience of Contractor’s Personnel
 |  |
| 1. Risk assessment and proposed management plan
 |  |
| 1. Quality of Sustanable Procurement Proposal
 |  |
| 1. key equipment strategy; and
 |  |
| 1. [include any other factors as appropriate].
 |  |
| [The above are proposed headings. Expand as appropriate to enable evaluation. Modify and/or add any other factors as appropriate] |  |

*[The above technical factors may be modified if appropriate ensuring that the documents requested from Proposers as part of their technical proposals (Section IV) enable evaluation of the technical factors.]* *[The weights should be allocated in terms of the relative significance of the technical factors. To enable evaluation of the technical factors, insert technical sub-factors and corresponding weights, as appropriate].* |
| **H. Opening of Financial Parts** |
| **ITP 34.1** | The Letter of Proposal and Price Schedules shallbe initialed by ***[insert number]*** representatives of the Employer conducting Proposal opening*.* ***[Insert procedure: Example: Each Proposal shall be numbered, any modification to the unit or total price shall be initialed by the Representative of the Employer, etc.]*** |
| **I. Evaluation of Financial Part** |
| **ITP 38.1** | The currency that shall be used for Proposal evaluation and comparison purposes to convert at the selling exchange rate all Proposal prices expressed in various currencies into a single currency is: ***[Insert name of currency]***The source of exchange rate shall be: \_\_\_\_\_\_\_\_ ***[Insert name of the source of exchange rates (e.g., the Central Bank in the Employer’s Country).]***The date for the exchange rate shall be the deadline for submission of Proposals as specified in **ITP 23**, unless otherwise specified by the Employer. The currency(ies) of the Proposal shall be converted into a single currency in accordance with the procedure under Alternative \_\_\_\_\_ that follows: ***Alternative A: Proposers quote entirely in local currency***For comparison of Proposals, the Proposal Price, corrected pursuant to **ITP 37.1,** shall first be broken down into the respective amounts payable in various currencies by using the selling exchange rates specified by the Proposer in accordance with **ITP 16.1.**In the second step, the Employer will convert the amounts in various currencies in which the Proposal Price is payable (excluding Provisional Sums) to the single currency identified above at the selling rates established for similar transactions by the authority specified and on the date stipulated above.***OR******Alternative B: Proposers quote in local and foreign currencies***The Employer will convert the amounts in various currencies in which the Proposal Price, corrected pursuant to **ITP 37.1**, is payable (excluding Provisional Sums) to the single currency identified above at the selling rates established for similar transactions by the authority specified and on the date stipulated above.  |
| **ITP 39.1** | ***[The following provision should be included and the required corresponding information inserted only if the Employer intends to apply margin of preference and it is allowed in the Procurement Plan for the subject contract. Otherwise delete]***A margin of domestic preference ***[insert* *either “shall” or “shall not”]*** *\_\_\_\_\_\_\_\_\_*apply. ***[If a margin of preference applies, the application methodology shall be defined in Section III – Evaluation and Qualification Criteria.]*** |
| **ITP 40.1 (f)** | The adjustments shall be determined using the following criteria as detailed in Section III: 1. Deviation in Time Schedule: ***[insert Yes or No. If yes insert the adjustment factor in Section III, Evaluation and Qualification Criteria]****;*
2. The Operation Service Proposal prices will be adjusted for Net Present Value in accordance with **ITP 43.1** and as specified in Section III;

and1. ***[insert any other specific criteria here and provide details in Section III, Evaluation and Qualification Criteria]***
 |
| **J. Evaluation of Combined Technical and Financial Part** |
| **ITP 43.1** | The weight to be given for cost is: \_\_\_\_\_\_\_\_ ***[indicate weight for cost such that weight for cost plus weight for total technical score is 1(one).]***The Employer***[will / will not]***adjust the Operation Service Proposal prices for Net Present Value (NPV). The requirements for the NPV calculation are specified in Section III, Evaluation and Qualification Criteria. |
| **ITP 44.1** | BAFO ***[“applies” / “does not apply”]***If BAFO applies, the procedure will be:  |
| **ITP 46.1** | Negotiation ***[“applies” / “does not apply”]***If negotiation applies, the procedure will be:  |
| **K. Award of Contract** |
| **ITP 54.1 and 54.2** | ***[Delete the following if not applicable]***The successful Proposer shall be required to submit an Environmental and Social (ES) Performance Security.***[The ES Performance Security shall normally be required where ES risks are high.]*** |
| **ITP 55.1** | The procedures for making a Procurement-related Complaint are detailed in the “[Procurement Regulations for IPF Borrowers](http://www.worldbank.org/en/projects-operations/products-and-services/brief/procurement-new-framework) (Annex III).” If a Proposer wishes to make a Procurement-related Complaint, the Proposer shall submit its complaint following these procedures, In Writing (by the quickest means available, such as by email or fax), to:**For the attention**: *[insert full name of person receiving complaints]***Title/position**: *[insert title/position]***Employer:** *[insert name of Employer]***Email address***: [insert email address]***Fax number**: *[insert fax number]* ***delete if not used***In summary, a Procurement-related Complaint may challenge any of the following:1. the terms of this request for proposal document;
2. the Employer’s decision to exclude a Proposer from the procurement process prior to the award of contract; and
3. the Employer’s decision to award the contract.
 |

Section III – Evaluation and Qualification Criteria

**Contents**

[A. Technical Part 50](#_Toc135387391)

[1. Qualification 50](#_Toc135387392)

[2. Evaluation of Technical Part (ITP 31) 51](#_Toc135387393)

[B. Financial Part 53](#_Toc135387394)

[1. Margin of Preference 53](#_Toc135387395)

[2. Evaluation of Financial Part (ITP 40.1(f)) 54](#_Toc135387396)

[C. Evaluation of Combined Technical and Financial Parts 55](#_Toc135387397)

[Combined Evaluation 55](#_Toc135387398)

[D. Multiple Contracts (ITP 40.3) 55](#_Toc135387399)

A. Technical Part

1. Qualification

**1.1 Update of Information**

The Proposer and any subcontractors shall meet or continue to meet the criteria used at the time of initial selection.

**1.2 Financial Resources**

Using the relevant Form No FIN 3.3 in Section IV, Proposal Forms, the Proposer must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet:

(i) the following cash-flow requirement:

and

(ii) the overall cash flow requirements for this contract and its current works commitment.

**1.3 Contractor’s Representative and Key Personnel**

The Proposer must demonstrate that it will have a suitably qualified Contractor’s Representative and sufficient suitably qualified Key Personnel as described in the Employer’s Requirements. The Proposer shall provide details of the Contractor’s Representative and such other Key Personnel that the Proposer considers appropriate, together with their academic qualifications and work experience. The Proposer shall complete the relevant Forms in Section IV, Proposal Forms. ***[If the contract has been assessed to present potential or actual cyber security risks, the Proposer must be required to include Cyber security expert/s among the Key Personnel.]***

**1.4 Equipment**

 The Proposer shall provide its strategy for acquiring and maintaining the key equipment that may be needed to perform the Contract.

The Proposer shall provide further details of proposed items of equipment using the relevant Form in Section IV.

**1.5 Subcontractors**

Any Specialized Sub-contractor identified at the time of Initial Selection shall continue to meet the applicable requirements.

Any other additional subcontractors for the following activities/ sub-activities must meet the following minimum criteria:

|  |  |  |
| --- | --- | --- |
| ***[Activity/Sub-activity No.]*** | **Description of *[List Activity/Sub-activity]*** | **Minimum Criteria to be met** |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

2. Evaluation of Technical Part (ITP 31)

Assessment of adequacy of Technical Proposal with Requirements in accordance with ITP 31.1.

…………………………………………………………………………………………………

*[Insert minimum technical requirements, if any, (or refer to appropriate technical requirements parts) that have to be met by the technical proposals prior to being considered for technical evaluation by applying the scored technical factors/subfactors in accordance with PDS ITP 31.2]*

The technical factors, and sub factors if any, to be evaluated and the scores to be given to each technical factor and sub factors are specified **in the PDS ITP 31.2**.

..............................................................................................................................................

***TECHINICAL PART SCORING METHOLOGY***

*[NOTE TO THE EMPLOYER: The Employer shall develop a scoring methodology to be included here . The following is only an example and can be modified to fit the purpose:]*

|  |  |  |  |
| --- | --- | --- | --- |
| *Score (of the total score for the factor/subfactor as applicable* | *Description* | *Remarks* |  |
| *0* | *Required feature is absent; no relevant information to demonstrate how the requirement is met* |  |  |
| *1* | *Required feature present with deficiencies such as insufficient or information that lacks clarity* |  |  |
| *2* | *Sufficient information to demonstrate how the requirement will be met* |  |  |
| *3* | *Sufficient information to demonstrate that the requirement will be marginally exceeded* |  |  |
| *4* | *Sufficient information that significantly exceed the requirement/proposal contributes to significant value addition* |  |  |

 The score for each sub- factor (i) within a factor (j) will be combined with the scores of sub- factors in the same factor as a weighted sum to form the Factor Technical Score using the following formula:



where:

*tji* = the technical score for sub- factor “i” in factor “j”

*wji* = the weight of sub- factor “i” in factor “j”,

*k* = the number of scored sub-factors in factor “j”

and 

The Factor Technical Scores will be combined in a weighted sum to form the total Technical Proposal Score using the following formula:



where:

*Sj* = the Factor Technical Score of factor “j”

*Wj* = the weight of factor “j” as specified in the **PDS**

*n* = the number of Factors

and 

B. Financial Part

1.  Margin of Preference

**If the PDS so specifies,** the Employer will grant a margin of preference of 7.5% (seven and one-half percent) to domestic contractors, in accordance with, and subject to, the following provisions:

(a) Contractors applying for such preference shall be asked to provide, as part of the data for qualification, such information, including details of ownership, as shall be required to determine whether, according to the classification established by the Borrower and accepted by the Bank, a particular contractor or group of contractors qualifies for a domestic preference. The request for proposals document shall clearly indicate the preference and the method that will be followed in the evaluation and comparison of Proposals to give effect to such preference.

(b) After Proposals have been received and reviewed by the Employer, responsive Proposals shall be classified into the following groups:

(i) Group A: Proposals offered by domestic contractors eligible for the preference.

(ii) Group B: Proposals offered by other contractors.

All evaluated Proposals in each group shall, as a first evaluation step, be compared to determine the Most Advantageous Proposal, and the Most Advantageous Proposal in each group shall be further compared with each other. If a result of this comparison, a Proposal from Group A is the Most Advantageous Proposal, it shall be selected for the award, if the Proposer is qualified. If a Proposal from Group B is the Most Advantageous Proposal, as a second evaluation step, all Proposals from Group B shall then be further compared with the Most Advantageous Proposal from Group A. For the purpose of this further comparison only, an amount equal to 7.5% (seven and one-half percent) of the respective Proposal price corrected for arithmetical errors, including unconditional discounts but excluding provisional sums and the cost of day works, if any, shall be added to the evaluated cost offered in each Proposal from Group B. If the Proposal from Group A is the Most Advantageous Proposal, it shall be selected for award. If not, the Most Advantageous Proposal from Group B based on the first evaluation step shall be selected.

2. Evaluation of Financial Part (ITP 40.1(f))

The following factors and methods will apply:***[use one or more of the following adjustment factors consistent with ITP 40.1 (f) of the PDS]***

#### Time Schedule

The Time for Completion of Design-Build is as specified in GC Sub-clause 1.1.78. No credit will be given for earlier completion. Proposals offering a Time for Completion of Design-Build beyond the designated period shall be rejected.

**Or**

The Time for Completion of Design-Build, as defined in GC Sub-clause 1.1.78, shall be between \_\_\_\_\_\_\_\_\_\_\_\_ minimum and \_\_\_\_\_\_\_\_\_\_\_\_ maximum. The adjustment rate in the event of completion beyond the minimum period shall be \_\_\_\_\_\_\_ (%) for each week of delay from that minimum period. No credit will be given for completion earlier than the minimum designated period. Proposals offering a completion date beyond the maximum designated period shall be rejected.

#### Net Present Valuation of Proposer’s Financial Part

The Design-Build Proposal Price shall not be discounted.

If the **PDS** provides for Net Present Valuation of the Operation Service Proposal Price, the annual amounts in the Operation Service price schedules, as adjusted in accordance with **ITP 40.1** (a) to (e), shall be discounted using a discount factor of [ ……] %. The discount base year shall be the year preceding the first year of the Operation Service Period.

For greater certainty, net present values shall be determined by applying the following discount factors to the annual amounts in the Proposal forms during the Operation Service Period.

|  |  |
| --- | --- |
| Operation Period | Discount factor to be applied |
| Year 1 |  |
| Year 2 |  |
| Year 3 |  |
| *etc.* |  |
|  |  |
|  |  |
|  |  |

####

#### Sustainable Procurement

*[Specify adjustments, if any, to be made for financial proposal evaluation purposes for quantifiable* sustainable *procurement requirements. Ensure that there is no duplication (double counting) with the point system technical factors/subfactors specified in PDS ITP 31.2.]*

#### Specific additional criteria

The relevant evaluation method, if any, shall be as follows:

C. Evaluation of Combined Technical and Financial Parts

Combined Evaluation

The Employer will evaluate and compare the Proposals that have been determined to be substantially responsive.

An Evaluated Proposal Score (B) will be calculated for each responsive Proposal using the following formula, which permits a comprehensive assessment of the Proposal price and the technical merits of each Proposal:

$$B=\frac{C\_{low}}{C}\*X\*100+\frac{T}{T\_{high}}\*\left(1-X\right)\*100$$

where

*C* = Evaluated Proposal Cost

*C low* = the lowest of all Evaluated Proposal Cost among responsive Proposals

*T* = the total Technical Score awarded to the Proposal

*Thigh* = the Technical Score achieved by the Proposal that was scored best among
 all responsive Proposals

*X* = weight for Cost

 The Proposal with the best evaluated Proposal Score (B) among responsive Proposals shall be the Most Advantageous Proposal provided the Proposer is qualified to perform the Contract.

D. Multiple Contracts (ITP 40.3)

*If not applicable state ‘Not Applicable’.*

If in accordance with **ITP 1.1**, Proposals are invited for more than one lot, the contract will be awarded to the Proposer or Proposers with the Most Advanageous Proposal for the individual lots.

However, if a Proposer, with Proposals that are substantially responsive and with highest evaluated score for individual lots, is not qualified for the combination of the lots, then the award will be made based on the highest total score for combination of lots for which Proposers are qualified.

*[Note - Example of the above scenario: A Proposer who was initially selected for either Lot A or Lot B but not both submits Proposals for Lots A and B. These two Proposals are substantially responsive and get the highest total score for Lot A and Lot B respectively. In such a case, a decision has to be made on whether this Proposer should be awarded Lot A or Lot B by considering the combined scores of Proposers for Lot A and Lot B.]*

Cross discounts for award of multiple lots will not be considered.

Section IV – Proposal Forms

**Table of Forms**

[Letter of Proposal - Technical Part 59](#_Toc135387406)

[Letter of Proposal - Financial Part 62](#_Toc135387407)

[Appendix to Proposal 65](#_Toc135387408)

[Schedule of Adjustment Data 65](#_Toc135387409)

[Table A. Design-Build Local Currency 65](#_Toc135387410)

[Table B. Design-Build Foreign Currency (FC) 66](#_Toc135387411)

[Table C. Summary of Payment Currencies (Design Build) 67](#_Toc135387412)

[Table D Schedule of Adjustment Data for the Operation Service 69](#_Toc135387413)

[Table E Schedule of Adjustment Data for the Asset Replacement Fund 71](#_Toc135387414)

[Schedule of Priced Activities and Sub-activities 72](#_Toc135387415)

[Part [1] Proposal Price Forms - Design-Build. 73](#_Toc135387416)

[Sample Schedule of Priced Activities Table 73](#_Toc135387417)

[Sample Schedule of Priced Sub- activities Table 74](#_Toc135387418)

[Specified Provisional Sums 75](#_Toc135387419)

[Summary (Design-Build) 76](#_Toc135387420)

[Part [2] Proposal Price Forms – Operation Service 77](#_Toc135387421)

[Operation Service Fees (excl. Asset Replacement Fund) 77](#_Toc135387422)

[Asset Replacement Schedule 78](#_Toc135387423)

[Summary for Operation Service 79](#_Toc135387424)

[Part 3: Grand Summary 80](#_Toc135387425)

[Technical Proposal Forms 81](#_Toc135387426)

[Design Proposal 82](#_Toc135387427)

[Construction Management Strategy 83](#_Toc135387428)

[Design Build. Method Statements for key construction activities 84](#_Toc135387429)

[Sustainable Procurement Proposal 85](#_Toc135387430)

[Code of Conduct for Contractor’s Personnel (ES) Form 86](#_Toc135387431)

[Design Build Work Program 90](#_Toc135387432)

[Design Build Personnel Organization Chart 91](#_Toc135387433)

[Operation Service Proposals 92](#_Toc135387434)

[Form EQU: Contractor’s Equipment 93](#_Toc135387435)

[Form PER -1. Contractor’s Representative and Key Proposed Personnel 94](#_Toc135387436)

[Form PER-2. Resume and Declaration of Contractor’s Representative and Key Personnel 96](#_Toc135387437)

[Risk assessment and Proposed Management Plan 98](#_Toc135387438)

[Proposed Subcontractors 99](#_Toc135387439)

[Qualification Forms 100](#_Toc135387440)

[Form ELI 1.1. Proposer Information Sheet 101](#_Toc135387441)

[Form ELI 1.2. Party to JV Information Sheet 102](#_Toc135387442)

[Form CON – 2. Historical Contract Non-Performance, Pending Litigation and Litigation History 103](#_Toc135387443)

[Form CON – 3. Environmental and Social Performance Declaration 105](#_Toc135387444)

[Form CON – 4 Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment Performance Declaration 107](#_Toc135387445)

[Form CCC Current Contract Commitments / Works in Progress 109](#_Toc135387446)

[Form FIN 3.3. Financial Resources 110](#_Toc135387447)

[Others 111](#_Toc135387448)

[Form of Proposal Security – Demand Guarantee 112](#_Toc135387449)

[Form of Proposal-Securing Declaration 114](#_Toc135387450)

[Form of Sexual Exploitation and Abuse (SEA), and/or Sexual Harassment (SH) Declaration 115](#_Toc135387451)

Letter of Proposal - Technical Part

*INSTRUCTIONS TO PROPOSERS*

|  |
| --- |
| *INSTRUCTIONS TO PROPOSERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE DOCUMENT**Place this Letter of Proposal in the first envelope “TECHNICAL PART”.**The Proposer must prepare the Letter of Proposal on stationery with its letterhead clearly showing the Proposer’s complete name and business address.**Note: All italicized text in black font is to help Proposers in preparing this form and Proposers shall delete it from the final document.* |

**Date of this Proposal submission**: *[insert date (as day, month and year) of Proposal submission]*

**RFP No.:** *[insert number of RFP process]*

**Request for Proposal No.**: *[insert identification]*

**Alternative No.**: *[insert identification No if this is a Proposal for an alternative]*

To: *[Employer insert:* ***name and address of Employer****]*

Dear Sir or Madam:

We, the undersigned Proposer, hereby submit our Proposal, in two parts, namely:

1. the Technical Part, and
2. The Financial Part.

Having examined the RFP Documents including any Addenda issued in accordance with **ITP 8**, we, the undersigned, offer to provide the Works and Operation Service to \_\_\_\_\_\_\_\_\_, in full conformity with the said RFP Documents and any Addenda.

We undertake, if our Proposal is accepted, to commence the Works and achieve Completion within the respective times stated in the RFP Documents.

We hereby certify that we, including any subcontractors or manufacturers for any part of the contract, meet the eligibility requirements and have no conflict of interest in accordance with **ITP 4.**

**Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH)**: *select the appropriate option from (i) to (v) below and delete the others].*

*We [where JV, insert: “including any of our JV members”], and any of our subcontractors*:

1. [have not been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations.]
2. [are subject to disqualification by the Bank for non-compliance with SEA/ SH obligations.]
3. [had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations. An arbitral award on the disqualification case has been made in our favor.]
4. [had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations for a period of two years. We have subsequently provided and demonstrated that we have adequate capacity and commitment to comply with SEA and SH prevention and response obligations.]
5. [had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations for a period of two years. We have attached documents demonstrating that we have adequate capacity and commitment to comply with SEA and SH prevention and response obligations.]

 We, along with any of our subcontractors, suppliers, consultants, manufacturers, or service providers for any part of the contract, are not subject to, and not controlled by any entity or individual that is subject to, a temporary suspension or a debarment imposed by the World Bank Group or a debarment imposed by the World Bank Group in accordance with the Agreement for Mutual Enforcement of Debarment Decisions between the World Bank and other development banks. Further, we are not ineligible under the Employer’s Country laws or official regulations or pursuant to a decision of the United Nations Security Council;

We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf engages in any type of Fraud and Corruption.

State-owned enterprise or institution: *[select the appropriate option and delete the other] [We are not a state-owned enterprise or institution] / [We are a state-owned enterprise or institution but meet the requirements of* ***ITP 4.6****]*;

**Potential DAB Members:** We hereby propose the following three persons, whose curriculum vitae are attached, as potential DAB members:

|  |  |
| --- | --- |
| Name | Address |
| * + - 1. …………
 |  |
| * + - 1. …………
 |  |
| * + - 1. …………
 |  |

We agree to abide by this Proposal, which, in accordance with **ITP 12** and **ITP 13**, consists of this letter (Letter of Proposal - Technical Part) and enclosures, until [ insert day, month and year in accordance with PDS 20.1], and it shall remain binding upon us and may be accepted by you at any time on or before this date..

Until the formal final Contract is prepared and executed between us, this Proposal, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding contract between us.

**Name of the Proposer**: *\*[insert complete name of the Proposer]*

**Name of the person duly authorized to sign the Proposal on behalf of the Proposer**:
\*\* *[insert complete name of person duly authorized to sign the Proposal]*

**Title of the person signing the Proposal**: *[insert complete title of the person signing the Proposal]*

**Signature of the person named above**: *[insert signature of person whose name and capacity are shown above]*

**Date signed** *[insert date of signing]* **day of** *[insert month]*, *[insert year]*

\*: In the case of the Proposal submitted by a Joint Venture specify the name of the Joint Venture as Proposer.

\*\*: Person signing the Proposal shall have the power of attorney given by the Proposer. The power of attorney shall be attached with the Proposal Schedules.

ENCLOSURE(S):

Letter of Proposal - Financial Part

*INSTRUCTIONS TO PROPOSERS*

|  |
| --- |
| *INSTRUCTIONS TO PROPOSERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE DOCUMENT**Place this Letter of Proposal in the second envelope “FINANCIAL PART”.**The Proposer must prepare the Letter of Proposal on stationery with its letterhead clearly showing the Proposer’s complete name and business address.**Note: All italicized text in black font is to help Proposers in preparing this form and Proposers shall delete it from the final document.* |

**Date of this Proposal submission**: *[insert date (as day, month and year) of Proposal submission]*

**RFP No.:** *[insert number of RFP process]*

**Request for Proposal No.**: *[insert identification]*

**Alternative No.**: *[insert identification No if this is a Proposal for an alternative]*

To: *[Employer insert:* ***name and address of Employer****]*

Dear Sir or Madam:

We, the undersigned Proposer, hereby submit the second part of our Proposal, the Financial Part

Having examined the RFP Documents including any Addenda issued in accordance with **ITP 8**, we, the undersigned, offer to provide the Works and Operation Service to \_\_\_\_\_\_\_\_\_, in full conformity with the said RFP Documents and any Addenda for the total Proposal Price, excluding any discounts offered below is

1. *[Insert one of the options below as appropriate]*

Option 1, in case of one lot: Total price is: *[insert the total price of the Proposal in words and figures, indicating the various amounts and the respective currencies]*;

Or

Option 2, in case of multiple lots: (a) Total price of each lot *[insert the total price of each lot in words and figures, indicating the various amounts and the respective currencies]*; and (b) Total price of all lots (sum of all lots) *[insert the total price of all lots in words and figures, indicating the various amounts and the respective currencies]*;

The discounts offered and the methodology for their application is:

(i) The discounts offered are: *[Specify in detail each discount offered]*

(ii) The exact method of calculations to determine the net price after application of discounts is shown below: *[Specify in detail the method that shall be used to apply the discounts]*;

If our Proposal is accepted, we undertake to provide an advance payment security and a Performance Security *[and an Environmental and Social (ES) Performance Security.* ***Delete if not applicable****]* in the form, in the amounts, and within the times specified in the RFP Documents.

We agree to abide by this Proposal, which, in accordance with **ITP 12** and **ITP 13**, consists of this letter (Letter of Proposal – Financial Part) and the enclosures listed below, until [ insert day, month and year in accordance with PDS 20.1], and it shall remain binding upon us and may be accepted by you at any time on or before this date..

**Commissions, gratuities and fees:** We have paid, or will pay the following commissions, gratuities, or fees with respect to the RFP process or execution of the Contract: *[insert complete name of each Recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity]*.

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Recipient | Address | Reason | Amount |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

(If none has been paid or is to be paid, indicate “none.”)

Until the formal final Contract is prepared and executed between us, this Proposal, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding contract between us.

**Name of the Proposer***:\*[insert complete name of the Proposer]*

**Name of the person duly authorized to sign the Proposal on behalf of the Proposer**: \*\* *[insert complete name of person duly authorized to sign the Proposal]*

**Title of the person signing the Proposal**: *[insert complete title of the person signing the Proposal]*

**Signature of the person named above**: *[insert signature of person whose name and capacity are shown above]*

**Date signed** *[insert date of signing]* **day of** *[insert month]*, *[insert year]*

\*: In the case of the Proposal submitted by a Joint Venture specify the name of the Joint Venture as Proposer.

\*\*: Person signing the Proposal shall have the power of attorney given by the Proposer. The power of attorney shall be attached with the Proposal Schedules.

ENCLOSURE(S):

Appendix to Proposal

Schedule of Adjustment Data

***[Design Build of the Works]***

 *[In Tables A, B, and C, below, the Proposer shall (a) indicate its amount of local currency payment, (b) indicate its proposed source and base values of indices for the different foreign currency elements of cost, (c) derive its proposed weightings for local and foreign currency payment, and (d) list the exchange rates used in the currency conversion. In the case of very large and/or complex works contracts, it may be necessary to specify several families of price adjustment formulae corresponding to the different works involved.]*

Table A. Design-Build Local Currency

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Index code\*** | **Index description\*** | **Source of index\*** | **Base value and date\*** | **Proposer’s related currency amount** | **Proposer’s Proposed weighting** |
|  | Nonadjustable | — | — | — | A: \*B: \*C: \*D: \*E: \* |
|  |  |  | **Total** |  | **1.00** |

*[\* To be entered by the Employer. Whereas “A” should a fixed percentage, B, C, D and E should specify a range of values and the Proposer will be required to specify a value within the range such that the total weighting = 1.00]*

Table B. Design-Build Foreign Currency (FC)

**State type:**  *[If the Proposer is allowed to receive payment in foreign currencies this table shall be used. If Proposer wishes to quote in more than one foreign currency (up to three currencies permitted) then this table should be repeated for each foreign currency.]*

| **Index code** | **Index description** | **Source of index** | **Base value and date** | **Proposer’s related source currency in type/amount** | **Equivalent in FC1** | **Proposer’s proposed weighting** |
| --- | --- | --- | --- | --- | --- | --- |
|  | Nonadjustable | **—** |  **—** | **—** |  | **A: \*****B: \*****C: \*****D: \*****E: \*** |
|  |  |  |  | **Total** |  | **1.00** |

*[\* To be entered by the Employer. Whereas “A” should a fixed percentage, B, C, D and E should specify a range of values and the Proposer will be required to specify a value within the range such that the total weighting = 1.00]*

Table C. Summary of Payment Currencies (Design Build)

Table: Alternative A

**For** *[insert name of Section of the Works]*

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Name of payment currency** | **A****Amount of currency** | **B****Rate of exchange****(local currency per unit of foreign)** | **C****Local currency equivalent****C = A x B** | **D****Percentage of Total Proposal Price (TPP)****100xC** **TPP** |
| **Local currency** |  | **1.00** |  |  |
| **Foreign currency #1** |  |  |  |  |
| **Foreign currency #2** |  |  |  |  |
| **Foreign currency #** |  |  |  |  |
| **Total Design-Build Proposal Price** |  |  |  | **100.00** |
| **Provisional sums expressed in local currency** | *[To be entered by the Employer]* |  | *[To be entered by the Employer]* |  |
| **TOTAL Design Build PROPOSAL PRICE (including provisional sum)** |  |  |  |  |

***[Table: Alternative B***

***To be used only with Alternative B Prices directly quoted in the currencies of payment. (ITP 16.1)***

Summary of currencies of the Proposal for: *[insert name of Section of the Works]*

|  |  |
| --- | --- |
| **Name of currency** | **Amounts payable** |
| Local currency:  |  |
| Foreign currency #1:  |  |
| Foreign currency #2:  |  |
| Foreign currency #3:  |  |
| Provisional sums expressed in local currency  | *[To be entered by the Employer]* |

Table D
Schedule of Adjustment Data for the Operation Service

**(excluding Asset Replacement)**

*[In Tables D1, D2 etc., below, the Proposer shall (a) indicate its proposed source and base values of indices for the different local and foreign currency elements of cost, (b) specify its proposed weightings for local and foreign currency payment.]*

**Table D1. Operation Service- Fee Component 1**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Name of currency component** | **Rate of exchange at base date****(Local currency per unit of foreign)** | **Name and source of index** | **Base value of index at Base Date** | **Proposer’s Proposed index weighting (%)*****[at base date]*** |
| *[insert name of local currency]* |  | *[Insert name of index(es)]* |  | b=  |
|  |  |  |  | c=  |
|  |  |  |  | d= |
| *[Insert name of Foreign Currency #1]* |  |  |  | w= |
| *[Insert name of Foreign Currency #2]* |  |  |  | y= |
| *[Insert name of Foreign Currency #3]* |  |  |  | z= |
|  |  |  | **Total** | 100% |

*[Notes for the Employer:*

*1) For simplicity the table allows only one index per foreign currency. Additional rows can be added if the Employer intends to permit Proposers to use multiple indexes per currency in which case the formula in the Schedule of Indexation will also require adjustment.*

*2) Additional tables (D2, D3 etc.) should be added for each component of the Operation Service Fee. For example, if the contractor is paid a fixed fee and a variable fee, two tables may be required; one table covering the fixed fee and the other covering the variable fee.*

*3) It is normally not necessary to have a non-adjustable component during the Operation Service Period.]*

Table E
Schedule of Adjustment Data for the Asset Replacement Fund

*[In Tables E1 etc., below, the Proposer shall indicate source and base values of indices for the different foreign currency elements of cost included in its Asset Replacement Schedule.]*

**Table E1. Asset Replacement**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name of currency** | **Rate of exchange at Base Date****(Local currency per unit of foreign)** | **Name and source of index** | **Base value of index at Base Date** |
| *[insert name of local currency]* |  | *[Insert name of index(es)]* |  |
| *[Insert name of Foreign Currency #1]* |  |  |  |
| *[Insert name of Foreign Currency #2]* |  |  |  |
| *[Insert name of Foreign Currency #2]* |  |  |  |

*[Notes for the Employer:*

*1) To be adapted by the Employer to suit its proposed Asset Replacement Proposal forms, Proposal currency requirements, and adjustment provisions.*

*2) For simplicity the table shows only one index per currency. Additional rows can be added if the Employer intends to permit Proposers to use multiple indexes per currency. In such cases, the Proposer should be required to provide index weightings for each currency.*

*3) The Employer shall note that the currency and index weighting may be different for each asset to be replaced. Therefore, there is no provision for the Proposer to specify its proposed weighting in this table*

*4) It is normally not necessary to have a non-adjustable component for the Asset Replacement Fund.]*

Schedule of Priced Activities and Sub-activities

The total of the prices of the activities in the Schedule of Priced Activities is the Proposer’s offer to complete the works on a “single responsibility” basis.

The cost of any activity or sub-activity that the Proposer may have omitted is deemed to be included in the price of other activities or sub-activities in the Schedule of Priced Activities and Sub-activities and will not be paid for separately by the Employer.

The priced activity and sub activity schedules provided by the Proposer will be used for Proposal evaluation. These schedules together with the work program serve as a basis for estimating the instalments in the Schedule of Payments.

Part [1] Proposal Price Forms - Design-Build.

Sample Schedule of Priced Activities Table

 *[To be completed by the Proposer (more tables to be used by the Proposer as appropriate)]*

|  |  |  |
| --- | --- | --- |
| **Activity No.** | **Description of Activity** | **Activity Price** |
| 1. | Design Services |  |
|  |  |  |
| 2. | Mobilization |  |
|  |  |  |
| 3. | Construction |  |
|  |  |  |
| 4. |  |  |
|  |  |  |
| 5. | etc |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  | Total price of Activities carried forward to Grand Summary, Page \_\_\_\_ |  |

Part [1] Proposal Price Forms - Design-Build

Sample Schedule of Priced Sub- activities Table

 *[to be completed by the Proposer (more tables to be used by the Proposer as appropriate)]*

Activity:

|  |  |  |
| --- | --- | --- |
| **Sub-activity No.** | **Description of Sub-activity** | **Sub-activity Price** |
| 1. |  |  |
|  |  |  |
| 2. |  |  |
|  |  |  |
| 3. |  |  |
|  |  |  |
| 4. |  |  |
|  |  |  |
| 5. | Etc. |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  | Total price of Sub-activities carried forward to the Priced Activity Schedule, Page \_\_\_\_ |  |

Part [1] Proposal Price Forms - Design-Build

Specified Provisional Sums

|  |  |  |
| --- | --- | --- |
| **Item no.** | **Description** | **Amount** |
| 1 |  |  |
|  |  |  |
|  |  |  |
| 2 |  |  |
|  |  |  |
|  |  |  |
| 3 |  |  |
|  |  |  |
|  |  |  |
| 4 |  |  |
|  | [*To be entered by the Employer. The provisional sums shall include an estimated amount to cover the Employer’s portion (50%) of DAB’s fees and expenses:]* Provisional sums for the Employer’s portion of DAB costs |  |
|  | [*To be entered by the Employer; Delete if not applicable:]* Provisional sums for any specific ES outcomes. |  |
| etc. |  |  |
|  |  |  |
|  | Total for Specified Provisional Sums(carried forward to Grand Summary (B), p. ) |  |

Part [1] Proposal Price Forms - Design-Build

Summary (Design-Build)

|  |  |  |
| --- | --- | --- |
| **General Summary** | **Page** | **Amount** |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| *Subtotal of Activities* | *(A)* |  |
|  |  |  |
| *Specified Provisional Sums ii* | *(B)* | *[sum]* |
| *Total of Activities and Provisional Sums (A + B +) i* | *(C)* |  |
| *Add Provisional Sum for Contingency Allowance (if any) ii* | *(D)* | *[sum]* |
| *Proposal Design Build Price (C + D) (Carried forward to Letter of Proposal)* | *(E)* |  |
|  |  |  |
| i)All Provisional Sums are to be expended in whole or in part at the direction and discretion of the Employer’s Representative in accordance with Sub-Clause 13.5 of the General Conditions. except with respect to DAB Fees and Expenses for which Sub-Clause 13.5 of the Particular Conditions – Part B shall apply.ii)To be entered by the Employer.\* For evaluation purposes, Provisional Sum will be excluded |

Part [2] Proposal Price Forms – Operation Service

Operation Service Fees (excl. Asset Replacement Fund)

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Ref.** | **Breakdown by Operation Service fees by revenue component** | **Totals** | **Yr. 1** | **Yr. 2** | **Yr. 3** | **etc.** |  |  |
| A | *e.g. Operation Service fixed fee* |  |  |  |  |  |  |  |
| B | *e.g. Operation Service variable fee* |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
| C | Provisional Sum for Auditing Body |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
| **D** | **Totals** |  |  |  |  |  |  |  |

i) All Provisional Sums are to be expended in whole or in part at the direction and discretion of the Employer’s Representative in accordance with Clause 13.5 of the Conditions of Contract.

ii) For evaluation purposes, Provisional Sums will be excluded

***[****The Employer shall adapt the form, and add additional forms, to suit the proposed Operation Service payment basis and permitted payment currencies. Add one additional Proposal form for each component of the Operation Service Fee]*

Part [2] Proposal Price Forms – Operation Service

Asset Replacement Schedule

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Ref.** | **Asset description** | **Scheduled Replacement Date** | **Amount in currency of Proposal** | **% Local (q)\******[state currency]*** | **% FC1 (r)\******[state currency]*** | **% FC2 (s)\******[state currency]*** | **% FC#*****[state currency]*** |
| 1 | Year 6 Asset Replacements |  |  |  |  |  |  |
|  | (a) Asset …. |  |  |  |  |  |  |
|  | (b) Asset …… |  |  |  |  |  |  |
|  | **Total Year 6 Asset Replacements** |  | ………….*(Carried to Form 2a)* |  |  |  |  |
| 2 | Year 7 Asset Replacements |  |  |  |  |  |  |
|  | (a) Asset …. |  |  |  |  |  |  |
|  | (b) Asset …… |  |  |  |  |  |  |
|  | **Total Year 7 Asset Replacements** |  | ………….*(Carried to Form 2a)* |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  | Continue table for each year of the operation service |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |

\* “q”, “r” and “s” etc. are the proportions in each currency to be used for cost indexation purposes as further detailed in Section IX, Contract Agreement, Appendix 2 – Schedule of Cost Indexation.

*[The Employer shall adapt the form if Proposers are allowed to be paid in multiple currencies.]*

Part [2] Proposal Price Forms – Operation Service

Summary for Operation Service

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Ref.** | **Activity** | **Total Operation Service Period *[sum all years]*** | **Yr. 1** | **Yr. 2** | **Yr. 3** | **etc.** |  |  |
| A | Operation Service (excluding asset replacement fund) |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
| B | Asset Replacement Fund (year 5 onwards) |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
| **C** | **Totals** |  | **Total carried forward** |

Part 3: Grand Summary

|  |  |  |
| --- | --- | --- |
| **General Summary** | **Page** | **Amount** |
|  |  |  |
| 1. Proposal Design-Build Price |  | Sum |
| 2. Proposal Operation Service Price |  | Sum |
| *3. Proposal total price (Design-Build + Operation Service Price (Carried forward to Letter of Proposal)* |  | *Sum* |
|  |  |  |
|  |

Technical Proposal Forms

Design Proposal

##

## The Proposer shall submit a design proposal which addresses as a minimum the following:

1. organizational arrangements for the design including: team structure, roles and responsibilities, interface arrangements, design review and approval procedures and quality assurance arrangements;
2. Proposed design deliverables [*Employer to specify any mandatory requirements appropriate to good international industry practice];*
3. design statement setting out how the Employers Requirements will be achieved;
4. Any added value the Proposer will bring including examples of innovative aspects of the design;
5. comments on the Employer's Requirements, including:
6. status of the information available and relevant design issues for the Works;
7. comments on any errors, defects or ambiguities noted in the Employer’s Requirements; and
8. *[details of any exceptions in the conceptual design taken to the Employer's Requirements]*;
9. Sustainable Procurement: sustainability aspects (e.g. energy efficiency, reduction of wastages, material reduction, sources of materials etc.) demonstrating the Proposer’s approach and commitment to sustainable design and construction practices;
10. strategy for gathering baseline ES information in time to inform design development;
11. details of how the ES requirements and any proposal to enhance ES outcomes will be incorporated into all design stages and how the implications for the construction phase has been considered;
12. details of the approach to managing risks, stakeholder engagement, consultation and environmental permits/consents;
13. value engineering (value management) arrangements, including consideration of ES issues; and
14. software systems intended to be employed for planning, design, records and reporting
15. *[modify/include any other relevant information, as appropriate.]*

Construction Management Strategy

The Proposer shall submit a construction management strategy which addresses as a minimum:

* + - * 1. organizational arrangements for the construction management including: team structure, roles and responsibilities, interface arrangements, approval procedures and quality assurance arrangements;
				2. subcontractor selection and management;
				3. proposals for training all personnel attending site;
				4. stakeholder engagement;
				5. obtaining and managing consents, permits and approvals;
				6. execution of Permanent Works and Temporary Works including Site establishment;
				7. site setup proposals including access, accommodation, welfare facilities, arrangement for plant and storage of material in particular those involving waste and hazardous materials;
				8. construction phasing proposals including sequence of work and management of conflicting activities;
				9. ensuring that geotechnical investigations or other advance works meet the ES requirements;
				10. risk management approach for geotechnical and subsurface aspects of the Works;
				11. quality management system including a draft of the quality management plan;
				12. sustainability aspects demonstrating the Proposer’s approach and commitment to sustainable construction practices (e.g. energy efficiency, reduction of wastages, material reduction and sources of materials etc.);
				13. preparation, approval and implementation of the Contractor’s environmental and social management plan;
				14. preparation, approval and implementation of the Contractor’s health and safety manual;
				15. grievance redress mechanisms;
				16. reporting arrangements, including topics (that include ES) and timescales in accordance with the Particular Conditions Special Provisions Sub-Clause 4.21;
				17. arrangements for testing upon completion of the works;
				18. arrangements for completion of Design-Build, including completion of as-built documents, preparation of operation and maintenance manuals, and any other relevant aspects; and
				19. additional aspects as stated in the Employer’s Requirements.
				20. *[**modify/include any other relevant information, as appropriate.]*

Design Build.
Method Statements for key construction activities

*The Proposer shall provide its method statements for addressing the following risks and carrying out the following construction activities. Each method statement shall describe the proposed approach, the level of staffing and experience, the safe system of work, and the equipment or materials to be used to manage risk or activity in accordance with the Employer’s Requirements.*

*[The Employer shall identify the key risks/ construction activities:*

*Examples:*

* *foundation excavation;*
* *erection of steel structures;*
* *prevention of Sexual Exploitation, and Abuse (SEA);*
* *management of traffic including construction traffic*

 Sustainable Procurement Proposal

*[****Note to Proposer****: In addition to submitting the* ***required***ES Management Strategies and Implementation Plans, *the Proposer shall provide its proposal to demonstrate how additional sustainable procurement requirements, if any, specified in Section VII- Works’ Requirements would be addressed. The Proposer shall also provide its proposal, if any, for exceeding the sustainable procurement requirements.]*

Code of Conduct for Contractor’s Personnel (ES) Form

**Note to the Proposer**:

**The minimum content of the Code of Conduct form as set out by the Employer shall not be substantially modified**. However, the Proposer may add requirements as appropriate, including to take into account Contract-specific issues/risks.

The Proposer shall initial and submit the Code of Conduct form as part of its proposal.

***Note to the Employer****:*

***The following minimum requirements shall not be modified****. The Employer may add additional requirements to address identified issues, informed by relevant environmental and social assessment.*

*The types of issues identified could include risks associated with: labor influx, spread of communicable diseases, and Sexual Exploitation and Abuse (SEA) etc.*

***Delete this Box prior to issuance of the RFP documents.***

**CODE OF CONDUCT FOR CONTRACTOR’S PERSONNEL**

We are the Contractor, [*enter name of Contractor*]. We have signed a contract with [*enter name of Employer*] for [*enter description of the Works*]. These Works will be carried out at [*enter the Site and other locations where the Works will be carried out*]. Our contract requires us to implement measures to address environmental and social risks related to the Works, including the risks of sexual exploitation, sexual abuse and sexual harassment.

This Code of Conduct is part of our measures to deal with environmental and social risks related to the Works. It applies to all our staff, labourers and other employees at the Works Site or other places where the Works are being carried out. It also applies to the personnel of each subcontractor and any other personnel assisting us in the execution of the Works. All such persons are referred to as “**Contractor’s Personnel”** and are subject to this Code of Conduct.

This Code of Conduct identifies the behavior that we require from all Contractor’s Personnel.

Our workplace is an environment where unsafe, offensive, abusive or violent behavior will not be tolerated and where all persons should feel comfortable raising issues or concerns without fear of retaliation.

**REQUIRED CONDUCT**

Contractor’s Personnel shall:

1. carry out his/her duties competently and diligently;
2. comply with this Code of Conduct and all applicable laws, regulations and other requirements, including requirements to protect the health, safety and well-being of other Contractor’s Personnel and any other person;
3. maintain a safe working environment including by:
	1. ensuring that workplaces, machinery, equipment and processes under each person’s control are safe and without risk to health;
	2. wearing required personal protective equipment;
	3. using appropriate measures relating to chemical, physical and biological substances and agents; and
	4. following applicable emergency operating procedures.
4. report work situations that he/she believes are not safe or healthy and remove himself/herself from a work situation which he/she reasonably believes presents an imminent and serious danger to his/her life or health;
5. treat other people with respect, and not discriminate against specific groups such as women, people with disabilities, migrant workers or children;
6. not engage in any form of Sexual Harassment, which means unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature with other Contractor’s or Employer’s Personnel;
7. not engage in Sexual Exploitation, which means any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another;
8. not engage in Sexual Abuse, which means the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions;
9. not engage in any form of sexual activity with individuals under the age of 18, except in case of pre-existing marriage;
10. complete relevant training courses that will be provided related to the environmental and social aspects of the Contract, including on health and safety matters, Sexual Exploitation and Abuse (SEA), and Sexual Harassment (SH);
11. report violations of this Code of Conduct; and
12. not retaliate against any person who reports violations of this Code of Conduct, whether to us or the Employer, or who makes use of the grievance mechanism for Contractor’s Personnel or the project’s Grievance Redress Mechanism.

**RAISING CONCERNS**

If any person observes behavior that he/she believes may represent a violation of this Code of Conduct, or that otherwise concerns him/her, he/she should raise the issue promptly. This can be done in either of the following ways:

1. Contact [*enter name of the Contractor’s Social Expert with relevant experience in handling* *sexual exploitation, sexual abuse and sexual harassment cases, or if such person is not required under the Contract, another individual designated by the Contractor to handle these matters*] in writing at this address [ ] or by telephone at [ ] or in person at [ ]; or
2. Call [ ] to reach the Contractor’s hotline *(if any)* and leave a message.

The person’s identity will be kept confidential, unless reporting of allegations is mandated by the country law. Anonymous complaints or allegations may also be submitted and will be given all due and appropriate consideration. We take seriously all reports of possible misconduct and will investigate and take appropriate action. We will provide warm referrals to service providers that may help support the person who experienced the alleged incident, as appropriate.

There will be no retaliation against any person who raises a concern in good faith about any behavior prohibited by this Code of Conduct. Such retaliation would be a violation of this Code of Conduct.

**CONSEQUENCES OF VIOLATING THE CODE OF CONDUCT**

Any violation of this Code of Conduct by Contractor’s Personnel may result in serious consequences, up to and including termination and possible referral to legal authorities.

FOR CONTRACTOR’S PERSONNEL:

I have received a copy of this Code of Conduct written in a language that I comprehend. I understand that if I have any questions about this Code of Conduct, I can contact [*enter name of Contractor’s contact person with relevant experience*]requesting an explanation.

Name of Contractor’s Personnel: [*insert name*]

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: (day month year): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Countersignature of authorized representative of the Contractor:

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: (day month year): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**ATTACHMENT 1:** Behaviors constituting Sexual Exploitation and Abuse (SEA) and behaviors and behaviors constituting Sexual Harassment (SH)

**ATTACHMENT 1 TO THE CODE OF CONDUCT FORM**

**BEHAVIORS CONSTITUTING SEXUAL EXPLOITATION AND ABUSE (SEA) AND BEHAVIORS CONSTITUTING SEXUAL HARASSMENT (SH)**

The following non-exhaustive list is intended to illustrate types of prohibited behaviors.

1. **Examples of sexual exploitation and abuse** include, but are not limited to:
* A Contractor’s Personnel tells a member of the community that he/she can get them jobs related to the work site (e.g. cooking and cleaning) in exchange for sex.
* A Contractor’s Personnel that is connecting electricity input to households says that he can connect women headed households to the grid in exchange for sex.
* A Contractor’s Personnel rapes, or otherwise sexually assaults a member of the community.
* A Contractor’s Personnel denies a person access to the Site unless he/she performs a sexual favor.
* A Contractor’s Personnel tells a person applying for employment under the Contract that he/she will only hire him/her if he/she has sex with him/her.
1. **Examples of sexual harassment** **in a work context**
* Contractor’s Personnel comment on the appearance of another Contractor’s Personnel (either positive or negative) and sexual desirability.
* When a Contractor’s Personnel complains about comments made by another Contractor’s Personnel on his/her appearance, the other Contractor’s Personnel comment that he/she is “asking for it” because of how he/she dresses.
* Unwelcome touching of a Contractor’s or Employer’s Personnel by another Contractor’s Personnel.
* A Contractor’s Personnel tells another Contractor’s Personnel that he/she will get him/her a salary raise, or promotion if he/she sends him/her naked photographs of himself/herself.

Design Build Work Program

The Proposershall set out a work program for design and construction of the Works to be undertaken, including identification of major milestones and critical path. The proposed work program shall be developed based on the Employer’s Requirements and shall consider the following key milestones:

1. design of the Works, including the submission of the design deliverables, review and approval of the design by the Employer’s Representative
2. processes and deliverables needed to commence the Works;
3. execution of the Works within the Time for Completion, highlighting activities imposing constraints on the construction sequence;
4. testing, commissioning and handing over of the completed Works;
5. No-objection to the Contractor’s MSIPs, which collectively form the C-ESMP, in accordance with the Particular Conditions of Contract Sub-Clause 4.1;
6. Constitution of the DAB;
7. SEA and SH orientation conference; and
8. *[insert any other relevant information, as may be appropriate.]*

Design Build Personnel Organization Chart

The Proposer shall provide an organization chart illustrating the proposed management structure and reporting lines for delivery of the Design Build. The organization chart shall include the names of all Key Personnel.

Operation Service Proposals

The Proposershall set out a detailed plan for the Operation Service which shall address the following:

1. Organisation and key personnel
2. Operations proposals
3. Preventative and reactive maintenance
4. Monitoring water/wastewater quality and flows
5. The operational systems to be developed, including details of any standards to be adopted or followed for example with respect to managing environmental and social risks during operation
6. Training of Contractor’s Personnel
7. Asset replacement
8. Preparation of required documents and manuals
9. Quality assurance
10. Hand-back arrangements
11. Emergency Preparedness and Response Plan
12. Reporting arrangements, including the appropriate topics (that include ES) and timescales in accordance with the Particular Conditions of Contract Sub-Clause 4.21 *[insert any other relevant information, as may be appropriate.]*

Form EQU:
Contractor’s Equipment

The Proposer shall set out its strategy for obtaining or accessing the key equipment necessary to execute the Works in accordance with the Design Build Works Program. In the strategy, the Proposer shall specify the manufacturer, capacity, model, power rating, age and maintenance condition, and how it will ensure that the equipment is maintained in accordance with manufacturer’s specifications for the duration of the Contract. The Proposer shall specify whether it will own, lease, rent or specially manufacture the key equipment.

A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Proposer.

|  |
| --- |
| Item of equipment |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |
|  | Details of current commitments |
|  |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |

Omit the following information for equipment owned by the Proposer.

|  |  |
| --- | --- |
| Owner | Name of owner |
|  | Address of owner |
|  |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |
|  |  |
|  |  |

Form PER -1.
Contractor’s Representative and Key Proposed Personnel

Proposers should provide the names and details of suitably qualified Contractor’s Representative and Key Personnel to perform the Contract. The data on their experience should be supplied using the Form PER-2 below for each candidate. Proposers should submit a fully detailed Key Personnel resource schedule for the whole contract implementation period. The resource schedule must include:

* the name and role for each Key Personnel position
* The duration of each Key Personnel appointment
* The level of effort (time) allocated to each Key Personnel position and its distribution throughout the contract implementation period.

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Title of position** | **Name of candidate** |  |
| *1.* | *[Contractor’s Representative]* |  |  |
| *2.* | ***[Cyber security Expert/s]*** *[Include as required]* |  |  |
| ***Key Personnel for Design***  |
| *3.* | *[Design Manager]* |  |  |
| *4.* | [Environmental Impact Assessment Specialist] |  |  |
| *5.* | *[Social Impact Assessment Specialist]* |  |  |
| *6.* | [Health and Safety Specialist] |  |  |
| *7.* | *[Biodiversity, Air quality, Noise etc. Specialists]* |  |  |
| *8.* | *[Modify/add others as appropriate]* |  |  |
| ***Key Personnel for Construction*** |
| *9.* | *[Construction Manager]* |  |  |
| *10.* | *[Environmental Specialist]* |  |  |
| *11.* | *[Health and Safety Specialist]* |  |  |
| *12.* | *[Social Specialist]* |  |  |
| *13.* | *Survey Manager* |  |  |
| *14.* | *[****Sexual Exploitation, Abuse and Harassment Expert(s)****]**[Where a Project SEA risks are assessed to be substantial or high, Key Personnel shall include an expert (s) with relevant experience in addressing sexual exploitation, sexual abuse and sexual harassment cases]* |  |  |
| *15.* | *[Modify/add others as appropriate]* |  |  |
| ***Key Personnel for operation service*** |
| *16.* | *Plant Manager*  |  |  |
| *17.* | *EHS Manager* |  |  |
| *18.* | *Community Relations Manager* |  |  |
| *19.* | *[Modify/add others as appropriate]* |  |  |

Form PER-2.
Resume and Declaration of Contractor’s Representative and Key Personnel

|  |
| --- |
| Name of Proposer |

|  |
| --- |
| Position *(title of position from Forms PER-1)* |
| Personnel information | Name  | Date of birth |
|  | Address | Email |
|  | Professional qualifications |
|  | Academic qualifications |
|  | Language proficiency *[language and levels of speaking, reading and writing skills]* |
| Present employment | Name of employer |
|  | Address of employer |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize professional experience over the last [20 years], in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

|  |  |  |
| --- | --- | --- |
| From | To | Company / Project / Position / Relevant technical and management experience |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**Declaration**

I, the undersigned Key Personnel, certify that to the best of my knowledge and belief, the information contained in this Form PER-2 correctly describes myself, my qualifications and my experience.

I confirm that I am available as certified in the following table and throughout the expected time schedule for this position as provided in the Proposal:

|  |  |
| --- | --- |
| **Commitment** | **Details** |
| **Commitment to duration of contract:** | *[insert period (start and end dates) for which this Key Personnel is available to work on this contract]* |
| **Time commitment:** | *[insert the number of days/week/months/ that this Key Personnel will be engaged]* |

I understand that any misrepresentation or omission in this Form may:

1. be taken into consideration during Proposal evaluation;
2. result in my disqualification from participating in the Proposal;
3. result in my dismissal from the contract.

**Name of Key Personnel: *[insert name]***

Signature:

Date: (day month year):

**Countersignature of authorized representative of the Proposer:**

Signature:

**Date: (day month year):**

Risk assessment and Proposed Management Plan

The Proposer should submit a risk register identifying the hazards anticipated during the implementation of the contract.

For the key hazards ranked by impact, the risk register shall include a description of the hazard, an assessment of the potential impact on health and safety, environment, cost, program or other, and the proposed mitigation strategy for each hazard.

*[****Note to the Proposer****: (i) As required in PDS 12.2 (l), also include method statement, management strategies and implementation plans and innovations, to manage cyber security risks; (ii) if there are assessed supply chain risks, the risk assessment and proposed management plans, must include proposed supply chain risks management plans.]*

Proposed Subcontractors

The following Subcontractors and/or manufacturers are proposed for carrying out the activity/sub-activity indicated. For any additional subcontractor (that is not the Specialized Subcontractor, if any, accepted in the initial selection process or subsequently approved by the Employer in accordance with **ITP 17.3**), Proposers are free to propose more than one for each activity/sub-activity.

|  |  |  |
| --- | --- | --- |
| **Activity/Sub-Activity**  | **Proposed Subcontractor ’s name and address** | **Nationality** |
|  |  |  |
|  |  |  |
|  |  |  |

Proposers shall submit an undertaking from each proposed subcontractor to confirm that they have read, understand and will comply with the ES obligations and code of conduct.

Qualification Forms

Form ELI 1.1.
Proposer Information Sheet

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

RFP No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Page \_\_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

|  |
| --- |
| 1. Proposer’s Legal Name  |
| 2. In case of JV, legal name of each party: |
| 3. If permitted under ITP 4.3, names of JV members that wish to form an SPV: |
| 4. Proposer’s actual or intended Country of Registration: |
| 5. Proposer’s Year of Registration:  |
| 6. Proposer’s Legal Address in Country of Registration: |
| 7. Proposer’s Authorized Representative *[Lead Member]* InformationName:Address:Telephone/Fax numbers:Email Address: |
| 8. Attached are copies of original documents of Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above, in accordance with ITP 4.4 In case of JV, letter of intent to form JV or JV agreement, in accordance with ITP 4.1 In case of state-owned enterprise or institution, in accordance with ITP 4.6, documents establishing:* Legal and financial autonomy
* Operation under commercial law
* Establishing that the Proposer is not under the supervision of the Employer

9. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership. The successful Proposer shall provide additional information on beneficial ownership, using the Beneficial Ownership Disclosure Form. |

Form ELI 1.2.
Party to JV Information Sheet

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

RFP No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Page \_\_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

|  |
| --- |
| 1. Proposer’s Legal Name:  |
| 2. JV’s Party legal name: |
| 3. JV’s Party Country of Registration: |
| 4. JV’s Party Year of Registration: |
| 5. JV’s Party Legal Address in Country of Registration: |
| 6. JV’s Party Authorized Representative InformationName:Address:Telephone/Fax numbers:Email Address: |
| 7. Attached are copies of original documents of Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above, in accordance with ITP 4.4. In case of a state-owned enterprise or institution, documents establishing legal and financial autonomy, operation in accordance with commercial law, and that they are not under the supervision of the Employer, in accordance with ITP 4.6.8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership. The successful Proposer shall provide additional information on beneficial ownership for each JV member using the Beneficial Ownership Disclosure Form. |
| 9. Does the JV wish to form an SPV ***[yes/ no] only relevant where PDS permits formation of SPV]*** |

Form CON – 2.
Historical Contract Non-Performance, Pending Litigation and Litigation History

***[This form should be used only if the information submitted at the time of initial selection requires updating. The following table shall be filled in for the Proposer and for JVs, each member of the Joint Venture]***

Proposer’s Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

JV Member’s Name\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

RFP No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages

|  |
| --- |
| Non-Performed Contracts in accordance with Section III, Evaluation and Qualification Criteria of the Initial Selection document  |
|  Contract non-performance did not occur since 1st January *[insert year]* Contract(s) not performed since 1st January *[insert year]*  |
| **Year** | **Non- performed portion of contract** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and US$ equivalent)** |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*Name of Employer: *[insert full name]*Address of Employer: *[insert street/city/country]*Reason(s) for nonperformance: *[indicate main reason(s)]* | *[insert amount]* |
| Pending Litigation, in accordance with Section III, Evaluation and Qualification Criteria of the Initial Selection document |
|  No pending litigation  |
|  Pending litigation  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Year of dispute** | **Amount in dispute (currency)** | **Contract Identification** | **Total Contract Amount (currency), USD Equivalent (exchange rate)** |
|  |  | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: Party who initiated the dispute: Status of dispute:  |  |
| Litigation History in accordance with Section III, Evaluation and Qualification Criteria of the Initial Selection document |
|  No Litigation History  Litigation History |
| **Year of award** | **Outcome as percentage of Net Worth** | **Contract Identification** | **Total Contract Amount (currency), USD Equivalent (exchange rate)** |
| *[insert year]* | *[insert percentage]* | Contract Identification: *[indicate complete contract name, number, and any other identification]*Name of Employer: *[insert full name]*Address of Employer: *[insert street/city/country]*Matter in dispute: *[indicate main issues in dispute]*Party who initiated the dispute: *[indicate “Employer” or “Contractor”]*Reason(s) for Litigation and award decision *[indicate main reason(s)]* | *[insert amount]* |

Form CON – 3.
Environmental and Social Performance Declaration

*[This form should be used only if the information submitted at the time of initial selection requires updating. The following table shall be filled in for the Proposer and for JVs, each member of the Joint Venture and each Specialized Subcontractor]*

Proposer’s Name: *[insert full name]*

Date: *[insert day, month, year]*

Joint Venture Member’s or Specialized Subcontractor’s Name: *[insert* *full name]*

RFP No. and title: *[insert RFP number and title]*

Page *[insert page number]* of *[insert total number]* pages

|  |
| --- |
| Environmental and Social Performance Declaration in accordance with Section III, Qualification Criteria, and Requirements of the Initial Selection document |
|  **No suspension or termination of contract**: An employer has not suspended or terminated a contract and/or called the performance security for a contract for reasons related to Environmental or Social (ES) performance since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 2.5. **Declaration of suspension or termination of contract**: The following contract(s) has/have been suspended or terminated and/or Performance Security called by an employer(s) for reasons related to Environmental or Social (ES) performance since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 2.5. Details are described below: |
| **Year** | **Suspended or terminated portion of contract** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and US$ equivalent)** |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*Name of Employer: *[insert full name]*Address of Employer: *[insert street/city/country]*Reason(s) for suspension or termination: *[indicate main reason(s)]* | *[insert amount]* |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*Name of Employer: *[insert full name]*Address of Employer: *[insert street/city/country]*Reason(s) for suspension or termination: *[indicate main reason(s) e.g. gender-based violence; sexual exploitation or sexual abuse breaches]* | *[insert amount]* |
| *…* | *…* | *[list all applicable contracts]* | *…* |
| **Performance Security called by an employer(s) for reasons related to ES performance** |
| **Year** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and US$ equivalent)** |
| *[insert year]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*Name of Employer: *[insert full name]*Address of Employer: *[insert street/city/country]*Reason(s) for calling of performance security: *[indicate main reason(s) e.g. gender-based violence; sexual exploitation or sexual abuse breaches]* | *[insert amount]* |
|  |  |  |

Form CON – 4
Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment Performance Declaration

***[This form should be used only if the information submitted at the time of initial selection requires updating. The following table shall be filled in for the Proposer, each member of a Joint Venture and each Subcontractor]***

Proposer’s Name: *[insert full name]*Date: *[insert day, month, year]*Joint Venture Member’s or Subcontractor’s Name: *[insert* *full name]*RFP No. and title: *[insert RFP number and title]*Page *[insert page number]* of *[insert total number]* pages

|  |
| --- |
| **SEA and/or SH Declaration** **in accordance with Section III, Qualification Criteria, and Requirements** |
| We:🞎 (a) have not been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations🞎 (b) are subject to disqualification by the Bank for non-compliance with SEA/ SH obligations🞎 (c) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations. An arbitral award on the disqualification case has been made in our favor.🞎 (d) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations for a period of two years. We have subsequently demonstrated that we have adequate capacity and commitment to comply with SEA/ SH obligations.🞎 (e) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations for a period of two years. We have attached evidence demonstrating that we have adequate capacity and commitment to comply with SEA/ SH obligations.   |
| **[*If (c) above is applicable*, *attach evidence of an arbitral award reversing the findings on the issues underlying the disqualification.]*** |
| ***[If (d) or ( e) above are applicable, provide the following information:]*** |
| Period of disqualification: From: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ To: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| If previously provided on another Bank financed works contract, details of evidence that demonstrated adequate capacity and commitment to comply with SEA/ SH obligations (**as per (d) above)**Name of Employer: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Name of Project: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Contract description: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Brief summary of evidence provided: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Contact Information: (Tel, email, name of contact person): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| As an alternative to the evidence under (d), other evidence demonstrating adequate capacity and commitment to comply with SEA/ SH obligations (**as per (e) above)** *[attach details as appropriate].* |

Form CCC
Current Contract Commitments / Works in Progress

Proposers and each partner to a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Name of contract** | **Employer, contact address/tel/fax** | **Value of outstanding work (current US$ equivalent)** | **Estimated completion date** | **Average monthly invoicing over last six months(US$/month)** |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| etc. |  |  |  |  |

Form FIN 3.3.
Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as indicated in Section III, Evaluation and Qualification Criteria

|  |  |
| --- | --- |
| **Source of financing** | **Amount (US$ equivalent)** |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |

Others

Commercial or contractual aspects of the RFP documents that the Proposer would like to discuss with the Employer during clarifications.

Form of Proposal Security – Demand Guarantee

**Beneficiary:**

**Request for Proposals No:**

**Date:**

**PROPOSAL GUARANTEE No.:**

**Guarantor:**

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Applicant”) has submitted or will submit to the Beneficiary its Proposal (hereinafter called “the Proposal”) for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ under Request for Proposals No. \_\_\_\_\_\_\_\_\_\_\_ (“the RFP”).

Furthermore, we understand that, according to the Beneficiary’s conditions, Proposals must be supported by a Proposal guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ (\_\_\_\_\_\_\_\_\_\_\_\_) upon receipt by us of the Beneficiary’s complying demand, supported by the Beneficiary’s statement, whether in the demand itself or a separate signed document accompanying or identifying the demand, stating that either the Applicant:

(a) has withdrawn its Proposal prior to the Proposal validity expiry date set forth in the Applicant’s Letter of Proposal, or any extension thereto provided by the Applicant; or

(b) having been notified of the acceptance of its Proposal by the Beneficiary prior to the expiry date of the Proposal validity or any extension thereto provided by the Applicant, (i) has failed to execute the contract agreement, or (ii) has failed to furnish the Performance Security and, if required, an Environmental and Social (ES) Performance Security, in accordance with the Instructions to Proposers (“ITP”) of the Beneficiary’s RFP document.

This guarantee will expire: (a) if the Applicant is the successful Proposer, upon our receipt of copies of the contract agreement signed by the Applicant and the Performance Security and, if required, an Environmental and Social (ES) Performance Security issued to the Beneficiary in relation to such contract agreement; or (b) if the Applicant is not the successful Proposer, upon the earlier of (i) our receipt of a copy of the Beneficiary’s notification to the Applicant of the results of the RFP process; or (ii)twenty-eight days after the expiry date of the Proposal validity.

Consequently, any demand for payment under this guarantee must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758.

*[signature(s)]*

Form of Proposal-Securing Declaration

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Proposal No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Alternative No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

To:

We, the undersigned, declare that:

We understand that, according to your conditions, Proposals must be supported by a Proposal-Securing Declaration.

We accept that we will automatically be suspended from being eligible for submitting proposals or bidding in any contract with the Employer, for the period of time specified in Section II – Proposal Data Sheet, if we are in breach of our obligation(s) under the Proposal conditions, because we:

(a) have withdrawn our Proposal prior to the expiry date of the Proposal validity specified in the Letter of Proposal or any extended date provided by us; or

(b) having been notified of the acceptance of our Proposal by the Employer prior to the expiry date of the Proposal validity in the Letter of Proposal or any extended date provided by us, (i) fail or refuse to execute the Contract, if required, or (ii) fail or refuse to furnish the Performance Security and, if required, an Environmental and Social (ES) Performance Security, in accordance with the ITP 54.

We understand this Proposal-Securing Declaration shall expire if we are not the successful Proposer, upon the earlier of (i) our receipt of your notification to us of the name of the successful Proposer; or (ii) twenty-eight days after the expiry date of of the Proposal validity.

Name of the Proposer**\***

Name of the person duly authorized to sign the Proposal on behalf of the Proposer**\*\*** \_\_\_\_\_\_\_

Title of the person signing the Proposal \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature of the person named above \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date signed \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_

**\***: In the case of the Proposal submitted by joint venture specify the name of the Joint Venture as Proposer

\*\*: Person signing the Proposal shall have the power of attorney given by the Proposer attached to the Proposal

*[Note: In case of a Joint Venture, the Proposal-Securing Declaration must be in the name of all members to the Joint Venture that submits the Proposal.]*

Form of Sexual Exploitation and Abuse (SEA), and/or Sexual Harassment (SH) Declaration

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ RFP No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Alternative No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Contract Title: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

To:

We, the undersigned, declare that:

We understand that Proposals must be supported by a SEA and/or SH Declaration.

We accept that, if awarded the Contract, we, including our Subcontractors, are required to comply with the SEA/SH Prevention and Response Obligations (during the Design-Build Period) under the Contract, and we further accept that the Bank may disqualify us (where we are a Contractor as a joint venture or an SPV, every member of the joint venture or an SPV, as applicable), from being awarded a Bank-financed contract for a period of two years, if it is determined by Dispute Adjudication Board (DAB) decision that we:

1. have failed to correct non-compliance with identified SAE/SH Prevention and Response Obligation; and/or
2. were non-compliant with such obligations at the time of an alleged incident,

and, in the event of recourse to the Emergency Arbitration provisions under the International Chamber of Commerce Arbitration Rules, an order to reverse the DAB Decision is not issued by the Emergency Arbitrator under the Rules.

Name of the Proposer**\***

Name of the person duly authorized to sign the Proposal on behalf of the Proposer**\*\*** \_\_\_\_\_\_\_

Title of the person signing the Proposal \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature of the person named above \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date signed \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_

**\***: In the case of the Proposal submitted by joint venture specify the name of the Joint Venture as Proposer

\*\*: Person signing the Proposal shall have the power of attorney given by the Proposer attached to the Proposal

*[Note: In case of a Joint Venture, the SEA and/or SH Declaration must be in the name of all members to the Joint Venture that submits the Proposal.]*

Section V – Eligible Countries

**Eligibility for the Provision of Goods, Works and non-consulting Services in Bank-Financed Procurement**

In reference to **ITP 4.8** and **ITP 5.1**, for the information of the Proposers, at the present time firms, goods and services from the following countries are excluded from this RFP process:

Under **ITP 4.8(a)** and **ITP 5.1**: *[insert a list of the countries following approval by the Bank to apply the restriction or state “none”].*

Under **ITP 4.8(b)** and **ITP 5.1**: *[insert a list of the countries following approval by the Bank to apply the restriction or state “none”]*

Section VI – Fraud and Corruption

**(Section VI shall not be modified)**

1. **Purpose**
	1. The Bank’s Anti-Corruption Guidelines and this annex apply with respect to procurement under Bank Investment Project Financing operations.
2. **Requirements**
3. The Bank requires that Borrowers (including beneficiaries of Bank financing); bidders (applicants/ proposers), consultants, contractors and suppliers; any sub-contractors, sub-consultants, service providers or suppliers; any agents (whether declared or not); and any of their personnel, observe the highest standard of ethics during the procurement process, selection and contract execution of Bank-financed contracts, and refrain from Fraud and Corruption.
4. To this end, the Bank:
5. Defines, for the purposes of this provision, the terms set forth below as follows:
6. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;
7. “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation;
8. “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;
9. “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;
10. “obstructive practice” is:
11. deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or
12. acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under paragraph 2.2 e. below.
13. Rejects a proposal for award if the Bank determines that the firm or individual recommended for award, any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, suppliers and/ or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;
14. In addition to the legal remedies set out in the relevant Legal Agreement, may take other appropriate actions, including declaring misprocurement, if the Bank determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement process, selection and/or execution of the contract in question, without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner at the time they knew of the practices;
15. Pursuant to the Bank’s Anti-Corruption Guidelines, and in accordance with the Bank’s prevailing sanctions policies and procedures, may sanction a firm or individual, either indefinitely or for a stated period of time, including by publicly declaring such firm or individual ineligible (i) to be awarded or otherwise benefit from a Bank-financed contract, financially or in any other manner;[[12]](#footnote-12) (ii) to be a nominated[[13]](#footnote-13) sub-contractor, consultant, manufacturer or supplier, or service provider of an otherwise eligible firm being awarded a Bank-financed contract; and (iii) to receive the proceeds of any loan made by the Bank or otherwise to participate further in the preparation or implementation of any Bank-financed project;
16. Requires that a clause be included in bidding/request for proposals documents and in contracts financed by a Bank loan, requiring (i) bidders (applicants/ proposers), consultants, contractors, and suppliers, and their sub-contractors, sub-consultants, service providers, suppliers, agents, personnel, permit the Bank to inspect[[14]](#footnote-14) all accounts, records and other documents relating to the procurement process, selection and/ or contract execution, and to have them audited by auditors appointed by the Bank.

PART 2 – Employer’s Requirements

Section VII – Employer’s Requirements

Table of Content

[Employer’s Requirements 121](#_Toc135387511)

[Environmental and Social (ES) Requirements 126](#_Toc135387512)

[Environmental and Social (ES) requirements 130](#_Toc135387513)

[Scope of the Works 132](#_Toc135387514)

[Site Information 133](#_Toc135387515)

[Contractor’s Representative and Key Personnel 134](#_Toc135387516)

[Specification 136](#_Toc135387517)

[Site Plans / Concept Drawings 137](#_Toc135387518)

[Supplementary Information 138](#_Toc135387519)

Employer’s Requirements

***Notes on preparing the Employer’s Requirements***

The Employer’s Requirements contains the Scope, the Specifications, the Drawings, and Supplementary Information that describe the Works and Operation Service.

This is a “single responsibility contract”. **The Employer is not expected to provide detailed technical specifications. However, the Employer must have a clear idea of what it wants and must communicate its needs to the Proposers.** **Hence, the section on Employer’s Requirements replaces the usual Technical Specifications of a more traditional approach**.

To enable Proposers to offer appropriate solutions, the Employer should specify the purpose for which the Works are intended (see also Sub- Clause 4.1 of the Conditions of Contract) and its particular requirements as clearly as possible. **The Employer’s requirements must therefore, specify exactly the particular requirements for the completed Works.** It will also be necessary to specify the tests that will be carried out on completion of the Works to verify compliance with the requirements specified.

The Employer should perform appropriate front-end tasks (such as geotechnical/environmental investigations and permit acquisitions) to enable the Employer to: (a) develop a realistic understanding of the contract’s scope and budget; and (b) furnish Proposers with information that they can reasonably rely upon in establishing their price and other commercial decisions.

While this section of the RFP document should endeavor to define the Employer’s Requirements as precisely as possible **care must be taken to avoid over-specifying details** to the extent that the flexibility and potential benefits associated with a “single responsibility” RFP approach are seriously eroded. This section on Employer’s Requirements should, therefore, be carefully prepared by experts who are familiar with the requirements and with the technical aspect of the required Works. As the contractor is expected to carry out the design, the Employer should provide the criteria to which it expects the design to confirm. The functional/ performance specifications may specify the characteristics, nature and performance of the finished work and any limitations which the Employer wishes to impose.

The Employer’s requirements should specify the Contractor’s Documents (Sub-Clause 5.2 of the General Conditions of Contract) that are required and their submission/approval procedures.

The Employer’s Requirements must be drawn up to permit the widest, possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials performance and/or functions of the Works. The Employer’s Requirements should stipulate that all goods and materials to be incorporated in the Works are new, unused, of the most recent or current models and incorporate all recent improvements in design and materials.

Care must be taken when drafting the Employer’s Requirements to ensure that the requirements are not restrictive. Recognized international standards should be used as much as possible for the description of goods, materials and workmanship. Where other particular standards are specified, whether national standards of the Borrower’s country or other standards, it should be stated that goods, materials and workmanship meeting other authoritative standards and which promise to ensure equal or higher quality than the standards specified, will also be acceptable. Where a brand name of a product is specified it should always be qualified with the terms “or equivalent”.

For such a contract, no detailed drawings would generally be available when inviting proposals.

It would, however, be useful to include **conceptual drawings** and/or outline design, if any and as appropriate, to supplement or help explain the general concept of the Employer’s needs. Proposers should be advised to the extent to which the Employer’s outline design is a suggestion or a requirement.

The Employer shall make available to Proposers all relevant data in the Employer’s possession on sub-surface and hydrological conditions at the Site, including environmental aspects. (See Sub-Clause 4.10 of the Conditions of Contract). In addition, the Employer’s Requirements should also include, as appropriate, information of a technical nature referring to Employer’s Requirements in the following (non-exhaustive list) Sub-Clauses of the Conditions of Contract:

|  |  |  |
| --- | --- | --- |
| **Sub-Clause No.** | **Information required** | **Remarks** |
| 1.1.33 | * Employer’s Equipment
 |  |
| 1.1.43 | * Financial Memorandum
 |  |
| 1.1.55 | * Operation Service Requirements
 |  |
| 1.9 | * Number of copies of Contractor’s Documents
* Publications to be kept on Site
 |  |
| 1.12 | * Intellectual Property rights retained by Employer
 |  |
| 1.14 | * Permissions being obtained by the Employer
 |  |
| 2.1 | * Possession of foundations, structures, plant or means of access
 | Please also refer to Sub-Clause 2.1 (Part A- Contract Data) to ensure consistency and applicability. |
| 4.1 | * Intended purposes for which the Works are required
 | As mentioned above |
| 4.5 | * Nominated Subcontractors
 |  |
| 4.6 | * Other contractors and others on Site, if any
* Documents relating to Contractor possession of assets
 |  |
| 4.7 | * Setting- out points, lines and levels of reference
 | The Sub-Clause states: “… specified in the contract or notified by the Employers Representative” |
| 4.18 | * Emissions, surface discharges and effluent.
 |  |
| 4.19 | * Details and prices of electricity, water, gas and other services if the services are to be available for the Contractor to use.
 |  |
| 4.20 | * Details of Employer’s Equipment and free-issue material, if any.
 |  |
| 4.21 | * Number of copies of progress reports
* Contents of progress reports
* Reporting requirements for the Operation Service
 |  |
| 4.27 | * Existing facilities
 |  |
| 5.1 | * Criteria (if any) for design personnel
 | *this may be part of the Key Personnel requirements in this Section VII.* |
| 5.2 | * Contractor’s Documents required and whether for approval
 | Specify, as appropriate, the extent to which the Contractor’s Documents are required, which of them are required for approval or consent (not just review), and the submission procedures. *As appropriate, also include any applicable requirements for mandatory review/checking and/or verification of, for example, design of structural elements by competent authorities or professionals. If so, include: (i) the processes required and whether, and to what extent, such reviews and/or verification of an element of design (and the Contractor’s documents associated with such element) shall replace the Employer’s Representative’s review under this Sub-Clause.*  |
| 5.4 | * Applicable Technical Standards and regulations
 | *This is also included under “Environmental and Social Requirements” below.* |
| 5.5 | * As- built drawings and other records of the Works
 |  |
| 6.1 | * Engagement of staff and labour
 |  |
| 6.6 | * Facilities for Contractor’s Personnel
* Facilities for Employer’s staff
 |  |
| 7.2 | * Samples
 |  |
| 7.4 | * Testing
 |  |
| 7.8 | * Royalties
 |  |
| 8.7 | * Handback requirements
 |  |
| 10.3 | * Terms for appointment of the Auditing Body
 |  |
| 10.4 | * Free issue materials, fuels, consumables and other items to be provided by the Employer:
 |  |
| 10.5 | * Training required for Employer’s Personnel
* Training materials
 |  |
| 11.1 | * Tests for completion of the Design-Build
 |  |

***Any additional******sustainable procurement technical requirements*** *(in addition to the ES requirements stated in the Environmental and Social Requirements section below) for the Works shall be clearly specified. Please refer to the Bank’s Procurement Regulations for Borrowers and Sustainable procurement guidance for further information. The sustainable procurement requirements shall be specified to enable evaluation of such requirements, as appropriate. This is a broad area and the requirements should be consistent with the objectives of the contract; (examples of such broad areas to be detailed as appropriate may include, but not limited to, energy efficiency, emission reduction, other methods for minimizing the carbon impact in the execution of the Works and/or the completed Works etc.) To encourage Proposers’ innovation in addressing sustainable procurement requirements, as long as the Proposal evaluation criteria specify the mechanism for monetary adjustments and/or rated criteria evaluation for the purpose of Proposals comparison, Proposers may be invited to offer Works that exceed the specified minimum sustainable procurement requirements.*

*[If the contract has been assessed to present potential or actual cyber security risks, the Employer shall specify cyber security requirements, including cyber security accreditations as appropriate.]*

*[If there are supply chain risks, the Employer shall require the Proposer to include its assessment of supply chain risks and proposal to manage the risks]*

*Separate draft templates for Employer’s Requirements for Water Treatment Plant and Wastewater Treatment Plant have been prepared to be used in conjunction with these SPDs and are annexed to the Guidance Note to these SPDs. The Employer should also take into account the general guidance set out here when drafting the Employer’s Requirements.*

Environmental and Social (ES) Requirements

***[Note to Employer: Notes under option 1 are intended for Projects with Project Concept Notes (PCN) Decision Notes dated after October 1, 2018.]***

***[OPTION 1]***

*[The Employer’s team preparing the ES requirements should include a suitably qualified Environmental and Social specialist/s.*

*In preparing detailed specifications for ES requirements the Borrower should refer to and consider the applicable environmental and social standards in the ESF including the specific requirements set out in the Environmental and Social Commitment Plan (ESCP), EHSGs and other GIIP as well as SEA and SH prevention and management obligations.*

*The ES requirements should be prepared in manner that does not conflict with the relevant General Conditions of Contract (and the corresponding Particular Conditions of Contract if any)* *and other parts of the Employer’s Requirements.*

*The following is a non-exhaustive list of Sub-Clauses of the Conditions of Contract that make reference to ES matters stated in the Employer’s Requirements]*

| **Sub-Clause/Clause No.** |  **Sub-Clause/Clause** | **Remarks** |
| --- | --- | --- |
| *4.6* | *Co-operation* | *Indicate specific aspects (if any) that require contractor’s cooperation such as to conduct environmental and social assessment.* |
| *4.8* | *Health and Safety Obligations* | *Indicate if access to or provision of services that accommodate physical, social and cultural needs of Contractor’s Personnel is required.**Indicate any additional requirements for the health and safety manual*  |
| *4.18* | *Protection of the Environment* | *Specify any values for emissions, surface discharges, effluent and any other pollutants from the Contractor’s activities that shall not be exceeded. The Contractor’s C-ESMP shall set out the measures the Contractor will take to ensure compliance with these limit values.* |
| *4.22* | *Security of the Site* | *State any additional requirements for the security arrangements (ESS4 of the ESF states the principles of porportionality, GIIP and applicable Laws. Include any other requirement set out in the ESCP.* |
| *4.24* | *Archeological and Geological Findings* | *Specify other requirements if any in accordance with the ESF – ESS8* |
| *5.4* | *Technical Standards and Regulations* | *State any:** *applicable technical standards and requirements including to address:*
* *climate change considerations,*
* *universal access,*

*risks of the public’s potential exposure to operational accidents or natural hazards, including extreme weather events,* |
| *6.2* |  *Rate of Wages and Conditions of Employment* | *State applicable requirements in accordance with the labour management procedure.* |
| *6.5* | *Working Hours* | *State applicable requirements in accordance with the labour management procedure.* |
| *6.27* | *Training of Contractor’s Personnel* | *As set out in the ESCP, specify, , details of any training to relevant Contractor’s Personnel to be provided by the Employer’s Personnel on environmental and social aspects. (*whom, what, when, where, how long etc.) |

*In addition to provisions in the above table, the Employer shall specify the following as applicable.*

***Management and Safety of Hazardous Materials***

*As applicable, specify requirements for the management and safety of hazardous materials (see ESF - ESS4 para. 17 and 18* *and relevant guidance notes).*

***Resource Efficiency and Pollution Prevention and Management***

*As applicable specify Resource Efficiency and Pollution Prevention and Management measures (see ESF -ESS3 and relevant guidance notes).*

* ***Resource efficiency***

*The Employer shall specify, as applicable, measures for improving efficient consumption of energy, water and raw materials, as well as other resources.*

* ***Energy:*** *When the Works have been assessed to involve a potentially significant use of energy, specify any applicable measures to optimize energy usage.*
* ***Water:*** *When the Works have been assessed to involve a potentially significant use of water or will have potentially significant impacts on water quality, specify any applicable measures that avoid or minimize water usage so that the Works’ water use does not have significant adverse impacts on communities, other users and the environment.*
* ***Raw material:*** *When the Works have been assessed to involve a potentially significant use of raw materials, specify any applicable measures to support efficient use of raw materials.*
* ***Pollution prevention and management***
* ***Management of air pollution:*** *specify any measure to avoid or minimize Works related air pollution**.* *See also Sub-Clause 4.18 of the Special Provisions and the table above on* ***Conditions*** *of Contract that make reference to ES matters in the Employer’s Requirements.*
* ***Management of hazardous and nonhazardous wastes:*** *specify any applicable measures to minimize the generation of waste, and reuse, recycle and recover waste in a manner that is safe for human health and the environment including storage, transportation and disposal of hazardous wastes.* *See also Sub-Clauses 4.8 and 4.18 of the Special Provisions and the table above on Conditions of Contract that make reference to ES matters in the Employer’s Requirements.*
* ***Management of chemicals and hazardous materials:*** *specify any applicable measures to**minimize and control the release and use of hazardous materials for Works activities including the production, transportation, handling, and storage of the materials.**See also Sub-Clauses 4.8 and 4.18 of the Special Provisions and the table above on Conditions of Contract that make reference to ES matters in the Employer’s Requirements.*
* ***Biodiversity Conservation and Sustainable Management of Living Natural Resources***

*The Employer shall specify, as applicable, Biodiversity Conservation and Sustainable Management of Living Natural Resources (see ESF - ESS6 and relevant guidance notes). This includes, as applicable:*

* *invasive alien species: managing the risk of invasive alien species during the execution of the Works;*
* *sustainable management of living natural resources; and*
* *certification and verification requirements for the supply of natural resource materials where there is a risk of significant conversion or significant degradation of natural or critical habitats.*

*See also Sub-Clause 4.18 of the Special Provisions and the table above on Conditions of Contract that make reference to ES matters in the Employer’s Requirements.*

***Road Safety***

*State any specific traffic and road safety requirement, as applicable. See also Sub-Clause 4.15 of the Special Provisions. For details, refer to the Guidance Note on Road safety.*

**SPECIFIED PROVISIONAL SUMS for ES OUTCOMES**

The total of the prices of the activities in the Activity Schedule is the Proposer’s offer to complete the works on a “single responsibility” basis. This includes all of the Contractor’s ES obligations under the Contract.

*Provisional sums may be specified by the Employer for achieving specific ES outcomes. (e.g.* *for HIV counselling service, and SEA and SH awareness and sensitization or to encourage the contractor to deliver ES outcomes beyond the requirement of the Contract*).

Environmental and Social (ES) requirements

***[Note to Employer: Notes under option 2 are intended for Projects with Project Concept Notes (PCN) Decision Notes on or before October 1, 2018.]***

***[OPTION 2]***

*[The Employer’s team preparing the ES requirements should include a suitably qualified Environmental and Social specialist/s.*

*The Employer should attach or refer to the Employer’s environmental and social, policies that will apply to the project. If these are not available, the Employer should use the following guidance in drafting an appropriate policy for the Works.*

**Suggested content for an Environmental and Social Policy (Statement)**

*The Works’ policy goal, as a minimum, should be stated to integrate environmental protection, occupational and community health and safety, gender, equality, child protection, vulnerable people (including those with disabilities), sexual harassment, gender-based violence, Sexual Exploitation and Abuse (SEA), HIV/AIDS awareness and prevention and wide stakeholder engagement in the planning processes, programs, and activities of the parties involved in the execution of the Works. The Employer is advised to consult with the World Bank to agree the issues to be included which may also address: climate adaptation, land acquisition and resettlement, indigenous people*, etc. *The policy should set the frame for monitoring, continuously improving processes and activities and for reporting on the compliance with the policy.*

*The policy shall include a statement that, for the purpose of the policy and/or code of conduct, the term “child” / “children” means any person(s) under the age of 18 years.*

*The policy should, as far as possible, be brief but specific and explicit, and measurable, to enable reporting of compliance with the policy in accordance with the Particular Conditions- Special Provisions- Sub-Clause 4.20.*

*As a minimum, the policy is set out to the commitments to:*

1. *apply good international industry practice to protect and conserve the natural environment and to minimize unavoidable impacts;*
2. *provide and maintain a healthy and safe work environment and safe systems of work;*
3. *protect the health and safety of local communities and users, with particular concern for those who are disabled, elderly, or otherwise vulnerable;*
4. *be intolerant of, and enforce disciplinary measures for illegal activities. To be intolerant of, and enforce disciplinary measures for gender-based violence, inhumane treatment, sexual exploitation, rape, sexual assault, sexual activity with children, and sexual harassment;*
5. *incorporate a gender perspective and provide an enabling environment where women and men have equal opportunity to participate in, and benefit from, planning and development of the Works;*
6. *work co-operatively, including with end users of the Works, relevant authorities, contractors and local communities;*
7. *engage with and listen to affected persons and organizations and be responsive to their concerns, with special regard for vulnerable, disabled, and elderly people;*
8. *provide an environment that fosters the exchange of information, views, and ideas that is free of any fear of retaliation, and protects whistleblowers;*
9. *minimize the risk of communicable diseases and to mitigate the effects of communicable diseases associated with the execution of the Works;*

*The policy should be signed by the senior manager of the Employer. This is to signal the intent that it will be applied rigorously.*

**Minimum Content of ES requirements**

*In preparing detailed specifications for ES requirements, the specialists should refer to and consider:*

* *relevant project reports consent/permit conditions*
* *required standards including World Bank Group EHS Guidelines*
* *relevant international conventions or treaties etc., national legal and/or regulatory requirements and standards (where these represent higher standards than the WBG EHS Guidelines)*
* *relevant international standards e.g. WHO Guidelines for Safe Use of Pesticides*
* *relevant sector standards e.g. EU Council Directive 91/271/EEC Concerning Urban Waste Water Treatment*
* *grievance redress mechanism including types of grievances to be recorded and how to protect confidentiality e.g. of those reporting allegations of SEA.*
* *SEA prevention and management.*

*The detail specification for ES should, to the extent possible, describe the intended outcome rather than the method of working.* *The ES requirements should be prepared in manner that does not conflict with the relevant General Conditions and Particular Conditions.*

**SPECIFIED PROVISIONAL SUMS for ES OUTCOMES**

*The total of the prices of the activities in the Activity Schedule is the Proposer’s offer to complete the works on a “single responsibility” basis.*

*This includes all of the Contractor’s ES obligations under the Contract.*

*Provisional sums may be specified by the Employer for achieving specific ES outcomes. (e.g.* *for HIV counselling service, and SEA awareness and sensitization or to encourage the contractor to deliver ES outcomes beyond the requirement of the Contract*).

Scope of the Works

*[See template of Employer Requirements for Water/ Wastewater Treatment Plant]*

Site Information

*[See template of Employer Requirements for Water/ Wastewater Treatment Plant]*

Contractor’s Representative and Key Personnel

*[****Note: Insert in the following table, the minimum key specialists required to execute the contract, taking into account the nature, scope, complexity and risks of the contract****.]*

**Contractor’s Representative and** **Key Personnel**

|  |  |  |  |
| --- | --- | --- | --- |
| **Item No** | **Position/specialization** | **Relevant academic qualifications** | **Minimum years of relevant work experience** |
| *1* | *[Contractor’s Representative]* | *e.g. degree in relevant field.* | *e.g.[years]* working on road projects in similar work environments |
| *2.* | *[If the contract has been assessed to present potential or actual cyber security risks, the Proposer must be required to include Cyber security expert/s among the Key Personnel.]* |  |  |
| ***Key Personnel for Design***  |
| *3.* | *[Design Manager]* |  |  |
| *4.* | [Environmental Impact Assessment Specialist] |  |  |
| *5.* | *[Social Impact Assessment Specialist]* |  |  |
| *6.* | [Health and Safety Specialist] |  |  |
| *7.* | *[Biodiversity, Air quality, Noise etc. Specialists]* |  |  |
| *8.* | *[Modify/add others as appropriate]* |  |  |
| ***Key Personnel for Construction*** |
| *9.* | *[Construction Manager]* |  |  |
| *10.* | *[Environmental Specialist]* |  |  |
| *11.* | *[Health and Safety Specialist]* |  |  |
| *12.* | *[Social Specialist]* |  |  |
| *13.* | *Survey Manager* |  |  |
| *14.*  | *Sexual Exploitation, Abuse and Harassment Expert(s)* *[Where a Project SEA risks are assessed to be substantial or high, Key Personnel shall include an expert (s) with relevant experience in addressing sexual exploitation, sexual abuse and sexual harassment cases]* |  | *[e.g. 5 years of monitoring and managing risks related to gender-based violence, out of which 3 years of relevant experience in addressing issues related to sexual exploitation, sexual abuse and sexual harassment]* |
| *15.* | *[Modify/add others as appropriate]* |  |  |
| ***Key Personnel for operation service*** |
| *16.* | *Plant Manager*  |  |  |
| *17.* | *EHS Manager* |  |  |
| *18.* | *Community Relations Manager* |  |  |
| *19.* | *[Modify/add others as appropriate]* |  |  |

Specification

*[Insert the specifications-see note above on drafting the specifications. The specifications should set out the applicable minimum standards that apply for the Works. In addition, other technical requirements to be incorporated in the design should be set out]*

Site Plans / Concept Drawings

Supplementary Information

PART 3 – Conditions of Contract and Contract Forms

Section VIII – General Conditions (GC)

Gold Book:

© FIDIC 2008. All rights reserved.

The Conditions of Contract are the “General Conditions” which form part of the “Conditions of Contract for Design, Build and Operate Projects first edition 2008” published by the Federation Internationale Des Ingenieurs – Conseils (FIDIC and the following “Particular Conditions” which comprise of the *World Bank’s* COPA and the amendments and additions to such General Conditions.

An original copy of the above FIDIC publication i.e. “Conditions of Contract for Design, Build and Operate Projects” must be obtained from FIDIC.

International Federation of Consulting Engineers (FIDIC)

FIDIC Bookshop – Box- 311 – CH – 1215 Geneva 15 Switzerland

Fax: +41 22 799 49 054

Telephone: +41 22 799 49 01

E-mail: fidic@fidic.org

[www.fidic.org](http://www.fidic.org)

FIDIC code: ISBN13: 978-2-88432-052-8

Section IX – Particular Conditions (PC)

The following particular conditions shall supplement the General Conditions. Whenever there is a conflict, the provisions herein shall prevail over those in the General Conditions.

**Particular Conditions of Contract**

**Part A – Contract Data**

| **Conditions** | **Sub-Clause** | **Data** |
| --- | --- | --- |
| Where the Contract allows for Cost Plus Profit, percentage profit to be added to the Cost: | 1.1.24 |  \_\_\_\_\_\_\_ *[insert the %, normally 5%]* |
| Cut-Off Date (number of days after the Time for Completion of Design-Build): | 1.1.26 | *[number of days]* |
| Employer’s Representative’s name and address:For the Design Build Period:For the Operation Service Period: | 1.1.35 |  |
| Parts of the Works that shall be designated a Section for the purposes of the Contract: | 1.1.70 |  |
| Time for Completion of Design-Build: | 1.1.78 | \_\_\_\_\_\_\_\_ days |
| Borrowers Name: | 1.1.85 |  |
| Agreed methods of electronic transmission: | 1.3 |  |
| Address of Employer for communications: | 1.3 |  |
| Address of Employer’s Representative for communications:For the Design Build Period:For the Operation Service Period: | 1.3 |  |
| Address of Contractor for communications: | 1.3 |  |
| Governing law: | 1.4 |  |
| Ruling language: | 1.4 |  |
| Language for communications: | 1.4 |  |
| Time for the Parties to sign a Contract Agreement | 1.6 | 28 days after receipt of the Letter of Acceptance |
| Joint and Several Liability:Type and minimum amounts of paid up share capital required:Minimum shareholding requirement after lock-in period: | 1.15 | If JV is permitted to form an SPV, specify here*[ ]*Lead shareholderOther shareholders |
| Time for access to the Site: | 2.1 | *[ Ideally, the right of access to and possession of all parts of the Site shall be given by the Commencement Date. If this is the case, insert: “No later than the Commencement Date”]* *[If it is not practical or feasible to give the right of access to and possession of all parts of the Site by the Commencement Date, select either of the following options and delete the remaining text in this Particular Conditions, Sub-Clause 2.1:**Option 1**“No later than the Commencement Date, except for the following parts ((include description of parts concerned) in a time and manner stated in the Employer’s Requirements.”**Option 2*  *“No later than the Commencement Date, except for the following parts (include description of parts concerned): within such times as may be required to enable the Contractor to proceed in accordance with the Programme or, if there is no Programme at that time, the initial programme submitted under Sub-Clause 8.3 [Programme”]]*  |
| Employer approval not required for variations less than: | 3.1 | …….. % of Accepted Contract Amount |
| Cyber security- Contractor’s obligations | 4.1 | *[If the contract has been assessed to present potential or actual cyber security risks, state that the cyber security provision at the end of Part B- Special Provisions- Sub-Clause 4.1 applies; otherwise state: “N/A”]* |
| Performance Security: | 4.2 | The Performance Security will be in the form of a \_\_\_\_ *[insert either one of “demand guarantee” or “performance bond”]* in the amount(s) of *[insert related figure(s)]* percent of the Accepted Contract Amount for the Design Build and in the same currency (ies) of the Accepted Contract Amount. |
| Reduction in Performance Security at the end of the Retention Period:Further reduction in Performance Security following five consecutive years of Operation Service during which the Contractor has achieved full compliance with the standards specified in the Schedule of Performance Standards | 4.2 |  |
| Environmental and Social (ES) Performance Security:ES Performance Security Required:Amount and type of the ES Performance Security: | 4.2 | **Yes / No**The ES Performance Security will be in the form of a “*demand guarantee”* in the amount(s) of *[insert % figure(s) normally 1% to 3%]* of the Accepted Contract Amount for the Design Build and in the same currency(ies) of the Accepted Contract Amount.***[The sum of the total “demand guarantees” (Performance Security and ES Performance Security) shall normally not exceed 10% of the Accepted Contract Amount for Design Build.]*** |
| Cyber security | 4.21 | [*[If the contract has been assessed to present potential or actual cyber security risks, indicate that the Progress Reports shall include cyber security aspects in accordance with Part B- Special Provisions- Sub-Clause 4.21; otherwise state: “N/A”.]* |
| Cyber security-immediate reporting | 4.21 | [*[If the contract has been assessed to present potential or actual cyber security risks, indicate Cyber security incidents to be immediately reported in accordance with Part B- Special Provisions- Sub-Clause 4.21; otherwise state: “N/A”.]* |
| Period for notification of errors, faults and other defects: | 5.1 | Days *[state number of days, normally not less than 28 days]* |
| Normal working hours on the Site: | 6.5 |  |
| Period of the Operation Service: | 8.2 | *[ ]* months |
| Time for Completion of Design-Build: | 9.2, 1.1.78 | *[ ]* months |
| Time for Completion of each Section: | 9.2, 1.1.78 | *[ ]* months |
| Delay damages payable for each day of delay | 9.6 | \_\_\_\_\_% of the Accepted Contract Amount for Design-Build, less provisional sum for DAB .*[If Sections are to be used, refer to Table: Summary of Sections below]* |
| Maximum amount of delay damages  | 9.6 | \_\_\_\_\_% of the Accepted Contract Amount for Design-Build less provisional sum for DAB. *[normally not exceeding 10%]* |
| Commencement Date if different from PC 10.2. | 10.2 |  |
| Maximum amount of Performance Damages payable by the Contractor (Operation Service): | 10.6 and 10.7 |  |
| Maximum amount of compensation payable by Employer (Operation Service): | 10.6b |  |
| Maximum amount of performance damages payable by the Contractor in any contract year during the Operation Service Period: | 10.6 and 10.7 |  |
| Rights of the Employer if the failure continues for more than 84 days: | 10.7 | *[if to be different from that as set out in Sub-Clause 10.7]* |
| Cyber security- Variation | 13.3 (a) | *[If the contract has been assessed to present potential or actual cyber security risks, state that the detailed particulars to be submitted to the Employer’s Representative shall include sufficient information to enable assessment of cyber security risks.]* |
| Percentage rate to be applied to Provisional Sums for overhead charges and profits: | 13.5 | \_\_\_% |
| Contract Price and Rates and Prices to be adjusted for changes in cost as further detailed in the Schedule of Cost Indexation:a) Design-Buildb) Operation Service (excluding Asset Replacement)c) Asset Replacement | 13.8 | a) Yes /Nob) Yes /Noc) Yes /No |
| Price adjustment permitted in Accepted Contract Amount for Operation Service to account for long term variations in Influent quality relative the Influent Baseline. | 13.9 | Yes /No*[If price adjustment is permitted then the Employer* ***must*** *include an Influent Baseline in the Employer’s Requirements]*  |
| Amount of Advance Payment  | 14.2 | \_\_\_\_\_\_\_\_% of the Accepted Contract Amount for the Design Build payable in the currencies and proportions in which the Accepted Contract Amount for Design Build is payable |
| Percentage deductions for the repayment of the Advance Payment: | 14.2 |  |
| Requirements for submission of Statements if different from the GC and PC: | 14.3 |  |
| Percentage of Retention: | 14.3 | \_\_\_\_% *[Insert percentage of retention, normally 5% and not exceeding 10%]* |
| Limit of Retention Money: | 14.3 | \_\_\_\_\_\_\_% *[Insert percentage of retention, normally 5% and not exceeding 10%]* |
| Plant and Materials for payment when shipped: | 14.6(b)(i) |  |
| Plant and Materials for payment when delivered to the Site: | 14.6(c)(i) |  |
| Minimum Amount of Interim Payment Certificate applicable for the Design-Build. Minimum Amount of Interim Payment Certificate applicable for the Operation Service.  | 14.7(b) |  |
| Cyber security- withholding payments | 14.7 | *[If the Contract has been assessed to present potential or actual cyber security risks, indicate that payments may be withheld for the Contractor’s failure to perform Cyber security obligations; otherwise state: “N/A”.]* |
| Financing charges for delayed payment: | 14.9 |  |
| Currencies for payment of Contract Price:*[or reference Schedule of Payments]* | 14.17 |  |
| Proportions of Local and Foreign Currencies are:*[or reference Schedule of Payments]* | 14.17 |  |
| Rate of Exchange*[or reference Schedule of Payments]* | 14.17 |  |
| Currencies of Payment of damages shall be:During the Design-BuildDuring the Operation Service: | 14.17 | *[insert currencies or reference Schedule of Performance Damages]* |
| Amount of Maintenance Retention Fund: | 14.19 |  |
| Operation of forces of nature allocated to the Contractor: | 17.1 b (iii) |  |
| Total liability of the Contractor shall not exceed: | 17.8 |  |
| Permitted deductible limits: | 19.2(a)(i) |  |
| Additional sum to be insured: | 19.2(a)(ii) |  |
| Employer’s Risks to be insured if different to Sub-Clause 17.1: | 19.2(a)4 |  |
| Exceptional Risks to be insured if different to Sub-Clause 18.1: | 19.2(a)5 |  |
| Insurance of Contractor’s Equipment (minimum amount required): | 19.2(b) | *[insert amount of insurance]* |
| Minimum amount of professional liability insurance required: | 19.2(c) | *[insert amount of insurance]* |
| Period for which professional liability insurance required: | 19.2(c)  |  |
| Minimum amount of insurance required for injury to persons and damage to property: | 19.2(d) | *[insert amount of insurance]* |
| Other insurances required from the Contractor (give details): | 19.2(f)  |  |
| Minimum amount of fire extended cover insurance required: | 19.3(a) | *[insert amount of insurance]* |
| Minimum amount of insurance required to cover injury to any person and damage to property: | 19.3(b) | *[insert amount of insurance]* |
| Other insurances required by law from the Contractor (give details): | 19.3(d) |  |
| Other optional insurances required from the Contractor (give details): | 19.3(e) |  |
| Time for appointment of DAB member(s): | 20.3 | 42 days after signature by both parties of the Contract Agreement.  |
| The DAB shall be comprised of: | 20.3 | *Either*: one sole Member*Or:* three Members*[For a Contract estimated to cost above USD 50 million, the DAB shall comprise of three members. For a Contract estimated to cost between USD 20 million and USD 50 million, the DAB may comprise of three members or a sole member. For a Contract estimated to cost less than USD 20 million, a sole member is recommended.]* |
| List of proposed members of DAB | 20.3 | Proposed by Employer [*Attach CVs to the request for proposals document and the Contract*]*1.\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**2.\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**3.\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Proposed by Contractor [*Attach CVs to the Contract*]*1.\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**2.\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**3.\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* |
| Appointment (if not agreed) to be made by: | 20.4 | *[Insert name of an international organization or official as the appointing entity or official]* |

**Table: Summary of Sections**

|  |  |  |
| --- | --- | --- |
| **Section Name/Description****(Sub-Clause 1.1.70)** | **Time for Completion of Design Build****(Sub-Clause 1.1.78)** | **Damages for Delay** **(Sub-Clause 9.6)** |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**Particular Conditions of Contract**

**Part B- Special Provisions**

|  |  |
| --- | --- |
| **Sub-Clause 1.1.11** | **Contract Agreement**: “if any” is deleted. |
| **Sub-Clause 1.1.21** | **Contractor’s Personnel**The following is added at the end of the sub-clause: “Contractor’s Personnel includes Key Personnel included in the Contract.” |
| **Sub-Clause 1.1.49** | **Letter of Tender**After “entitled letter of tender”, “or letter of Proposal” is added. |
| **Sub-Clause 1.1.72** | **Site**After “are to be executed”, “, including storage and working areas,” is added. |
| **Sub-Clause 1.1.84 to 1.1.93 are added after Sub-Clause 1.1.83** |
| **Sub-Clause 1.1.84** | **“Bank”** means The International Bank for Reconstruction and Development and/or the International Development Association (whether acting on its own account or in its capacity as administrator of trust funds provided by other donors. |
| **Sub-Clause 1.1.85** | **“Borrower”** means the borrower or recipient of Bank’s Investment Project Financing (IPF) identified in the Contract Data. |
| **Sub-Clause 1.1.86** | “**ES**” means Environmental and Social (including Sexual Exploitation and Abuse (SEA) and Sexual Harassment (SH)). |
| **Sub-Clause 1.1.87** | “**Sexual Exploitation and Abuse” “(SEA)”** means the following:**Sexual Exploitation** is defined as any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another. **Sexual Abuse** is defined as the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions; and **“Sexual Harassment” “(SH)”** is defined as unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature by the Contractor’s Personnel with other Contractor’s or Employer’s Personnel.**“SEA/SH Prevention and Response Obligations”** means the Contractor’s obligations during the Design-Build Period in regards to the prevention of and response to SEA/SH as set forth in Sub-Clauses 4.1, 4.4, 4.21, 4.29, 6.9, 6.26, and 6.27. |
| **Sub-Clause 1.1.88** |  **“Existing Facilities”** means the existing plant, equipment, buildings and other assets at the Site to be taken over and operated by the Contractor as further described in the Employer’s Requirements. |
| **Sub-Clause 1.1.89** |  **“Performance Standards”** means the standards to be achieved by the Contractor during the Operations Period and includes the standards specified in the Schedule of Performance Standards. |
| **Sub-Clause 1.1.90** | **“Schedule of Performance Standards”** means the schedule attached to the Contract Agreement specifying the core output Performance Standards to be achieved by the Works and the Contractor at commissioning and during the Operation Service Period. |
| **Sub-Clause 1.1.91** |  **“Schedule of Performance Damages”** means the schedule attached to the Contract Agreement which specifies the amounts of damages payable by the Contractor in respect of a breach of the standards specified in the Schedule of Performance Standards. |
| **Sub-Clause 1.1.92** |  **“Influent”** means the untreated water/ wastewater entering the Works at the delivery point to the Works).  |
| **Sub-Clause 1.1.93** |  **“Influent Baseline”** means the quality characteristics of the untreated Influent as set out in the Employer Requirements, used as the baseline for the design of the Works.” |
| **Sub-Clause 1.2** | **1.2 Interpretation**The following is added as a new sub- clause: Unless inconsistent with any provision of the Contract, the meaning of any trade term and the rights and obligations of the Parties thereunder shall be prescribed by Incoterms. Incoterms means international rules for interpreting trade terms published by the International Chamber of Commerce (latest edition), 38 Cours Albert 1er, 75008 Paris, France. |
| **Sub Clause 1.2(g)** | **Tender**The following is added as a new sub-clause: (e) “the word “tender” is synonymous with “Proposal” and “tenderer” with “Proposer” and the words “tender documents” with “request for proposal documents”. |
| **Sub-Clause 1.3** | **Communications**In the third line “, discharges” is added after “requests.” |
| **Sub-Clause 1.4** | **Law and Language**the whole Sub-Clause is replaced with the following in its entirety: “**1.4 Law and Language**The second sentence is deleted and replaced by:“The ruling language of the Contract shall be that stated in the Contract Data.” |
| **Sub-Clause 1.5** | **Priority of Documents**The following documents are added in the list of Priority Documents after (e): “(f) the Particular Conditions Part C- Fraud and Corruption;(g) the Particular Conditions Part D- Environmental and Social (ES) Metrics for Progress Reports;(h) Particular Conditions- Part E- Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment Performance Declaration for Subcontractors during;” and the list renumbered accordingly. |
| **Sub-Clause 1.6** | **Contract Agreement**in the second line “unless they agree otherwise” is replaced with “unless the Particular Conditions establish otherwise.” |
| **Sub-Clause 1.7** | **Operating License**The first paragraph is deleted and replaced with the following: “In consideration of the Contractor’s performance of the Operation Service, from the date of commencement of the Operation Service the Employer grants to the Contractor for the Operation Service Period, the exclusive right, license and authority to occupy, use and enjoy the Site free of charge and free and clear of all claims for the purposes of carrying the Operation Services. Together with the Letter or Acceptance, the Employer shall, where necessary, issue, or cause to be issued, to the Contractor the Operating License or equivalent legal authorization to enable the Contractor to operate and maintain the Works during the Operation Service Period.” This Operating License shall come into full force and effect upon the issue of the Commissioning Certificate required under Clause 11.7 and shall remain in force during the Operation Service Period.” |
| **Sub-Clause 1.8** | **Assignment**The whole sub-clause is replaced with the following:“(a) Except as provided in (b), (c) and (d) below, neither Party shall assign the whole or any part of the Contract or any benefit or interest in or under the Contract without the consent of the other Party. (b) The Contractor may as security in favour of a bank or financial institution, assign its right to any monies due, or to become due, under the Contract.(c) During the Operation Service Period, the Employer may assign the whole of the Contract to the agency, if any, specified in the Contract Data subject to the following:1. The Employer shall provide at least 90 days’ written notice to the Contractor of its intention to assign the Contract. Such notice shall specify the financial arrangements that have been made for payment of the Contract Price to the Contractor.
2. The Employer shall not assign the Contract until reasonable evidence has been provided to the Contractor that financial arrangements have been made, and will be maintained, which will enable the agency to pay the Contract Price punctually.

(d) Where the Contractor is composed of a joint venture, no joint venture member shall assign or novate its interest in the Contract or the joint venture until the second anniversary of the date of the Commissioning Certificate. Following the second anniversary of the issue of the Commissioning Certificate a joint venture party that is not the lead member of the joint venture may assign its interest to the other partners to the joint venture on the consent of the Employer, such consent not to be unreasonably withheld.(e) Where the Contractor is an SPV, no member of the SPV shall assign its holding in the SPV until the second anniversary of the date of the Commissioning Certificate. Following the second anniversary of the issue of the Commissioning Certificate a member of the SPV on the consent of the Employer, such consent not to be unreasonably withheld, dilute its shareholding in the SPV to the percentage stated in the PDS.  |
| **Sub-Clause 1.9** | **Care and Supply of Documents**“of a technical nature” is deleted from the last paragraph. |
| **Sub-Clause 1 .13** | **Confidential Details**Sub-Clause 1.13 is replaced with the following in its entirety:“**1.13 Confidential Details**The Contractor’s Personnel and the Employer’s Personnel shall disclose all such confidential and other information as may be reasonably required in order to verify compliance with the Contract and allow its proper implementation.Each of them shall treat the details of the Contract as private and confidential, except to the extent necessary to carry out their respective obligations under the Contract, to comply with applicable Laws or the information is required by the Bank. Each of them shall not publish or disclose any particulars of the Works prepared by the other Party without the previous agreement of the other Party. However, the Contractor shall be permitted to disclose any publicly available information, or information otherwise required to establish his qualifications to compete for other projects.” |
| **Sub-Clause 1.14** | **Compliance with Laws**At the end of (b), “failure to do so.” is replaced with “failure to do so, unless the Contractor is impeded to accomplish these actions and shows evidence of its diligence.” |
| **Sub-Clause 1.15.2** | **Joint and Several Liability**Before “If the Contractor constitutes” “1.15.1” is added. The following is then added:“1.15.2 If the Contractor is an SPV, throughout the Contract Period, the Contractor shall be bound to maintain its share capital at a minimum level of set out in the Contract Data of the total paid up share capital of the Contractor. The share capital may be increased without the Employer’s prior approval but a written notice of information shall be sent to the Employer. Any reduction of the Contractor’s share capital shall be subject to the prior written consent of the Employer.1.15.3 The Lead Member who holds at least fifty-one percent (51%) of the subscribed and paid up equity of the Contractor at the Commencement Date shall continue holding at least fifty-one percent (51%) of the subscribed and paid up equity of the Contractor for a period up to the second anniversary of the date of the Commissioning Certificate, [and at least twenty-six percent (26%) for the following five (5) years] subject to the transferee having similar experience to the Lead Member and the approval of the Employer. 1.15.4 The other Members who hold less than forty-nine percent (49%) of the subscribed and paid up equity of the Contractor at the Commencement Date shall continue holding the same percentage of the subscribed and paid up equity of the Concessionaire up to the second anniversary of the date of the Commissioning Certificate.” |
| **Sub-Clause 1.16** | **Inspections and Audit by the Bank**The following Sub-Clause is added after Sub-Clause 1.15: “**1.16 Inspections and Audit by the Bank**Pursuant to paragraph 2.2 e. of Particular Conditions - Part C- Fraud and Corruption, the Contractor shall permit and shall cause its agents (where declared or not), subcontractors, subconsultants, service providers, suppliers, and personnel, to permit, the Bank and/or persons appointed by the Bank to inspect the site and/or the accounts, records and other documents relating to the procurement process, selection and/or contract execution, and to have such accounts, records and other documents audited by auditors appointed by the Bank. The Contractor’s and its Subcontractors’ and subconsultants’ attention is drawn to Sub-Clause 15.8 (Fraud and Corruption) which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility pursuant to the Bank’s prevailing sanctions procedures).” |
| **Sub-Clause 2.4** | **Employer’s Financial Arrangements**The Sub-Clause is replaced with the following:“**2.4 Employer’s Financial Arrangements**The Employer shall submit, before the Commencement Date and thereafter within 28 days after receiving any request from the Contractor, reasonable evidence that financial arrangements have been made and are being maintained which will enable the Employer to pay the Contract Price punctually (as estimated at that time) in accordance with Clause 14 [Contract Price and Payment]. Before the Employer makes any material change to his financial arrangements, the Employer shall give notice to the Contractor with detailed particulars.In addition, if the Bank has notified to the Borrower that the Bank has suspended disbursements under its loan, which finances in whole or in part the execution of the Works, the Employer shall give Notice of such suspension to the Contractor with detailed particulars, including the date of such notification, with a copy to the Employer’s Representative, within 7 days of the Borrower having received the suspension notification from the Bank. If alternative funds will be available in appropriate currencies to the Employer to continue making payments to the Contractor beyond a date 60 days after the date of Bank notification of the suspension, the Employer shall provide reasonable evidence in his Notice of the extent to which such funds will be available.” |
| **Sub-Clause 2.5** | The following Sub-Clause is added:**“ SEA/SH Conference**The Employer shall organize and run a SEA/SH orientation conference as soon as possible after the constitution of the DAB and prior to the commencement of any physical work. The SEA/SH orientation conference shall be attended by the Contractor, its Subcontractors, the Employer’s Representative, the DAB members and all other relevant persons. The objective of the SEA/SH orientation conference shall be to ensure a common understanding of all SEA contractual requirements and remedies, including those available under Sub-Clause 20.12 [*SEA/SH Referrals*], Sub-Clause 20.13 [*Dissatisfaction with DAB’s decision of SEA/SH Referrals*] and Sub-Clause 20.14 [*Bank’s disqualification of the Contractor and its Subcontractor/s].”* |
| **Sub-Clause 3.1** | **Employer’s Representative’s Duties and Authority**“**3.1 Employer’s Representative’s Duties and Authority”**the following shall be added to the end of the third paragraph:“The Employer shall promptly inform the Contractor of any change to the authority attributed to the Employer’s Representative.” Paragraph 3.1(c) is followed by:“and(d) any act by the Employer’s Representative in response to a Contractor’s request except as otherwise expressly specified shall be notified in writing to the Contractor within 28 days of receipt.”The following provisions apply thereafter:“The Employer’s Representative shall obtain the specific approval of the Employer before taking action under the-following Sub-Clauses of these Conditions: (a) Sub-Clause 4.12: agreeing or determining an extension of time and/or additional cost. (b) Sub-Clause 13.1: instructing a Variation, except;(i) in an emergency situation as determined by the Employer’s Representative, or (ii) if such a Variation would increase the Accepted Contract Amount by less than the percentage specified in the Contract Data. (c) Sub-Clause 13.3: Approving a proposal for Variation submitted by the Contractor in accordance with Sub Clause 13.1 or 13.2. (d) Sub-Clause 13.4: Specifying the amount payable in each of the applicable currencies Notwithstanding the obligation, as set out above, to obtain approval, if, in the opinion of the Employer’s Representative, an emergency occurs affecting the safety of life or of the Works or of adjoining property, he may, without relieving the Contractor of any of his duties and responsibility under the Contract, instruct the Contractor to execute all such work or to do all such things as may, in the opinion of the Employer’s Representative, be necessary to abate or reduce the risk. The Contractor shall forthwith comply, despite the absence of approval of the Employer, with any such instruction of the Employer’s Representative. The Employer’s Representative shall determine an addition to the Contract Price, in respect of such instruction, and an adjustment to the Time for Completion of Design-Build if any, in accordance with Clause 13 and shall notify the Contractor accordingly, with a copy to the Employer.” |
| **Sub-Clause 3.3** | **Instructions of the Employer’s Representative** The last sentence in the second paragraph starting: “These instructions shall be given in writing.” is replaced with: “Whenever practicable, their instructions shall be given in writing. If the Employer’s Representative or a delegated assistant:* + 1. gives an oral instruction,
		2. receives a written confirmation of the instruction, from (or on behalf of) the Contractor, within two working days after giving the instruction, and
		3. does not reply by issuing a written rejection and/or instruction within two working days after receiving the confirmation,

then the confirmation shall constitute the written instruction of the Employer’s Representative or delegated assistant (as the case may be).” |
| **Sub- Clause 3.4** | **Replacement of the Employer’s Representative** Replace the sub-clause with the following:“**3.4 Replacement of the Employer’s Representative**If the Employer intends to replace the Employer’s Representative, the Employer shall, not less than 21 days before the intended date of replacement, give notice to the Contractor of the name, address and relevant experience of the intended replacement Employer’s Representative. If the Contractor considers the intended replacement Employer’s representative to be unsuitable, he has the right to raise objection against him by notice to the Employer, with supporting particulars, and the Employer shall give full and fair consideration to this objection.” |
| **Sub- Clause 3.5** | **Determinations**In the second paragraph replace the first sentence with: “The Employer’s Representative shall give notice to both Parties of each agreement or determination, with supporting particulars, within 28 days from the receipt of the corresponding claim or request except when otherwise specified.” |
| **Sub-Clause 4.1** | **Contractor’s General Obligations**At the end of the second paragraph, the following is added: “All equipment, material, and services to be incorporated in or required for the Works shall have their origin in any eligible source country as defined by the Bank.”The following is inserted after the paragraph “The Contractor shall, whenever required by the…”*.*“The Contractor shall not carry out works, including mobilization and/or pre-construction activities (e.g. clearance for haul roads, site accesses and work site establishment, geotechnical investigations or investigations to select ancillary features such as quarries and borrow pits), unless the Employer’s Representative gives consent, a consent that shall not be unreasonably delayed, to the measures the Contractor proposes to manage the environmental and social risks and impacts, which at a minimum shall include applicable Management Strategies and Implementation Plans (MSIPs) and applying the Code of Conduct for Contractor’s Personnel submitted as part of the Proposal and agreed as part of the Contract. The Contractor shall submit, to the Employer’s Representative for its approval, any additional MSIPs as are necessary to manage the ES risks and impacts of ongoing Works (e.g. excavation, earth works, bridge and structure works, stream and road diversions, quarrying or extraction of materials, concrete batching and asphalt manufacture). These MSIPs collectively comprise the Contractor’s Environmental and Social Management Plan (C-ESMP). The C-ESMP shall be part of the Contractor’s Documents. The Contractor shall review the C-ESMP, periodically (but not less than every six (6) months), and update it as required to ensure that it contains measures appropriate to the Works. The updated C-ESMP shall be submitted to the Employer’s Representative for its approval.The following is added at the end of the Sub-Clause: “The Contractor shall provide relevant contract-related information, as the Employer and/or Employer’s Representative may reasonably request to conduct Stakeholder engagements. “Stakeholder” refers to individuals or groups who:* + - 1. are affected or likely to be affected by the Contract; and
			2. may have an interest in the Contract.

The Contractor shall also directly participate in Stakeholder engagements, as the Employer and/or Employer’s Representative may reasonably request.Pursuant to the Contract Data, the Contractor, including its Subcontractors/ suppliers/ manufacturers shall take all technical and organizational measures necessary to protect the information technology systems and data used in connection with the Contract. Without limiting the foregoing, the Contractor, including its Subcontractors/ suppliers/ manufacturers, shall use all reasonable efforts to establish, maintain, implement and comply with, reasonable information technology, information security, cyber security and data protection controls, policies and procedures, including oversight, access controls, encryption, technological and physical safeguards and business continuity/disaster recovery and security plans that are designed to protect against and prevent breach, destruction, loss, unauthorized distribution, use, access, disablement, misappropriation or modification, or other compromise or misuse of or relating to any information technology system or data used in connection with the Contract.” |
| **Sub-Clause 4.2** | **Performance security**Add in the first paragraph second line after “of the Contract” “and if applicable, an Environmental and Social (ES) Performance Security for compliance with the contractor’s ES obligations”.Delete the third paragraph and replace with the following:“The Contractor shall deliver the Performance Security and, if applicable, an ES Performance Security, to the Employer within 28 days after receiving the Letter of Acceptance and shall send a copy to the Employer’s Representative. The Performance Security and, if applicable, ES Performance Security, shall be issued by a reputable bank or financial institution selected by the Contractor. The Performance Security shall be, as stipulated in the Contract Data, and shall be in accordance with the form included in the request for proposals documents for the subject contract or in another form acceptable to the Employer.”In the fourth, sixth [and seventh] paragraphs, references to “Performance Security” shall include references to “ES Performance Security” if applicable.Delete the fifth paragraph and replace with: “The Employer shall not make a claim under the Performance Security or the ES Performance Security, as applicable, except for amounts to which the Employer is entitled under the Contract.”At the end of the sub-clause, add“Without limitation to the provisions of the rest of this Sub-Clause, whenever the Employer’s Representative determines an addition or a reduction to the Contract Price as a result of a change in cost and/or legislation, or as a result of a Variation, amounting to more than 25 percent of the portion of the Contract Price payable in a specific currency, the Contractor shall at the Employer’s Representative 's request promptly increase, or may decrease, as the case may be, the value of the Performance Security in that currency by an equal percentage.”At the end of this Sub Clause 4.2, add:“If specified in the Contract Data the Contractor shall obtain at his cost an Environmental and Social (ES) Performance Security for compliance with the Contractor’s ES obligations during the Design-Build Period in the amounts and currencies set out in the Contract Data.The Contractor shall deliver the ES Performance Security to the Employer within 28 days after receiving the Letter of Acceptance and shall send a copy to the Employer's Representative. The ES Performance Security shall be issued by an entity and from within a country (or other jurisdiction) approved by the Employer and shall be in the form annexed to the Particular Conditions, as stipulated by the Employer in the Contract Data, or in another form approved by the Employer.The Contractor shall ensure that the ES Performance Security is valid and enforceable until the issue of the Commissioning Certificate. If the terms of the Performance Security specify its expiry date, and the Contractor has not become entitled to receive the Commissioning Certificate by the date 28 days prior to the expiry date, the Contractor shall extend the validity of the ES Performance Security until the Contractor has been entitled to receive the Commissioning Certificate. Failure by the Contractor to maintain the validity of the ES Performance Security shall be grounds for termination in accordance with Sub-Clause 15.2 [Termination for Contractor's Default].The Employer shall not make a claim under the ES Performance Security, as applicable, except for amounts to which the Employer is entitled under the Contract.The Employer shall indemnify and hold the Contractor harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from a claim under the Performance Security which the Employer was not entitled to make.The Employer shall return the ES Performance Security to the Contractor within 21 days after receiving a copy of the Contract Commissioning Certificate.In the following General Conditions sub-clauses references to “Performance Security” shall include references to “ES Performance Security, as applicable”:2.1- Right of Access to the Site14.7- Issue of Interim Payment Certificate14.8(a)- Payment14.14- Discharge15.2(a)- Termination15.5- Employer’s Entitlement to Termination 16.4(a)- Payment on termination”. |
| **Sub-Clause 4.3** | **Contractor’s Representative**The following sentence is added at the end of the Sub-Clause: “If the Contractor’s Representative’s delegates are not fluent in the said language, the Contractor shall make competent interpreters available during all working hours in a number deemed sufficient by the Employer’s Representative.” |
| **Sub-Clause 4.4** | **Subcontractors**The following is added before “The Contractor shall be responsible for the acts or…”“The Contractor shall require in all subcontracts relating to the Works that Subcontractors execute the Works in accordance with the Contract, including complying with the relevant ES requirements and the SEA/SH Prevention and Response Obligations.”The following paragraph is added before the paragraph starting: “If any Subcontractor is entitled…”:“The Contractor’s submission, for the Employer’s Representative consent under (b) in the preceding paragraph shall include a Subcontractor’s declaration in accordance with the Particular Conditions- Part E-Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment Performance Declaration for Subcontractors.”The following paragraphs are added at the end of Sub-Clause 4.4:“All subcontracts relating to the Works shall include provisions which entitle the Employer to require the subcontract to be assigned to the Employer under Sub-Clause 15.2. [*Termination for Contractor’s Default*]. All subcontracts for the Design-Build shall also include a provision stipulating that the Subcontractor accepts that the Bank may disqualify the Subcontractor from being awarded a Bank financed contract for a period of two years if the Subcontractor is determined to have failed to comply with its SEA/SH Prevention and Response Obligations.Where practicable, the Contractor shall give fair and reasonable opportunity for contractors from the Country to be appointed as Subcontractors.” |
| **Sub-Clause 4.6** | **Co-operation**The following is added as the second paragraph: “The Contractor shall also, as stated in the Employer’s Requirements or as instructed by the Employer’s Representative, cooperate with and allow appropriate opportunities for the Employer’s Personnel to conduct any environmental and social assessment.”in the second paragraph (now third paragraph): “to suffer delays and/or” is added before “to incur Unforeseeable Cost.” |
| **Sub-Clause 4.8** | The Sub-Clause is replaced with the following: **“Health and Safety Obligations**The contractor shall:1. comply with all applicable health and safety regulations and Laws;
2. comply with all applicable health and safety obligations specified in the Contract;
3. take care for the health and safety of all persons entitled to be on the Site and other places, if any, where the Works are being executed;
4. keep the Site and Works clear of unnecessary obstruction so as to avoid danger to these persons;
5. provide fencing, lighting, safe access, guarding and watching of the Works until the issue of the Contract Completion Certificate;
6. provide any Temporary Works (including roadways, footways, guards and fences) which may be necessary, because of the execution of the Works, for the use and protection of the public and of owners and occupiers of adjacent land;
7. provide health and safety training of Contractor’s Personnel as appropriate and maintain training records;
8. actively engage the Contractor’s Personnel in promoting understanding, and methods for, implementation of health and safety requirements, as well as in providing information to Contractor’s Personnel, and provision of personal protective equipment without expense to the Contractor’s Personnel;
9. put in place workplace processes for Contractor’s Personnel to report work situations that they believe are not safe or healthy, and to remove themselves from a work situation which they have reasonable justification to believe presents an imminent and serious danger to their life or health;
10. Contractor’s Personnel who remove themselves from such work situations shall not be required to return to work until necessary remedial action to correct the situation has been taken. Contractor’s Personnel shall not be retaliated against or otherwise subject to reprisal or negative action for such reporting or removal;
11. subject to Sub-Clause 4.6, collaborate with the entities and Personnel under paragraph (a), (b) and (c) of Sub-Clause 4.6, in applying the health and safety requirements. This is without prejudice to the responsibility of the relevant entities for the health and safety of their own personnel; and
12. establish and implement a system for regular (not less than six-monthly) review of health and safety performance and the working environment.

Subject to Sub-Clause 4.1, the Contractor shall submit to the Employer’s Representative for its approval a health and safety manual which has been specifically prepared for the Works, the Site and other places (if any) where the Contractor intends to execute the Works. The procedures for review of the health and safety manual and its updates shall be as described in Sub-Clause 5.2 *[ Contractor’s Documents]*.The health and safety manual shall set out all the health and safety requirements under the Contract, 1. which shall include at a minimum:
2. the procedures to establish and maintain a safe working environment without risk to health at all workplaces, machinery, equipment and processes under the control of the Contractor, including control measures for chemical, physical and biological substances and agents;
3. details of the training to be provided, records to be kept;
4. the procedures for prevention, preparedness and response activities to be implemented in the case of an emergency event (i.e. an unanticipated incident, arising from both natural and man-made hazards, typically in the form of fire, explosions, leaks or spills, which may occur for a variety of different reasons including failure to implement operating procedures that are designed to prevent their occurrence, extreme weather or lack of early warning);
5. the measures to be taken to avoid or minimize the potential for community exposure to water-borne, water-based, water-related, and vector-borne diseases,
6. the measures to be implemented to avoid or minimize the spread of communicable diseases (including transfer of Sexually Transmitted Diseases or Infections (STDs), such as HIV virus) and non-communicable diseases associated with the execution of the Works, taking into consideration differentiated exposure to and higher sensitivity of vulnerable groups. This includes taking measures to avoid or minimize the transmission of communicable diseases that may be associated with the influx of temporary or permanent Contract-related labour;
7. the policies and procedures on the management and quality of accommodation and welfare facilities if such accommodation and welfare facilities are provided by the Contractor in accordance with Sub-Clause 6.6; and
8. any other requirements stated in the Employer’s Requirements.
9. The paragraph starting with: “In addition to the reporting requirement of…” is deleted and replaced with the addition to GC Sub-Clause 4.21 in Sub-Clause 4.21 of the Special Provisions.
 |
| **Sub-Clause 4.12** | **Unforeseeable Physical Conditions**The last paragraph is replaced with: “The Employer’s Representative shall take account of any evidence of the physical conditions foreseen by the Contractor when submitting the Tender, which shall be made available by the Contractor, but shall not be bound by the Contractor’s interpretation of any such evidence.” |
| **Sub-Clause 4.13** | **Rights of Way and Facilities**The sub-clause is replaced with the following: “Unless otherwise specified in the Contract the Employer shall provide effective access to and possession of the Site including special and/or temporary rights-of-way which are necessary for the Works. The Contractor shall obtain, at his risk and cost, any additional rights of way or facilities outside the Site which he may require for the purposes of the Works.” |
| **Sub-Clause 4.15** | **Access Route**“at Base Date” is added at the end of the first sentence.The following is added at the end of Sub-Clause 4.15: “The Contractor shall take all necessary safety measures to avoid the occurrence of incidents and injuries to any third party associated with the use, if any, of Contractor’s Equipment on public roads or other public infrastructure.The Contractor shall monitor and use road safety incidents and accidents reports to identify negative safety issues, and establish and implement necessary measures to resolve them.” |
| **Sub-Clause 4.18** | **Protection of the Environment**Sub-Clause 4.18 Protection of the Environment is replaced with: “The Contractor shall take all necessary measures to:* + 1. protect the environment (both on and off the Site); and
		2. limit damage and nuisance to people and property resulting from pollution, noise and other results of the Contractor’s operations and/ or activities.

The Contractor shall ensure that emissions, surface discharges, effluent and any other pollutants from the Contractor’s activities shall exceed neither the values indicated in the Employer’s Requirements, nor those prescribed by applicable Laws.In the event of damage to the environment, property and/or nuisance to people, on or off Site as a result of the Contractor’s operations, the Contractor shall agree with the Employer’s Representative the appropriate actions and time scale to remedy, as practicable, the damaged environment to its former condition. The Contractor shall implement such remedies at its cost to the satisfaction of the Employer’s Representative.” |
| **Sub-Clause 4.21** | **Progress Reports**Sub-Clause 4.21 (g) is replaced by the following:“4.21 (g) the Environmental and Social (ES) metrics set out Particular Conditions- Part D;”The following is added at the end of the Sub-Clause:“If stated in the Contract Data, progress reports shall include status of compliance to cyber security risks management, and any foreseeable cyber security risk and mitigation.In addition to the reporting requirement of this sub-paragraph (g) of Sub-Clause 4.21 [*Progress Reports*], and subject to the specific requirement on handling allegations of SEA and/or SH in accordance with Sub-Clause 6.26, the Contractor shall inform the Employer’s Representative immediately of any allegation, incident or accident, which has or is likely to have a significant adverse effect on the environment, the affected communities, the public, Employer’s Personnel or Contractor’s Personnel. This includes, but is not limited to, any incident or accident causing fatality or serious injury; significant adverse effects or damage to private property; any cyber security incidents as specified in the Contract Data; or any allegation of SEA and/or SH. In case of SEA and/or SH, while maintaining confidentiality as appropriate, the type of allegation (sexual exploitation, sexual abuse or sexual harassment), gender and age of the person who experienced the alleged incident should be included in the information.The Contractor, upon becoming aware of the allegation, incident or accident, shall also immediately inform the Employer’s Representative of any such incident or accident on the Subcontractors’ or suppliers’ premises relating to the Works which has or is likely to have a significant adverse effect on the environment, the affected communities, the public, Employer’s Personnel or Contractor’s, its Subcontractors’ and suppliers’ personnel. The notification shall provide sufficient detail regarding such incidents or accidents. The Contractor shall provide full details of such incidents or accidents to the Employer’s Representative within the timeframe agreed with the Employer’s Representative. The Contractor shall require its Subcontractors and suppliers (other than Subcontractors) to immediately notify the Contractor of any incidents or accidents referred to in this Subclause.” |
| **Sub-Clause 4.22** | **Security of the Site**The Sub-Clause is replaced with the following:“The Contractor shall be responsible for the security of the Site, and:1. for keeping unauthorised persons off the Site;
2. authorised persons shall be limited to the Contractor’s Personnel, the Employer’s Personnel, and to any other personnel identified as authorised personnel (including the Employer’s other contractors on the Site), by a Notice from the Employer or the Employer’s Representative to the Contractor.

Subject to Sub-Clause 4.1, the Contractor shall submit for the Employer’s Representative’s No-objection a security management plan that sets out the security arrangements for the Site.The Contractor shall (i) conduct appropriate background checks on any personnel retained to provide security; (ii) train the security personnel adequately (or determine that they are properly trained) in the use of force (and where applicable, firearms), and appropriate conduct towards Contractor’s Personnel, Employer’s Personnel and affected communities; and (iii) require the security personnel to act within the applicable Laws and any requirements set out in the Employer’s Requirements. The Contractor shall not permit any use of force by security personnel in providing security except when used for preventive and defensive purposes in proportion to the nature and extent of the threat.In making security arrangements, the Contractor shall also comply with any additional requirements stated in the Employer’s Requirements.” |
| **Sub-Clause 4.24** | The heading is replaced with: “**Archaeological and Geological Findings”.**The first paragraph is replaced with the following:“All fossils, coins, articles of value or antiquity, structures, groups of structures, and other remains or items of geological, archaeological, paleontological, historical, architectural or religious interest found on the Site shall be placed under the care and custody of the Employer. The Contractor shall:1. take all reasonable precautions, including fencing-off the area or site of the finding, to avoid further disturbance and prevent Contractor’s Personnel or other persons from removing or damaging any of these findings;
2. train relevant Contractor’s Personnel on appropriate actions to be taken in the event of such findings; and
3. implement any other action consistent with the requirements of the Employer’s Requirements and relevant Laws.”
 |
| **Sub-Clause 4.26** | **Demolition**: the following Sub-Clause is added:“The Contractor shall not demolish any building or structure except where specified in the Employer’s Requirements, or with the prior written approval of the Employer’s Representative. The conditions for the re-use, sale and disposal of demolished materials shall be as specified in the Employer Requirements.” |
| **Sub-clause 4.27** | **Existing Facilities**: the following Sub-Clause is added:“The Contractor shall take over, rehabilitate, upgrade, operate and maintain the Existing Facilities to the extent specified in the Employer’s Requirements. Unless stated otherwise in the Employer’s Requirements, the Contractor shall provide, and pay for, all labour, equipment, materials (including spare parts and consumables), and electricity necessary to operate and maintain the Existing Facilities. During the Design-Build Period, (a) the Contractor shall use all reasonable endeavors to meet the standards of performance specified for the Existing Facilities in the Employer’s Requirements;(b) The Employer shall indemnify and hold harmless the Contractor against any and all claims made against it in respect of the operation of the Existing Facilities to the extent that the condition or design of the Existing Facilities renders them unable to meet the applicable performance standards.”As at the date of commencement of the Operation Service the Existing Facility, unless specified otherwise in the Employer’s Requirements, will be deemed to form part of the Works, and all references in the Contract to Works, Permanent Works, Plant and Site etc. shall be deemed to include the Existing Facilities. |
| **Sub-clause 4.28****Suppliers (other than Subcontractors)** | The following Sub-Clauses are added: **4.28.1 Forced Labour** The Contractor shall take measures to require its suppliers (other than Subcontractors) not to employ or engage forced labour including trafficked persons as described in Sub-Clause 6.20. If forced labour/trafficking cases are identified, the Contractor shall take measures to require the suppliers to take appropriate steps to remedy them. Where the supplier does not remedy the situation, the Contractor shall within a reasonable period substitute the supplier with a supplier that is able to manage such risks. **4.28.2 Child labour** The Contractor shall take measures to require its suppliers (other than Subcontractors) not to employ or engage child labour as described in Sub-Clause 6.21. If child labour cases are identified, the Contractor shall take measures to require the suppliers to take appropriate steps to remedy them. Where the supplier does not remedy the situation, the Contractor shall within a reasonable period substitute the supplier with a supplier that is able to manage such risks.**4.28.3 Serious Safety Issues** The Contractor, including its Subcontractors, shall comply with all applicable safety obligations, including as stated in Sub-Clauses 4.4, 4.8 and 6.7. The Contractor shall also take measures to require its suppliers (other than Subcontractors) to adopt procedures and mitigation measures adequate to address safety issues related to their personnel. If serious safety issues are identified, the Contractor shall take measures to require the suppliers to take appropriate steps to remedy them. Where the supplier does not remedy the situation, the Contractor shall within a reasonable period substitute the supplier with a supplier that is able to manage such risks. **4.28.4 Obtaining natural resource materials in relation to supplier**The Contractor shall obtain natural resource materials from suppliers that can demonstrate, through compliance with the applicable verification and/ or certification requirements, that obtaining such materials is not contributing to the risk of significant conversion or significant degradation of natural or critical habitats such as unsustainably harvested wood products, gravel or sand extraction from river beds or beaches.If a supplier cannot continue to demonstrate that obtaining such materials is not contributing to the risk of significant conversion or significant degradation of natural or critical habitats, the Contractor shall within a reasonable period substitute the supplier with a supplier that is able to demonstrate that they are not significantly adversely impacting the habitats. |
| **Sub-clause 4.29** | The following Sub-Clause is added: “**Code of Conduct**The Contractor shall have a Code of Conduct for the Contractor’s Personnel. The Contractor shall take all necessary measures to ensure that each Contractor’s Personnel is made aware of the Code of Conduct including specific behaviors that are prohibited, and understands the consequences of engaging in such prohibited behaviors. These measures include providing instructions and documentation that can be understood by the Contractor’s Personnel and seeking to obtain that person’s signature acknowledging receipt of such instructions and/or documentation, as appropriate.The Contractor shall also ensure that the Code of Conduct is visibly displayed in multiple locations on the Site and any other place where the Works will be carried out, as well as in areas outside the Site accessible to the local community and project affected people. The posted Code of Conduct shall be provided in languages comprehensible to Contractor’s Personnel, Employer’s Personnel and the local community.The Contractor’s Management Strategy and Implementation Plans shall include appropriate processes for the Contractor to verify compliance with these obligations.”  |
| **Sub-Clause 6.1** | **Engagement of Staff and Labour**The following paragraphs are added at the end of the Sub-Clause:“The Contractor shall provide the Contractor’s Personnel information and documentation that are clear and understandable regarding their terms and conditions of employment. The information and documentation shall set out their rights under relevant labour Laws applicable to the Contractor’s Personnel (which will include any applicable collective agreements), including their rights related to hours of work, wages, overtime, compensation and benefits, as well as those arising from any requirements in the Employer’s Requirements. The Contractor’s Personnel shall be informed when any material changes to their terms or conditions of employment occur. The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour with appropriate qualifications and experience from sources within the Country.” |
| **Sub-Clause 6.2** | **Rates of Wages and Conditions of Labour**The following paragraphs are added at the end of the Sub-Clause:“The Contractor shall inform the Contractor’s Personnel about:1. any deduction to their payment and the conditions of such deductions in accordance with the applicable Laws or as stated in the Employer’s Requirements; and
2. their liability to pay personal income taxes in the Country in respect of such of their salaries, wages, allowances and any benefits as are subject to tax under the Laws of the Country for the time being in force.

The Contractor shall perform such duties in regard to such deductions thereof as may be imposed on him by such Laws.Where required by applicable Laws or as stated in the Employer’s Requirements, the Contractor shall provide the Contractor’s Personnel written notice of termination of employment and details of severance payments in a timely manner. The Contractor shall have paid the Contractor’s Personnel (either directly or where appropriate for their benefit) all due wages and entitlements including, as applicable, social security benefits and pension contributions, on or before the end of their engagement/ employment.” |
| **Sub-Clause 6.5** | **Working Hours**The following is inserted at the end of the Sub-Clause:“The Contractor shall provide the Contractor’s Personnel annual holiday and sick, maternity and family leave, as required by applicable Laws or as stated in the Employer’s Requirements.” |
| **Sub-Clause 6.6** | **Facilities for Staff and Labour**The following is added as the last paragraph:“If stated in the Employer’s Requirements, the Contractor shall give access to or provide services that accommodate the physical, social and cultural needs of the Contractor’s Personnel. The Contractor shall also provide similar facilities for the Employer’s Personnel as stated in the Employer’s Requirements.” |
| **Sub-Clause 6.7** | **Health and Safety**In the beginning of the Sub-Clause: “The Contractor shall” is replaced with: In addition to the requirements of Sub-Clause 4.8 [*Health and Safety Obligations*], the Contractor shall” The first sentence of the last paragraph is deleted. |
| **Sub-Clause 6.9** | **Contractor’s personnel**The Sub-Clause is replaced with:““The Contractor’s Personnel (including Key Personnel, if any) shall be appropriately qualified, skilled, experienced and competent in their respective trades or occupations. The Employer’s Representative may require the Contractor to remove (or cause to be removed) any person employed on the Site or Works, including the Contractor’s Representative and Key Personnel (if any), who:1. persists in any misconduct or lack of care;
2. carries out duties incompetently or negligently;
3. fails to comply with any provision of the Contract;
4. persists in any conduct which is prejudicial to safety, health, or the protection of the environment;
5. based on reasonable evidence, is determined to have engaged in Fraud and Corruption during the execution of the Works;
6. has been recruited from the Employer’s Personnel in breach of Sub-Clause 6.3 [*Persons in the Service of the Employer*];
7. undertakes behaviour which breaches the Code of Conduct for Contractor’s Personnel (ES).

If appropriate, the Contractor shall then promptly appoint (or cause to be appointed) a suitable replacement with equivalent skills and experience. Notwithstanding any requirement from the Employer’s Representative to remove or cause to remove any person, the Contractor shall take immediate action as appropriate in response to any violation of (a) through (g) above. Such immediate action shall include removing (or causing to be removed) from the Site or other places where the Works are being carried out, any Contractor’s Personnel who engages in (a), (b), (c), (d), (e) or (g) above or has been recruited as stated in (f) above.In the case of replacement of the Contractor’s Representative, Sub-Clause 4.3 [*Contractor’s Representative*] shall apply. In the case of replacement of Key Personnel (if any), the replacement provision in this Sub-Clause 6.9 shall apply. If the Contractor intends to replace a Key Personnel, the Contractor shall, not less than 30 days before the intended date of replacement, give notice to the Employer’s Representative, the name, address, academic qualifications and relevant experience of the intended replacement Key Personnel. The Contractor shall not, without the prior consent of the Employer’s Representative, revoke the appointment of the Key Personnel or appoint a replacement.” |
| **The following Sub-Clauses 6.12 to 6.27 are added after sub-clause 6.11**  |
| **Sub-Clause 6.12****Foreign Personnel** | The Contractor may bring into the Country any foreign personnel who are necessary for the execution of the Works to the extent allowed by the applicable Laws. The Contractor shall ensure that these personnel are provided with the required residence visas and work permits. The Employer will, if requested by the Contractor, use its best endeavours in a timely and expeditious manner to assist the Contractor in obtaining any local, state, national, or government permission required for bringing in the Contractor’s personnel.The Contractor shall be responsible for the return of these personnel to the place where they were recruited or to their domicile. In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial. |
| **Sub-Clause 6.13****Supply of Foodstuffs** | The Contractor shall arrange for the provision of a sufficient supply of suitable food as may be stated in the Employer’s Requirements at reasonable prices for the Contractor’s Personnel for the purposes of or in connection with the Contract. |
| **Sub-Clause 6.14****Supply of Water** | The Contractor shall, having regard to local conditions, provide on the Site an adequate supply of drinking and other water for the use of the Contractor’s Personnel. |
| **Sub-Clause 6.15****Measures against Insect and Pest Nuisance** | The Contractor shall at all times take the necessary precautions to protect the Contractor’s Personnel employed on the Site from insect and pest nuisance, and to reduce the danger to their health. The Contractor shall comply with all the regulations of the local health authorities, including use of appropriate insecticide. |
| **Sub-Clause 6.16****Alcoholic Liquor or Drugs** | The Contractor shall not, otherwise than in accordance with the Laws of the Country, import, sell, give, barter or otherwise dispose of any alcoholic liquor or drugs, or permit or allow importation, sale, gift, barter or disposal thereto by Contractor’s Personnel. |
| **Sub-Clause 6.17****Arms and Ammunition** | The Contractor shall not give, barter, or otherwise dispose of, to any person, any arms or ammunition of any kind, or allow Contractor’s Personnel to do so. |
| **Sub-Clause 6.18****Festivals and Religious Customs** | The Contractor shall respect the Country’s recognized festivals, days of rest and religious or other customs. |
| **Sub-Clause 6.19****Funeral Arrangements** | The Contractor shall be responsible, to the extent required by local regulations, for making any funeral arrangements for any of its local employees who may die while engaged upon the Works. |
| **Sub-Clause 6.20****Forced Labour** | The Contractor, including its Subcontractors, shall not employ or engage forced labour. Forced labour consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty, and includes any kind of involuntary or compulsory labour, such as indentured labour, bonded labour or similar labour-contracting arrangements. No persons shall be employed or engaged who have been subject to trafficking. Trafficking in persons is defined as the recruitment, transportation, transfer, harbouring or receipt of persons by means of the threat or use of force or other forms of coercion, abduction, fraud, deception, abuse of power, or of a position of vulnerability, or of the giving or receiving of payments or benefits to achieve the consent of a person having control over another person, for the purposes of exploitation. |
| **Sub-Clause 6.21****Child Labour** | The Contractor, including its Subcontractors, shall not employ or engage a child under the age of 14 unless the national law specifies a higher age (the minimum age). The Contractor, including its Subcontractors, shall not employ a child between the minimum age and the age of 18 in a manner that is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development.The Contractor including its Subcontractors, shall only employ children between the minimum age and the age of 18 after an appropriate risk assessment has been conducted by the Contractor with the Employer’s Representative’s consent. The Contractor shall be subject to regular monitoring by the Employer’s Representative that includes monitoring of health, working conditions and hours of work. Work considered hazardous for children is work that, by its nature or the circumstances in which it is carried out, is likely to jeopardize the health, safety, or morals of children. Such work activities prohibited for children include work:1. with exposure to physical, psychological or sexual abuse;
2. underground, underwater, working at heights or in confined spaces;
3. with dangerous machinery, equipment or tools, or involving handling or transport of heavy loads;
4. in unhealthy environments exposing children to hazardous substances, agents, or processes, or to temperatures, noise or vibration damaging to health; or

under difficult conditions such as work for long hours, during the night or in confinement on the premises of the employer. |
| **Sub-Clause 6.22****Employment Records of Workers** | The Contractor shall keep complete and accurate records of the employment of labour at the Site. The records shall include the names, ages, genders, hours worked and wages paid to all workers. These records shall be summarised on a monthly basis and submitted to the Employer’s Representative. These records shall be included in the details to be submitted by the Contractor under Sub-Clause 6.10 [Records of Contractor’s Personnel and Equipment]. |
| **Sub-Clause 6.23****Workers’ Organisations** | In countries where the relevant labour laws recognise workers’ rights to form and to join workers’ organisations of their choosing and to bargain collectively without interference, the Contractor shall comply with such laws. In such circumstances, the role of legally established workers’ organizations and legitimate workers’ representatives will be respected, and they will be provided with information needed for meaningful negotiation in a timely manner. Where the relevant labour laws substantially restrict workers’ organisations, the Contractor shall enable alternative means for the Contractor’s Personnel to express their grievances and protect their rights regarding working conditions and terms of employment. The Contractor shall not seek to influence or control these alternative means. The Contractor shall not discriminate or retaliate against the Contractor’s Personnel who participate, or seek to participate, in such organisations and collective bargaining or alternative mechanisms. Workers’ organisations are expected to fairly represent the workers in the workforce. |
| **Sub-Clause 6.24****Non-Discrimination and Equal Opportunity** | The Contractor shall not make decisions relating to the employment or treatment of Contractor’s Personnel on the basis of personal characteristics unrelated to inherent job requirements. The Contractor shall base the employment of Contractor’s Personnel on the principle of equal opportunity and fair treatment, and shall not discriminate with respect to any aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment, access to training, job assignment, promotion, termination of employment or retirement, and disciplinary practices. Special measures of protection or assistance to remedy past discrimination or selection for a particular job based on the inherent requirements of the job shall not be deemed discrimination. The Contractor shall provide protection and assistance as necessary to ensure nondiscrimination and equal opportunity, including for specific groups such as women, people with disabilities, migrant workers and children (of working age in accordance with Sub-Clause 6.21). |
| **Sub-Clause 6.25****Contractor’s Personnel Grievance Mechanism** | The Contractor shall have a grievance mechanism for Contractor’s Personnel, and where relevant the workers’ organizations stated in Sub-Clause 6.23, to raise workplace concerns (other than those relating to SEA and/or SH, which shall be addressed under Sub-Clause 6.26 below). The grievance mechanism shall be proportionate to the nature, scale, risks and impacts of the Contract. The mechanism shall address concerns promptly, using an understandable and transparent process that provides timely feedback to those concerned in a language they understand, without any retribution, and shall operate in an independent and objective manner. The Contractor’s Personnel shall be informed of the grievance mechanism at the time of engagement for the Contract, and the measures put in place to protect them against any reprisal for its use. Measures will be put in place to make the grievance mechanism easily accessible to all Contractor’s Personnel. The grievance mechanism shall not impede access to other judicial or administrative remedies that might be available, or substitute for grievance mechanisms provided through collective agreements.The grievance mechanism may utilize existing grievance mechanisms, providing that they are properly designed and implemented, address concerns promptly, and are readily accessible to such Contractor’s Personnel. Existing grievance mechanisms may be supplemented as needed with Contract-specific arrangements. |
| **Sub-Clause 6.26** **Contractor’s SEA/SH Response Mechanism; Receipt of SEA/SH allegations; and Contractor’s and non-compliance, during the Design-Build Period**  | * + 1. The Contractor’s SEA/SH Response Mechanism during the Design-Build Period

The Contractor shall put in place an effective mechanism for receiving and promptly addressing allegations of SEA and/or SH from the Contractor’s or Employer’s Personnel or any other person including third parties (“SEA/SH Response Mechanism”). The Contractor’s Personnel shall be informed of the SEA/SH Response Mechanism at the time of engagement for the Contract and informed of the measures put in place to protect them against any reprisal for its use. For all other persons (including the Employer’s Personnel and affected communities), information about this SEA/SH Response Mechanism, including how to submit an allegation or concern and also measures protecting against reprisal, shall be displayed, in languages comprehensible to the Contractor’s Personnel, Employer’s Personnel, and the affected communities, in locations easily accessible to them.The SEA/SH Response Mechanism shall permit allegations or concerns to be submitted in writing, in person or by phone, with appropriate provision for confidential treatment, and shall permit the submission of anonymous allegations. The Contractor shall have in place a dedicated person with appropriate skills, experience and training to receive and review such allegations or concerns. As part of the SEA/SH Response Mechanism, the Contractor shall maintain and implement ethical and safe processes for investigating and addressing allegations of SEA and/or SH. These measures should identify appropriate responses to SEA and/or SH allegations, including the actions set forth in Sub-Clause 6.9, and other appropriate disciplinary measures in the case of the Contractor’s Personnel. * + 1. Receipt of SEA/SH allegations during the Design-Build Period

Any allegation of SEA and/or SH received by the Contractor (including through its Subcontractor/s), the Employer or the Employer’s Representative shall be documented and promptly submitted to the other two parties. While maintaining confidentiality of the person who experienced the alleged incident, as appropriate, the documentation and submission should include the type of alleged incident (sexual exploitation, sexual abuse or sexual harassment), gender and age of the person who experienced the alleged incident.Upon receipt of any SEA and/or SH allegation as described above, the Contractor shall immediately apply its the SEA/SH Response Mechanism, as described in Sub-Clause 6.26.1, to review and address the allegation or concern. The Employer shall promptly refer the allegation to the DAB pursuant to Sub-Clause 20.12 *[“SEA/SH Referral”].* * + 1. Contractor’s non-compliance with SEA/SH contractual obligations during the Design-Build Period

If the Employer’s Representative identifies that the Contractor, including its Subcontractor/s, has not complied with the SEA/SH Prevention and Response Obligations under the Contract, the Employer’s Representative shall give a Notice to Correct to the Contractor in accordance with Sub-Clause 15.1, copied to the Employer and the DAB. If the Contractor fails to comply with the Notice to Correct, the Employer’s Representative shall immediately notify the Employer and the Contractor. Upon receipt of such a notification, the Employer shall refer the non-compliance to the DAB for its review and decision pursuant to Sub-Clause 20.12 *[“SEA/SH Referral”].*If a DAB report, prepared in accordance with Rule 3 of the DAB Procedural Rules, identifies potential non-compliance of the Contractor, including its Subcontractor/s, with the SEA/SH Prevention and Response Obligations, the Employer’s Representative shall review the potential non-compliance and determine whether a Notice to Correct shall be issued to the Contractor. If the Employer’s Representative determines that a Notice to Correct shall not be given to the Contractor, the Employer’s Representative shall inform the Employer copying the DAB, providing the basis for its determination. If the Employer’s Representative, however, determines that a Notice to Correct shall be given to the Contractor, the Employer’s Representative shall give a Notice to Correct to the Contractor in accordance with Sub-Clause 15.1, copied to the Employer and the DAB. If the Contractor fails to comply with the Notice to Correct, the Employer’s Representative shall immediately notify the Employer and the Contractor. Upon receipt of such a notification, the Employer shall refer the non-compliance to the DAB for its review and decision pursuant to Sub-Clause 20.12 *[“SEA/SH Referral”].* |
| **Sub-Clause 6.27****Training of Contractor’s Personnel** | The Contractor shall provide appropriate training to relevant Contractor’s Personnel on ES aspects of the Contract, including appropriate sensitization on prohibition of SEA and health and safety training referred to in Sub-Clause 4.8 As stated in the Employer’s Requirements or as instructed by the Employer’s Representative, the Contractor shall also allow appropriate opportunities for the relevant Contractor’s Personnel to be trained on ES aspects of the Contract by the Employer’s Personnel. The Contractor shall provide training on SEA, including its prevention, to any of its personnel who has a role to supervise other Contractor’s Personnel. |
| **Sub-Clause 7.3 Inspection** | The following is added in the first paragraph after “Employer’s Personnel” “(including the Bank staff or consultants acting on the Bank’s behalf, stakeholders and third parties, such as independent experts, local communities, or non-governmental organizations)”Sub-Clause 7.3 (c) is replaced with: “carry out other duties and inspections, including carrying out environmental and social audit.” |
| **Sub-Clause 7.4** | **Testing**The second paragraph shall start as: “Except as otherwise specified in the Contract, the Contractor shall….”. |
| **Sub-Clause 7.7** | **Ownership of Plant and Materials**The first paragraph shall start as: “Except as otherwise specified in the Contract, ….” Further in each of point (b) and (c), “when the Contractor is entitled to payment of the value” is replaced with “when the Contractor is paid the corresponding value”.The following is added at the end of the sub-clause: “For the avoidance of doubt, vehicles, trucks, mobile plant and site equipment (other than temporary mobile plant and temporary site equipment brought onto the site to undertake specific remedial tasks), tools, office equipment, software and office consumables used by the Contractor for the Operation Service shall become the property of the Employer. Vehicles used for personal transportation of the Contractor’s Personnel and computers and mobile devices allocated for the personal use of the Contractor’s Personnel shall be Contractor’s Equipment. The Contractor shall maintain up-to-date inventories of the Contractor’s Equipment, Materials and Temporary Works throughout the term of the Contract.” |
| **Sub-Clause 8.1** | **Commencement Date**The sub- clause is replaced in its entirety with the following:“**8.1 Commencement Date**Except as otherwise specified in the Contract, the Commencement Date shall be the date at which the following precedent conditions have all been fulfilled and the Employer’s Representative’s notification recording the agreement of both Parties on such fulfilment and instructing to commence the Work is received by the Contractor:(a) signature of the Contract Agreement by both Parties, and if required, approval of the Contract by relevant authorities of the Country;(b) delivery to the Contractor of reasonable evidence of the Employer’s financial arrangements (under Sub-Clause 2.4 [Employer’s Financial Arrangements]);(c) except if otherwise specified in the Contract Data, effective access to and possession of the Site given to the Contractor together with such permission(s) under (a) of Sub-Clause 1.14 [Compliance with Laws] as required for the commencement of the Works;(d) receipt by the Contractor of the Advance Payment under Sub-Clause 14.2 [Advance Payment] provided that the corresponding bank guarantee has been delivered by the Contractor; and(e) constitution of the DAB in accordance with Sub-Clause 20.3 and Sub-Clause 20.4 as applicable.Subject to Sub-Clause 4.1 on the Management Strategies and Implementation Plans and the C-ESMP and Sub-Clause 4.8 on the health and safety manual, the Contractor, shall commence the execution of the Works as soon as is reasonably practicable after the Commencement Date, and shall then proceed with the Works with due expedition and without delay.” |
| **Sub-Clause 9.5** | **Rate of Progress**The following is added as the last paragraph of the sub- clause: “Additional costs of revised methods including acceleration measures, instructed by the Employer’s Representative to reduce delays resulting from causes listed under Sub-Clause 8.4 [Extension of Time for Completion] shall be paid by the Employer, without generating, however, any other additional payment benefit to the Contractor.” |
| **Sub-Clause 9.11** | **Resumption of Work**The following is added at the end of the sub-clause after “suspension”: “after receiving from the Employer’s Representative an instruction to this effect under Clause 13 [Variations and Adjustments].” |
| **Sub-Clause 10.1** | **General Requirements:** The following is added after Operation Management Requirements: “, and Performance Standards.”**Sub-Clause 10.1 General Requirements:** The second paragraph is replaced with the following:“The Contractor shall follow the requirements of the operation and maintenance manuals and any additional Operation Service plans and manuals, prepared by the Contractor in accordance with the Operation Management Requirements. No significant alteration to such arrangements and methods shall be made without the prior approval of the Employer's Representative.” |
| **Sub-Clause 10.2** | **Commencement of Operation Service:** The first paragraph is replaced with the following:“Unless otherwise stated in the Contract Data, the date of commencement of the Operation Service shall be the date seven days following the date of issuance of the Commissioning Certificate issued under Sub-Clause 11.7 [Commissioning Certificate], or such earlier date the Parties may agree to.” |
| **Sub-Clause 10.6** | **Delays and Interruptions during the Operation Service**: Sub-paragraph (a) is replaced with the following “(a) If there are any delays or interruptions during the Operation Service which are caused by the Contractor or by a cause for which the Contractor is responsible, the Contractor, subject to Sub-Clause 3.5 [*Determinations*], shall pay the Employer the performance damages for delay and interruptions specified in the Schedule of Performance Damages. The Employer shall be entitled to recover the amounts due by making corresponding deductions from the payments due to the Contractor. However, the amount of Performance Damages in any contract year of the Operation Service, and the total amount of Performance Damages payable by the Contractor to the Employer, shall not exceed the amounts stated in the Contract Data. There will be no extension of the period of the Operation Service as a result of any such delay or interruption.If a delay or interruption results in a failure to meet Performance Standards and the Contractor is also liable to pay performance damages pursuant to Sub-Clause 10.7, then damages shall not be imposed under both clauses, and the Employer shall determine whether to impose damages under this Sub-Clause 10.6 (a) or under Sub-Clause 10.7.”  |
| **Sub-Clause 10.7** | **Failure to Reach Production Outputs:** replace title with “Failure to Meet Performance Standards” and replace entire sub-clause with the following:“In the event that the Contractor fails to achieve the Performance Standards required under the Contract, the Parties shall jointly establish the cause of such failure. (a) If the failure is due to the Employer or any of his servants or agents, then, after consultation with the Contractor, the Employer shall give written instruction to the Contractor of the measures which the Employer requires the Contractor to take.If the Contractor suffers any additional cost as a result of the failure or the measures instructed by the Employer, the Employer, subject to Sub-Clause 3.5 [*Determinations*] and Sub-Clause 20.1 [*Contractor's Claims*], shall pay the Contractor his Cost Plus Profit.(b) If the failure is due to the Contractor then, after due consultation with the Employer, the Contractor shall at its own expense make any changes, modifications or additions to the Works, to its operating procedures, and to the Contractor’s Personnel, as may be necessary to bring the Works and Operation Service into compliance with the Performance Standards. If the failure relates to a Performance Standard for which damages are specified in the Schedule of Performance Damages, then he Contractor, subject to Sub-Clause 3.5 [*Determinations*], shall pay the Employer the performance damages specified in the Schedule of Performance Damages. The Employer shall be entitled to recover the amount due by making corresponding deductions from the payments due to the Contractor.The amount of compensation payable by the Contractor to the Employer under this sub-clause in any contractyear of the Operation Service Period and total amount of compensation payable by the Contractor under this Sub-Clause 10.7 (*Failures to meet Performance Standards*) shall not exceed the amounts stated in the Contract Data.Unless otherwise stated in the Contract Data, if the failure continues for a period of more than 84 days and the Contractor is unable to achieve the required Performance Standards, the Employer may either:(i) continue with the Operation Service at a reduced level of compensation determined in accordance with Sub-Clause 3.5 [*Determinations*]; or,(ii) give Notice to the Contractor of not less than 56 days of its decision to terminate the Contract, in accordance with Sub-Clause 15.2 [*Termination for Contractor's Default*]. In such an event, the Employer shall be free to continue the Operation Service itself or by others.”  |
| **Sub-Clause 10.9** | **Ownership of Output and Revenue:** Add at the beginning of the paragraph the following:“Unless specified otherwise in the Contract Data,” |
| **Sub-Clause 11.1** | In the fifth paragraph, “Schedule of Guarantees” is replaced with “Schedule of Performance Standards” |
| **Sub-Clause 11.8** | **Joint Inspection Prior to Contract Completion**: Replace the first paragraph with the following:“Not less than two years prior to the expiry date of the Operation Service Period, the Employer's Representative and the Contractor shall carry out a joint inspection of the Works and, within 28 days of the completion of the joint inspection, the Contractor shall submit a report on the condition of the Works, for the Approval of the Employer’s Representative, identifying all remedial works and asset replacements (excluding routine maintenance works) that are necessary a) to satisfy the handback requirement specified in the Employer’s Requirements, and b) to ensure that the Works can be operated in full compliance with the Performance Standards after the Contract Completion Date.” |
| **Sub-Clause 13.1** | **Right to Vary**In the first paragraph, “The variation shall not comprise the omission of any work which is to be carried out by others” is deleted. In the second paragraph, added as (iv): “such Variation triggers a substantial change in the sequence or progress of the Works.”In the second paragraph, “Schedule of Guarantees” is replaced with “Schedule of Performance Standards” |
| **Sub-Clause 13.3** | **Variation procedure**The following is added to the end of Sub-Clause 13.3. (a): “sufficient ES information to enable an evaluation of ES risks and impacts; and sufficient information to enable assessment of cyber security risks as specified in the Contract Data.” |
| **Sub-Clause 13.5** | **Provisional Sums**The following is added at the end of the sub-clause: “The Provisional Sum shall be used to cover the Employer's share of the DAB members’ fees and expenses, in accordance with Clause 20.3. No prior instruction of the Employer’s Representative shall be required with respect to the work of the DAB. The Contractor shall submit the DAB members’ invoices and satisfactory evidence of having paid 100% of such invoices as part of the substantiation of those Statements submitted under Sub-Clause 14.3.” |
| **Sub-Clause 13.6** | **Adjustments for Change in Legislation**The following is added at the end of the sub-clause: “Notwithstanding the foregoing, the Contractor shall not be entitled to an extension of time if the relevant delay has already been taken into account in the determination of a previous extension of time and such Cost shall not be separately paid if the same shall already have been taken into account in the indexing of any inputs to the table of adjustment data in accordance with the provisions of Sub-Clause 13.8 [Adjustments for Changes in Cost].” |
| **Sub-Clause 13.9** | The following Sub-Clause is added**“13.9** **Adjustments for Changes in Influent Quality**: If provided for in the Contract Data, the Contract Price and/or Performance Standards shall be adjusted to take account of the impacts of long term changes in the characteristics of the Influent received at the delivery point to the Works, relative to the Influent Baseline, provided that:1. The changes in Influent characteristics are sustained and permanent;
2. The changes give rise to an increase or decrease in the Contractor’s annual Operation Service costs (excluding any Asset Replacement amounts) of greater than 5 % [*or Employer may insert alternative value*] relative to what the costs would have been had the long term changes in the characteristics of the Influent not occurred.

In such case, either the Employer or the Contractor shall be entitled to initiate an adjustment in the Contract Price and/or Performance Standards. The Contractor shall be entitled to make a claim for an adjustment in the Contract Price in accordance with Sub-Clause 20.1 (Contractor’s Claims), and/or may submit a proposal for an adjustment in the Performance Standards under Sub-Clause 13.2 (Value Engineering). The Employer shall be entitled to vary the Contract Price or Performance Standards by issuing a Variation in accordance with Clause 13 (Variations and Adjustments)Following a successful claim under this Sub-Clause, the Employer’s Representative shall update the Influent Baseline to reflect the long term changes to the characteristics, and the updated Influent Baseline shall be used as the baseline against which to evaluate any further claims for price adjustment under this Sub-Clause.”  |
| **Sub-Clause 14.1** | **The Contract Price****[ *Note to the Employer: include one of the following two alternative texts as applicable*]**The following is added at the end of the Sub-Clause: **[ *Alternative 1*]****“**Notwithstanding the provisions of subparagraph (b), Contractor's Equipment, including essential spare parts therefor, imported by the Contractor for the sole purpose of executing the Contract shall be exempt from the payment of import duties and taxes upon importation.”**[*Alternative 2*]**“Notwithstanding the provisions of subparagraph (b), Contractor's Equipment, including essential spare parts therefore, imported by the Contractor for the sole purpose of executing the Contract shall be temporarily exempt from the payment of import duties and taxes upon initial importation, provided the Contractor shall post with the customs authorities at the port of entry an approved export bond or bank guarantee, valid until the Time for Completion plus six months, in an amount equal to the full import duties and taxes which would be payable on the assessed imported value of such Contractor's Equipment and spare parts, and callable in the event the Contractor's Equipment is not exported from the Country on completion of the Contract. A copy of the bond or bank guarantee endorsed by the customs authorities shall be provided by the Contractor to the Employer upon the importation of individual items of Contractor's Equipment and spare parts. Upon export of individual items of Contractor's Equipment or spare parts, or upon the completion of the Contract, the Contractor shall prepare, for approval by the customs authorities, an assessment of the residual value of the Contractor's Equipment and spare part to be exported, based on the depreciation scale (s) and other criteria used by the customs authorities for such purposes under the provisions of the applicable Laws. Import duties and taxes shall be due and payable to the customs authorities by the Contractor on (a) the difference between the initial imported value and the residual value of the Contractor's Equipment and spare parts to exported; and (b) on the initial imported value of the Contractor's Equipment and spare parts remaining in the Country after completion of the Contract. Upon payment of such dues within 28 days of being invoiced, the bond or bank guarantee shall be reduced or released accordingly; otherwise the security shall be called in the full amount remaining.” |
| **Sub-Clause 14.2** | **Advance payment**The sub-clause is replaced in its entirety by the following:“14.2 **Advance Payment**The Employer shall make an advance payment, as an interest-free loan for mobilization and cash flow support, when the Contractor submits a guarantee in accordance with this Sub-Clause. The total advance payment, the number and timing of instalments (if more than one), and the applicable currencies and proportions, shall be as stated in the Contract Data.Unless and until the Employer receives this guarantee, or if the total advance payment is not stated in the Contract Data, this Sub-Clause shall not apply.The Employer’s Representative shall deliver to the Employer and to the Contractor an Interim Payment Certificate for the advance payment or its first instalment after receiving a Statement (under Sub-Clause 14.3 [Application for Advance and Interim Payment Certificates]) and after the Employer receives (i) the Performance Security in accordance with Sub-Clause 4.2 [Performance Security] and (ii) a guarantee in amounts and currencies equal to the advance payment. This guarantee shall be issued by a reputable bank or financial institution selected by the Contractor and shall be in accordance with the form included in the request for proposals documents for the subject contract or in another form acceptable to the Employer.The Contractor shall ensure that the guarantee is valid and enforceable until the advance payment has been repaid, but its amount shall be progressively reduced by the amount repaid by the Contractor as indicated in the Payment Certificates. If the terms of the guarantee specify its expiry date, and the advance payment has not been repaid by the date 28 days prior to the expiry date, the Contractor shall extend the validity of the guarantee until the advance payment has been repaid.Unless stated otherwise in the Contract Data, the advance payment shall be repaid through percentage deductions from the interim payments determined by the Employer’s Representative in accordance with Sub-Clause 14.7 [Issue of Advance and Interim Payment Certificates], as follows: 1. deductions shall commence in the next interim Payment Certificate following that in which the total of all certified interim payments (excluding the advance payment and deductions and repayments of retention) exceeds 30 percent (30%) of the Accepted Contract Amount for the Design Build less Provisional Sums; and
2. deductions shall be made at the amortization rate stated in the Contract Data of the amount of each Interim Payment Certificate (excluding the advance payment and deductions for its repayments as well as deductions for retention money) in the currencies and proportions of the advance payment until such time as the advance payment has been repaid; provided that the advance payment shall be completely repaid prior to the time when 90 percent (90%) of the Accepted Contract Amount for the Design Build less Provisional Sums has been certified for payment.

If the advance payment has not been repaid prior to the issue of the Commissioning Certificate for the Works or prior to termination under Clause 15 [Termination by Employer], Clause 16 [Suspension and Termination by Contractor] or Clause 18 [Exceptional Risks] (as the case may be), the whole of the balance then outstanding shall immediately become due and in case of termination under Clause 15 [Termination by Employer], except for Sub-Clause 15.5 [Employer’s Entitlement to Termination for Employer’s Convenience], payable by the Contractor to the Employer.” |
| **Sub-Clause 14.3** | **Application for Advance and Interim Payment Certificates** The following is added to the end of the second paragraph: “The Contractor shall prepare separate Statements for the Design-Build and for the Operation Service.” |
| **Sub- Clause 14.7** | **Issue of Advance and Interim Payment Certificates**In the first paragraph, “issue to the Employer” is replaced with “deliver to the Employer and to the Contractor.”The following is added to the third paragraph as (c): 1. if the Contractor was, or is, failing to perform any ES obligations or work under the Contract, the value of this work or obligation, as determined by the Employer’s Representative, may be withheld until the work or obligation has been performed, and/or the cost of rectification or replacement, as determined by the Employer’s Representative, may be withheld until rectification or replacement has been completed. Failure to perform includes, but is not limited to the following:
2. failure to comply with any ES requirements described in the Employer’s Requirements;
3. failure to regularly review C-ESMP and/or update it in a timely manner to address emerging ES issues, or anticipated risks or impacts;
4. failure to implement the C-ESMP e.g. failure to provide required training or sensitization;
5. failing to have appropriate consents/permits prior to undertaking Works or related activities;
6. failure to submit ES report/s (as described in Particular Conditions 4.21), or failure to submit such reports in a timely manner;
7. failure to implement remediation as instructed by the Employer’s Representative within the specified timeframe (e.g. remediation addressing non-compliance/s).

The following is added as penultimate paragraph: “As specified in the Contract Data, if the Contractor fails to perform its cyber security obligations under the Contract, an assessed amount, as determined by the Employer’s Representative, may be withheld until the obligation has been performed.” |
| **Sub-Clause 14.8** | **Payment**(b) and (c) are replaced with the following“(b) the amount certified in each Interim Payment Certificate within 56 days after the Employer’s Representative receives the Statement and supporting documents; or, at a time when the Bank’s loan or credit (from which part of the payments to the Contractor is being made) is suspended, the amount shown on any statement submitted by the Contractor within 14 days after such statement is submitted, any discrepancy being rectified in the next payment to the Contractor; and(c) the amount certified in the Final Payment Certificate within 56 days after the Employer receives this Payment Certificate; or, at a time when the Bank’s loan or credit (from which part of the payments to the Contractor is being made) is suspended, the undisputed amount shown in the Final Statement within 56 days after the date of notification of the suspension in accordance with Sub-Clause 16.2 [Termination by Contractor].” |
| **Sub-Clause 14.9** | **Delayed Payment**In the second paragraph,4th line, after “currency of payment,” the following is inserted: “or, if not available, the interbank offered rate,” |
| **Sub-Clause 14.10** | **Payment of Retention money**The following is added to the end of the Sub-Clause:“Unless otherwise stated in the Contract, when the Commissioning Certificate has been issued for the Works and the first half of the Retention Money has been certified for payment by the Employer’s Representative, the Contractor shall be entitled to substitute a guarantee, in the form annexed to the Particular Conditions or in another form approved by the Employer and issued by a reputable bank or financial institution selected by the Contractor, for the second half of the Retention Money. The Contractor shall ensure that the guarantee is in the amounts and currencies of the second half of the Retention Money and is valid and enforceable until the Contractor has executed and completed the Works and remedied any defects, as specified for the Performance Security in Sub-Clause 4.2. On receipt by the Employer of the required guarantee, the Employer’s representative shall certify and the Employer shall pay the second half of the Retention Money. The release of the second half of the Retention Money against a guarantee shall then be in lieu of the release under the second paragraph of this Sub-Clause. The Employer shall return the guarantee to the Contractor within 21 days after receiving a copy of the performance certificate.” |
| **Sub-Clause 14.12** | **Issue of Final Payment Certificate Design-Build**In the first paragraph, “issue, to the Employer,” is replaced with “deliver, to the Employer and to the Contractor”. Further (a) is replaced with: “the amount which he fairly determines is finally due for the Design Build; and” |
| **Sub-Clause 14.15** | **Issue of Final Payment Certificate Operation Service**In the first paragraph, “issue, to the Employer,” is replaced with “deliver, to the Employer and to the Contractor”. Further (a) is replaced with: “the amount which he fairly determines is finally due for the Operation Service; and; and (b) is replaced with: “the amount which he fairly determines is finally due for the Contract; and” |
| **Sub- Clause 14.17** | **Currencies of Payment** In the first paragraph, “Unless otherwise stated in the Particular Conditions,” is deleted. |
| **Sub-Clause 15.2** | **Termination for Contractor’s Default**The following is added as (h) before “or if any of the Contractor’s Personnel”: “(h) based on reasonable evidence, has engaged in Fraud and Corruption as defined in paragraph 2.2 of the Particular Conditions - Part C- Fraud and Corruption, in competing for or in executing the Contract.” Further in the second paragraph, “or (h)” is added after “or (g)” and paragraph (h) is renumbered (i). |
| **Sub-Clause 15.5** | **Termination for Employer’s Convenience**The last paragraph is replaced with the following: “The Employer shall not terminate the Contract under this Sub-Clause in order to execute or operate the Works (or any part thereof) himself, or arrange for the Works (or any part thereof) to be executed or operated by another contractor, or to avoid a termination of the Contract by the Contractor under Clause 16.2 [Termination by Contractor]” |
| **Sub-Clause 15.8** | **Fraud and Corruption**The following new Sub-Clause is added:“15.8.1 The Bank requires compliance with the Bank’s Anti-Corruption Guidelines and its prevailing sanctions policies and procedures as set forth in the Bank’s Sanctions Framework, as set forth in the Particular Conditions - Part C- Fraud and Corruption.”.15.8.2 The Employer requires the Contractor to disclose any commissions or fees that may have been paid or are to be paid to agents or any other party with respect to the request for proposals process or execution of the Contract. The information disclosed must include at least the name and address of the agent or other party, the amount and currency, and the purpose of the commission, gratuity or fee.” |
| **Sub-Clause 16.1** | **Contractor’s Entitlement to Suspend Work**The following paragraph added after the first paragraph: “Notwithstanding the above, if the Bank has suspended disbursements under the loan or credit from which payments to the Contractor are being made, in whole or in part, for the execution of the Works, and no alternative funds are available as provided for in Sub-Clause 2.4 [Employer’s Financial Arrangements], the Contractor may by Notice suspend work or reduce the rate of work at any time, but not less than 7 days after the Borrower having received the suspension notification from the Bank.” |
| **Sub-Clause 16.2** | **Termination by Contractor**(d) is replaced with: “the Employer substantially fails to perform his obligations under the Contract in such manner as to materially and adversely affect the economic balance of the Contract and/or the ability of the Contractor to perform the Contract,”Further, the “or” is deleted at the end of sub-paragraph (f), and the following is added as a new sub-paragraph (h): “the Contractor does not receive within 180 days after receiving the Letter of Acceptance, for reasons not attributable to the Contractor, the Employer’s Representative’s instruction recording the agreement of both Parties on the fulfilment of the conditions for the Commencement Date under Sub-Clause 8.1 [Commencement Date].The following is added as penultimate paragraph: “In the event the Bank suspends the loan or credit from which part or whole of the payments to the Contractor are being made, if the Contractor has not received the sums due to him upon expiration of the 14 days referred to in Sub-Clause 14.8 [Payment] for payments under Interim Payment Certificates, the Contractor may, without prejudice to the Contractor's entitlement to financing charges under Sub-Clause 14.9 [Delayed Payment], take one of the following actions, namely (i) suspend work or reduce the rate of work under Sub-Clause 16.1, or (ii) terminate the Contract by giving notice to the Employer, with a copy to the Employer’s Representative, such termination to take effect 14 days after the giving of the notice.” |
| **Sub-clause 16.3** | **Cessation of Work and removal of Contractor’s Equipment**In paragraph (b), the following is added after “received payment” “, including those items listed in the Employer’s Requirements”. |
| **Sub-Clause 17.8** | **Limitation of Liability**: The sub-clause is replaced with the following:“Neither Party shall be liable to the other Party for loss of use of any Works, loss of profit, loss of any contract or for any indirect or consequential loss or damage which may be suffered by the other Party in connection with the Contract, other than as specifically provided in Sub-Clause 9.8 [Delay Damages relating to Design Build]; Sub-Clause 10.6 [Delays and Interruption during the Operation Service]; Sub-Clause 10.7 [Failure to Meet Performance Standards]; Sub-Clause 12.2 [Cost of Remedying Defects]; Sub-Clause 15.4 [Payment after Termination for Contractor’s Default]; Sub-Clause 16.4 [Payment on Termination]; Sub-Clause 17.9 [Indemnities by the Contractor]; Sub-Clause 17.10 [Indemnities by the Employer]; Sub-Clause 17.6(b) [Consequences of Employer’s Risks resulting in Damage] and Sub-Clause 17.12 [Risk of Infringement of Intellectual and Industrial Property Rights]. The total liability of the Contractor to the Employer, under or in connection with the Contract other than under Sub-Clause 4.19 [Electricity, Water and Gas], Sub-Clause 4.20 [Employer’s Equipment and Free-Issue Materials], Sub-Clause 17.1 [Indemnities] and Sub-Clause 17.5 [Intellectual and Industrial Property Rights], shall not exceed the sum resulting from the application of a multiplier (less or greater than one) to the Accepted Contract Amount, as stated in the Contract Data, or (if such multiplier or other sum is not so stated) the Accepted Contract Amount.This Sub-Clause shall not limit liability in any case of fraud, deliberate default or reckless misconduct by the defaulting Party.” |
| **Sub-Clause 17.9** | **Indemnities by the Contractor**Sub-paragraph (b) is replaced with: “damage to or loss of any property, real or personal (other than the Works), to the extent that such damage or loss arises out of or in the course of or by reason of the design, the execution and completion or operation and maintenance of the Works, unless and to the extent that any such damage or loss is attributable to any negligence, willful act or breach of the Contract by the Employer, the Employer’s Personnel.” |
| **Sub-Clause 17.13** | **Use of Employer’s Accommodation/Facilities**The following sub-clause added as 17.13:“Sub**-Clause 17.13 - Use of Employer’s Accommodation/ Facilities**The Contractor shall take full responsibility for the care of the Employer provided accommodation and facilities, if any, as detailed in the Employer’s Requirements, from the respective dates of hand-over to the Contractor until cessation of occupation (where hand-over or cessation of occupation may take place after the date stated in the Commissioning Certificate for the Works).If any loss or damage happens to any of the above items while the Contractor is responsible for their care arising from any cause whatsoever other than those for which the Employer is liable, the Contractor shall, at his own cost, rectify the loss or damage to the satisfaction of the Employer’s Representative.” |
| **Sub-Clause 18.1** | **Exceptional Risks**The following added in (b) before “rebellion”: “sabotage by persons other than the Contractor’s Personnel,” Further in (c) and other employees of the Contractor and Subcontractors” is deleted.The following additional paragraphs are added at the end of the Sub-Clause: “(g) upstream pollution of the Influent that prevents the Contractor from providing the Operation Service in accordance with this Agreement.(h) if provided for in the Contract Data, events of high Influent turbidity in which the suspended solids exceed the value specified in the Contract Data and which prevent the Contractor from providing the Operation Service in accordance with this Agreement. [*Only relevant for water treatment - provision to be deleted for wastewater treatment plant* *projects*](i) the wastewater Influent flow exceeds a capacity Performance Standard for the Works and prevents the Contractor from providing the Operation Service in accordance with this Agreement [*provision to be deleted for water treatment plant* *projects*]” |
| **Sub-Clause 18.4** | **Consequences of an Exceptional Event**(b) is replaced with: “if the event or circumstance is of the kind described in sub-paragraphs (i) to (iv) of Sub-Clause 18.1 [Exceptional Risks] and, in sub-paragraphs (b) to (e), and (g) to (i), occurs in the Country, payment of any such Cost, including the costs of rectifying or replacing the Works and/or Goods damaged or destroyed by Exceptional Event, to the extent they are not recovered through the insurance policy referred to in Sub-Clause 19.2 [Insurances to be Provided by the Contractor during the Design-Build Period].” |
| **Sub-Clause 18.56** | **Optional Termination, Payment and Release**In (c), “and necessarily” is inserted after “reasonably”. |
| **Sub-Clause 19.1** | **Insurance General Requirements**After the fourth paragraph the following paragraph is added: “Wherever the Employer is the insuring Party, each insurance shall be effected with insurers and in terms acceptable to the Contractor. These terms shall be consistent with any terms agreed by both Parties before the date of the Letter of Acceptance. This agreement of terms shall take precedence over the provisions of this Clause.” Further the following is added as the final paragraph: “The Contractor shall be entitled to place all insurance relating to the Contract (including, but not limited to the insurance referred to Clause 19) with insurers from any eligible source country.” |
| **Sub-Clause 19.2** | **Insurances to be provided by the Contractor during the Design Build Period**At the beginning of the Sub-Clause, add “unless otherwise stated in the Contract Data,”  |
| **Sub-Clause 19.3** | **Insurances to be provided by the Contractor during the Operation Service Period** At the beginning of the Sub-Clause, add “unless otherwise stated in the Contract Data,”  |
| **Sub-Clause 20.3** | **Appointment of the Dispute Adjudication Board**The following is added at the end of the first paragraph: “The DAB shall also review and decide on any SEA/SH Referral submitted to the DAB pursuant to Sub-Clause 6.26.2 [*Receipt of SEA/SH allegations*] and Sub-Clause 6.26.3 [*Contractor’s non-compliance with SEA/SH contractual obligations*], in accordance with Sub-Clause 20.12 [*SEA/SH Referrals].*In the second paragraph, at the end of the first sentence after deleting: “.”, the following is added: “, each of whom shall meet the criteria set forth in Sub-Clause 3 of Appendix- General Conditions of Dispute Adjudication Agreement.”After the second paragraph, the following paragraph is inserted: “If the Contract is with a foreign Contractor, the DAB members shall not have the same nationality as the Employer or the Contractor.” |
| **Sub-Clause 20.4** | **Failure to Agree Dispute Adjudication Board**In (a): “by the date stated in the first paragraph of Sub-Clause 20.3[*Appointment of the Dispute Adjudication Board*]” is replaced with: “within 42 days from the date the Contract is signed by both Parties”. In (b) and (c): “by such date” refers to “within 42 days from the date the Contract is signed by both Parties”. |
| **Sub- Clause 20.8** | **Arbitration**In the first paragraph, “unless otherwise agreed by both Parties:” is deleted and replaced with: “The Parties agree:”  |
| **The following Sub-Clauses 20.12 to 20.14 are added** |
| **Sub-Clause 20.12 SEA/SH Referrals** | SEA/SH Referrals pursuant to Sub-Clause 6.26 shall be submitted by the Employer to the DAB in writing, copied to the Contractor and the Employer’s Representative. For a DAB of three persons, the SEA/SH Referrals shall be deemed to have been received by the DAB on the date it is received by the chairperson of the DAB. Upon receipt of a SEA/SH Referral, the DAB shall request the Contractor in writing (copied to the Employer and the Employer’s Representative) to submit a statement demonstrating its compliance, including the compliance of any Subcontractor identified in the SEA/SH Referral, with the SEA/SH Prevention and Response Obligations, including the actions taken in response to a SEA/SH allegation and/or any Employer Representative’s Notice to Correct for non-compliance with the SEA/SH contractual obligations. The Contractor shall within 28 days of receipt of this request, submit in writing such statement to the DAB copied to the Employer and the Employer’s Representative. In reviewing the Referral, the DAB shall focus exclusively on compliance of the Contractor, including any Subcontractor identified in the SEA/SH Referral, with the SEA/SH Prevention and Response Obligations, including the actions taken in response to the SEA/SH allegation and/or any Employer Representative’s Notice to Correct for non-compliance with the SEA/SH obligations. The DAB shall not assess the merits of an underlying allegation, including the factual aspects of the alleged SEA and/or SH incident.The DAB decision, which shall state that it is issued under this Sub-Clause 20.12, shall be provided in writing to the Parties with a copy to the Employer’s Representative within 42 days of receiving the SEA/SH Referral. The decision of the DAB taken pursuant to this Sub-Clause 20.12 shall be binding on the Parties and any of its Subcontractor/s as applicable.The DAB decision arising from an allegation of SEA/SH incident shall state whether the Contractor, including any Subcontractor identified in the SEA/SH referral, was in compliance with its SEA/SH obligations at the time of occurrence of the alleged incident. The DAB decision shall not disclose the name of the alleged survivor nor of the alleged perpetrator. |
| **Sub-Clause 20.13****Dissatisfaction with DAB’s decision on SEA/SH Referrals** | If either Party is dissatisfied with the DAB’s decision issued under Sub-Clause 20.12 [SEA/SH Referrals], such Party may give a Notice to the other Party of its dissatisfaction in accordance with Sub-Clause 20.6 [Obtaining Dispute Adjudication Board’s Decision]. Sub-Clause 20.7 *[Amicable Settlement]* shall not apply.If the DAB’s decision has not become final and binding pursuant to Sub-Clause 20.6, the matter shall be finally settled by arbitration in accordance with Sub-Clause 20.8 *[Arbitration].*Where arbitration is conducted pursuant to the ICC Arbitration Rules, the parties agree that the time limit set in Article 1.6 of Appendix V to the ICC Arbitration Rules shall be 10 days from the notification of the Emergency Arbitrator Order unless the President of the ICC International Court of Arbitration determines that a longer period is necessary. |
| **Sub-Clause 20.14****Bank’s disqualification of the Contractor and its Subcontractor/s** | The Employer shall immediately notify the Bank of the DAB’s decision on SEA/SH Referral, any notification received on the commencement of Emergency Arbitration, and the Emergency Arbitrator Order if any. If the DAB determines that the Contractor has failed to correct identified non-compliance with SEA/SH Prevention and Response Obligation or it was non-compliant with such obligations at the time of an alleged incident, the Bank may disqualify the Contractor (where the Contractor is a joint venture or an SPV, every member of the joint venture or an SPV, as applicable), as well as any Subcontractor/s determined to be non-compliant, from being awarded a Bank-financed contract, unless the ICC Emergency Arbitrator grants an order in favor of the Contractor. The disqualification period shall be for two years unless the Contractor receives an arbitration award in its favor within the two year period. The Contractor’s disqualification under this Sub-Clause is without prejudice to the Parties’ rights and obligations under the Contract. |
| **General Conditions of Dispute Adjudication Agreement** |
| **3.Warranties** | The second paragraph starting “When appointing the Member” is replaced with: “When appointing the Member, each Party relies on the Member’s representations, that he/she:1. has at least a bachelor’s degree in relevant disciplines such as law, engineering, construction management or contract management;
2. has at least ten years of experience in contract administration/management and dispute resolution, out of which at least five years of experience as an arbitrator or adjudicator in construction-related disputes;
3. has received formal training as an adjudicator from an internationally recognized organization;
4. has experience and/or is knowledgeable in the type of work which the Contractor is to carry out under the Contract;
5. has experience in the interpretation of construction and/or engineering contract documents;
6. has familiarity with the forms of contract published by FIDIC since 1999, and an understanding of the dispute resolution procedures contained therein; and
7. is fluent in the language for communications stated in the Contract Data (or the language as agreed between the Parties and the DAB).”
 |
| **4.General Obligations of the Member** | “and” is deleted from the end of subparagraph (j) and added at the end of (k).The following is then added as (l):“handle SEA/SH Referrals in accordance with Sub-Clause 20.12 of the Conditions of Contract.” |
| **6.Payments** | From the paragraph starting with: “The Member shall submit invoices for”: “and air fares” and “other” are deleted from the first and second sentences respectively. |
| **Procedural Rules for Dispute Adjudication Board members** |
| Rule 1 | In the first sentence: “ Unless otherwise agreed by the Employer and the Contractor, the DAB shall visit the Site at intervals of not more than 140 days” is replaced with: “Unless otherwise agreed with the Employer and the Contractor, the DAB shall hold face-to face meetings with the Employer and the Contractor, and/or visit the Site at intervals of not more than 90 days during the Design-Build Period and not more than 140 days during the Operation Service Period.”In the second sentence: “ consecutive visits” is replaced with: “ consecutive face-to-face meetings with the Employer and the Contractor and/or Site visits”The following is then added at the end of the paragraph: “ In addition to the face-to face meetings, as agreed with the Employer and the Contractor, the DAB may also hold virtual meetings with the Employer and the Contractor.” |
| Rule 2 | The following is inserted after the first sentence: “The agenda shall include review of the (i) Contractor’s compliance with the SEA/SH Prevention and Response Obligations; and (ii) Employer’s representative’s failure to discharge its duties under the Contract in this regard, including as specified in Sub-Clause 6.26 of the Contract Conditions.” |
| Rule 3 | The following is added at the end of the paragraph: “The report shall identify any issue which raises SEA and/or SH concerns, including details of any potential noncompliance of the Contractor, including its Subcontractor/s, with the SEA/SH Prevention and Response Obligations. The DAB shall also provide a report to the Employer on any potential failure of the Employer’s Representative to discharge its duties in regard to the SEA/SH Prevention and Response Obligations, including on identifying the Contractor’s failure to comply with the obligations, and the Notice to Correct and notification duties in accordance with Sub-Clause 6.26 of the Contract Conditions.” |
| Rule 10 | “and” is deleted from (g) and the following is added: “and (i) appoint one or more experts (including legal and technical expert (s)), with the agreement of the Parties.” “Chairman” is replaced with “Chairperson”. |

**Particular Conditions**

**Part C- Fraud and Corruption**

***(Text in this Particular Conditions - Part C*** ***shall not be modified)***

1. **Purpose**

1.1 The Bank’s Anti-Corruption Guidelines and this annex apply with respect to procurement under Bank Investment Project Financing operations.

2. **Requirements**

2.1 The Bank requires that Borrowers (including beneficiaries of Bank financing); bidders, consultants, contractors and suppliers; any sub-contractors, sub-consultants, service providers or suppliers; any agents (whether declared or not); and any of their personnel, observe the highest standard of ethics during the procurement process, selection and contract execution of Bank-financed contracts, and refrain from Fraud and Corruption.

2.2 To this end, the Bank:

a. Defines, for the purposes of this provision, the terms set forth below as follows:

i. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;

ii. “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation;

iii. “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;

iv. “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;

v. “obstructive practice” is:

(a) deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harass or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or

(b) acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under paragraph 2.2 e. below.

b. Rejects a proposal for award if the Bank determines that the firm or individual recommended for award, any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, suppliers and/ or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

c. In addition to the legal remedies set out in the relevant Legal Agreement, may take other appropriate actions, including declaring misprocurement, if the Bank determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement process, selection and/or execution of the contract in question, without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner at the time they knew of the practices;

d. Pursuant to the Bank’s Anti- Corruption Guidelines and in accordance with the Bank’s prevailing sanctions policies and procedures, may sanction a firm or individual, either indefinitely or for a stated period of time, including by publicly declaring such firm or individual ineligible (i) to be awarded or otherwise benefit from a Bank-financed contract, financially or in any other manner[[15]](#footnote-15); (ii) to be a nominated [[16]](#footnote-16) sub-contractor, consultant, manufacturer or supplier, or service provider of an otherwise eligible firm being awarded a Bank-financed contract; and (iii) to receive the proceeds of any loan made by the Bank or otherwise to participate further in the preparation or implementation of any Bank-financed project;

e. Requires that a clause be included in bidding/request for proposals documents and in contracts financed by a Bank loan, requiring (i) bidders, consultants, contractors, and suppliers, and their sub-contractors, sub-consultants, service providers, suppliers, agents, personnel, permit the Bank to inspect [[17]](#footnote-17) all accounts, records and other documents relating to the submission of bids and contract performance, and to have them audited by auditors appointed by the Bank.

**Particular Conditions**

 **Part D- Environmental and Social (ES)**

**Metrics for Progress Reports**

***[Note to Employer: the following metrics may be amended to reflect the specifics of the Contract. The metrics that are required should be determined by the ES risks and impacts of the Works.]***

*Metrics for regular reporting:*

*environmental incidents or non-compliances with contract requirements, including contamination, pollution or damage to ground or water supplies;*

*health and safety incidents, accidents, injuries that require treatment and all fatalities;*

*interactions with regulators: identify agency, dates, subjects, outcomes (report the negative if none);*

*status of all permits and agreements:*

* + 1. work permits: number required, number received, actions taken for those not received;
		2. status of permits and consents:
	+ list areas/facilities with permits required (quarries, asphalt & batch plants), dates of application, dates issued (actions to follow up if not issued), dates submitted to resident engineer (or equivalent), status of area (waiting for permits, working, abandoned without reclamation, decommissioning plan being implemented, etc.);
	+ list areas with landowner agreements required (borrow and spoil areas, camp sites), dates of agreements, dates submitted to resident engineer (or equivalent);
	+ identify major activities undertaken in each area in the reporting period and highlights of environmental and social protection (land clearing, boundary marking, topsoil salvage, traffic management, decommissioning planning, decommissioning implementation);
	+ for quarries: status of relocation and compensation (completed, or details of activities and current status in the reporting period).

*health and safety supervision:*

1. safety officer: number days worked, number of full inspections & partial inspections, reports to construction/project management;
2. number of workers, work hours, metric of PPE use (percentage of workers with full personal protection equipment (PPE), partial, etc.), worker violations observed (by type of violation, PPE or otherwise), warnings given, repeat warnings given, follow-up actions taken (if any);

*worker accommodations:*

1. number of expats housed in accommodations, number of locals;
2. date of last inspection, and highlights of inspection including status of accommodations’ compliance with national and local law and good practice, including sanitation, space, etc.;
3. actions taken to recommend/require improved conditions, or to improve conditions.

*Health services: provider of health services, information and/or training, location of clinic, number of non-safety disease or illness treatments and diagnoses (no names to be provided);*

*gender (for expats and locals separately): number of female workers, percentage of workforce, gender issues raised and dealt with (cross-reference grievances or other sections as needed);*

*training:*

1. number of new workers, number receiving induction training, dates of induction training;
2. number and dates of toolbox talks, number of workers receiving Occupational Health and Safety (OHS), environmental and social training;
3. number and dates of communicable diseases (including STDs) sensitization and/or training, no. workers receiving training (in the reporting period and in the past); same questions for gender sensitization, flag person training.
4. number and date of SEA and SH prevention sensitization and/or training events, including number of workers receiving training on Code of Conduct for Contractor’s Personnel (in the reporting period and in the past), etc.

*environmental and social supervision:*

1. environmentalist: days worked, areas inspected and numbers of inspections of each (road section, work camp, accommodations, quarries, borrow areas, spoil areas, swamps, forest crossings, etc.), highlights of activities/findings (including violations of environmental and/or social best practices, actions taken), reports to environmental and/or social specialist/construction/site management;
2. sociologist: days worked, number of partial and full site inspections (by area: road section, work camp, accommodations, quarries, borrow areas, spoil areas, clinic, HIV/AIDS center, community centers, etc.), highlights of activities (including violations of environmental and/or social requirements observed, actions taken), reports to environmental and/or social specialist/ construction/ site management; and
3. community liaison person(s): days worked (hours community center open), number of people met, highlights of activities (issues raised, etc.), reports to environmental and/or social specialist /construction/site management.

*Grievances: list new grievances (e.g. allegations of SEA and SH) received in the reporting period and unresolved past grievances by date received, complainant, how received, to whom referred to for action, resolution and date (if completed), data resolution reported to complainant, any required follow-up (Cross-reference other sections as needed):*

1. Worker grievances;
2. Community grievances

*Traffic, road safety and vehicles/equipment:*

1. traffic and road safety incidents and accidents involving project vehicles & equipment: provide date, location, damage, cause, follow-up;
2. traffic and road safety incidents and accidents involving non-project vehicles or property (also reported under immediate metrics): provide date, location, damage, cause, follow-up;
3. overall condition of vehicles/equipment (subjective judgment by environmentalist); non-routine repairs and maintenance needed to improve safety and/or environmental performance (to control smoke, etc.).

*Environmental mitigations and issues (what has been done):*

1. dust: number of working bowsers, number of waterings/day, number of complaints, warnings given by environmentalist, actions taken to resolve; highlights of quarry dust control (covers, sprays, operational status); % of rock/ spoil lorries with covers, actions taken for uncovered vehicles;
2. erosion control: controls implemented by location, status of water crossings, environmentalist inspections and results, actions taken to resolve issues, emergency repairs needed to control erosion/sedimentation;
3. quarries, borrow areas, spoil areas, asphalt plants, batch plants: identify major activities undertaken in the reporting period at each, and highlights of environmental and social protection: land clearing, boundary marking, topsoil salvage, traffic management, decommissioning planning, decommissioning implementation;
4. blasting: number of blasts (and locations), status of implementation of blasting plan (including notices, evacuations, etc.), incidents of off-site damage or complaints (cross-reference other sections as needed);
5. spill clean-ups, if any: material spilled, location, amount, actions taken, material disposal (report all spills that result in water or soil contamination;
6. waste management: types and quantities generated and managed, including amount taken offsite (and by whom) or reused/recycled/disposed on-site;
7. details of tree plantings and other mitigations required undertaken in the reporting period;
8. details of water and swamp protection mitigations required undertaken in the reporting period.

*compliance:*

1. compliance status for conditions of all relevant consents/permits, for the Work, including quarries, etc.): statement of compliance or listing of issues and actions taken (or to be taken) to reach compliance;
2. compliance status of C-ESMP/ESIP requirements: statement of compliance or listing of issues and actions taken (or to be taken) to reach compliance
3. compliance status of SEA and SH prevention and response action plan: statement of compliance or listing of issues and actions taken (or to be taken) to reach compliance
4. compliance status of Health and Safety Management Plan re: statement of compliance or listing of issues and actions taken (or to be taken) to reach compliance
5. other unresolved issues from previous reporting periods related to environmental and social: continued violations, continued failure of equipment, continued lack of vehicle covers, spills not dealt with, continued compensation or blasting issues, etc. Cross-reference other sections as needed

**Particular Conditions**

**Part E- Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment Performance Declaration**

*[The following table shall be filled in by each subcontractor proposed by the Contractor**, that was not named in the Contract]*

 Subcontractor’s Name: *[insert full name]* Date: *[insert day, month, year]* Contract reference *[insert contract reference]* Page *[insert page number]* of *[insert total number]* pages

|  |
| --- |
| **SEA and/or SH Declaration**  |
| We:🞎 (a) have not been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations.🞎 (b) are subject to disqualification by the Bank for non-compliance with SEA/ SH obligations.🞎 (c) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations. An arbitral award on the disqualification case has been made in our favor. 🞎 (d) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations for a period of two years. We have subsequently demonstrated that we have adequate capacity and commitment to comply with SEA /SH obligations. 🞎 (e) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations for a period of two years. We have attached specific evidence demonstrating that we have adequate capacity and commitment to comply with SEA and SH obligations. |
| **[*If (c) above is applicable*, *attach evidence of an arbitral award reversing the findings on the issues underlying the disqualification.]*** |
| ***[If (d) or ( e) above are applicable, provide the following information:]*** |
| Period of disqualification: From: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ To: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| If previously provided on another Bank financed works contract, details of evidence that demonstrated adequate capacity and commitment to comply with SEA/SH obligations (**as per (d) above)**Name of Employer: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Name of Project: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Contract description: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Brief summary of evidence provided: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Contact Information: (Tel, email, name of contact person): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| As an alternative to the evidence under (d), other evidence demonstrating adequate capacity and commitment to comply with SEA/SH obligations (**as per (e) above) )** *[attach details as appropriate].*\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

Name of the Subcontractor

Name of the person duly authorized to sign on behalf of the Subcontractor \_\_\_\_\_\_\_

Title of the person signing on behalf of the Subcontractor \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature of the person named above \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date signed \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_

Countersignature of authorized representative of the Contractor:

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date signed \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_

Section X – Contract Forms

**Table of Forms**

[Notification of Intention to Award 210](#_Toc135387573)

[Beneficial Ownership Disclosure Form 214](#_Toc135387574)

[Letter of Acceptance 216](#_Toc135387575)

[Contract Agreement 217](#_Toc135387576)

[Appendix 1 – Schedule of Payments 219](#_Toc135387577)

[Appendix 2 – Schedule of Cost Indexation 220](#_Toc135387578)

[Appendix 3 - Schedule of Performance Standards 223](#_Toc135387579)

[Appendix 4 - Schedule of Performance Damages 226](#_Toc135387580)

[Performance Security - Option 1: Demand Guarantee 227](#_Toc135387581)

[Performance Security - Option 2: Performance Bond 229](#_Toc135387582)

[Environmental and Social (ES) Performance Security 231](#_Toc135387583)

[Advance Payment Security 233](#_Toc135387584)

[Retention Money Security 235](#_Toc135387585)

Notification of Intention to Award

***[This Notification of Intention to Award shall be sent to each Proposer that submitted a Proposal, unless the Proposer has previously received notice of exclusion from the process at an interim stage of the procurement process.]***

***[Send this Notification to the Proposer’s Authorized Representative named in the Proposer Information Form]***

For the attention of Proposer’s Authorized Representative

Name: *[insert Authorized Representative’s name]*

Address: *[insert Authorized Representative’s Address]*

Telephone/Fax numbers: *[insert Authorized Representative’s telephone/fax numbers]*

Email Address: *[insert Authorized Representative’s email address]*

***[IMPORTANT: insert the date that this Notification is transmitted to all participating Proposers. The Notification must be sent to all Proposers simultaneously. This means on the same date and as close to the same time as possible.]***

**DATE OF TRANSMISSION**: This Notification is sent by: *[email/fax]* on *[date]* (local time)

**Notification of Intention to Award**

**Employer:** *[insert the name of the Employer]*

**Project:***[insert name of project]*

**Contract title:** *[insert the name of the contract]*

**Country:** *[insert country where RFP is issued]*

**Loan No. /Credit No. / Grant No.:** *[insert reference number for loan/credit/grant]*

**RFP No:** *[insert RFP reference number from Procurement Plan]*

This Notification of Intention to Award (Notification) notifies you of our decision to award the above contract. The transmission of this Notification begins the Standstill Period. During the Standstill Period you may:

1. request a debriefing in relation to the evaluation of your Proposal, and/or
2. submit a Procurement-related Complaint in relation to the decision to award the contract.
3. **The successful Proposer**

|  |  |
| --- | --- |
| **Name:** | *[insert name of successful Proposer]* |
| **Address:** | *[insert address of the successful Proposer]* |
| **Contract price:** | *[insert contract price of the successful Proposer]* |
| **Total combined score:** | *[insert the total combined score of the successful Proposer]* |

1. **Other Proposers *[INSTRUCTIONS: insert names of all Proposers that submitted a Proposal , the Proposal prices as read out and evaluated, technical and combined scores]***

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Name of Proposer** | **Technical Score** | **Proposal price** | **Evaluated Proposal Cost****(if applicable)** | **Combined Score** |
| *[insert name]* | *[insert Technical score]* | *[insert Proposal price]* | *[insert evaluated cost]* | *[insert combined score]* |
| *[insert name]* | *[insert Technical score]* | *[insert Proposal price]* | *[insert evaluated cost]* | *[insert combined score]* |
| *[insert name]* | *[insert Technical score]* | *[insert Proposal price]* | *[insert evaluated cost]* | *[insert combined score]* |
| *[insert name]* | *[insert Technical score]* | *[insert Proposal price]* | *[insert evaluated cost]* | *[insert combined score]* |
| *[insert name]* | *[insert Technical score]* | *[insert Proposal price]* | *[insert evaluated cost]* | *[insert combined score]* |

1. **Reason/s why your Proposal was unsuccessful *[Delete if the combined score already reveals the reason]***

|  |
| --- |
| ***[INSTRUCTIONS: State the reason/s why this Proposer’s Proposal was unsuccessful. Do NOT include: (a) a point by point comparison with another Proposer’s Proposal or (b) information that is marked confidential by the Proposer in its Proposal.]*** |

1. **How to request a debriefing**

|  |
| --- |
| **DEADLINE: The deadline to request a debriefing expires at midnight on *[insert date]* (local time).**You may request a debriefing in relation to the results of the evaluation of your Proposal. If you decide to request a debriefing your written request must be made within three (3) Business Days of receipt of this Notification of Intention to Award. Provide the contract name, reference number, name of the Proposer, contact details; and address the request for debriefing as follows:**Attention**: *[insert full name of person, if applicable]***Title/position**: *[insert title/position]***Agency**: *[insert name of Employer]***Email address**: *[insert email address]***Fax number**: *[insert fax number]* ***delete if not used***If your request for a debriefing is received within the 3 Business Days deadline, we will provide the debriefing within five (5) Business Days of receipt of your request. If we are unable to provide the debriefing within this period, the Standstill Period shall be extended by five (5) Business Days after the date that the debriefing is provided. If this happens, we will notify you and confirm the date that the extended Standstill Period will end. The debriefing may be in writing, by phone, video conference call or in person. We shall promptly advise you in writing how the debriefing will take place and confirm the date and time.If the deadline to request a debriefing has expired, you may still request a debriefing. In this case, we will provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of the Contract Award Notice. |

1. **How to make a complaint**

|  |
| --- |
| **DEADLINE: The deadline for submitting a Procurement-related Complaint challenging the decision to award the contract expires on midnight, *[insert date]* (local time).**Provide the contract name, reference number, name of the Proposer, contact details; and address the Procurement-related Complaint as follows:**Attention**: *[insert full name of person, if applicable]***Title/position**: *[insert title/position]***Agency**: *[insert name of Employer]***Email address**: *[insert email address]***Fax number**: *[insert fax number]* ***delete if not used***At this point in the procurement process, you may submit a Procurement-related Complaint challenging the decision to award the contract. You do not need to have requested, or received, a debriefing before making this complaint. Your complaint must be submitted within the Standstill Period and received by us before the Standstill Period ends.Further information:For more information, see the “[Procurement Regulations for IPF Borrowers](https://policies.worldbank.org/sites/ppf3/PPFDocuments/Forms/DispPage.aspx?docid=4005) (Procurement Regulations) (Annex III).” You should read these provisions before preparing and submitting your complaint. In addition, the World Bank’s Guidance “[How to make a Procurement-related Complaint](file:///F%3A%5C2.%20%20World%20Bank%202017%5C17.%20Tools%20and%20Templates%5CNIA%5Cget%20the%20address%20once%20it%20is%20published)” provides a useful explanation of the process, as well as a sample letter of complaint.In summary, there are four essential requirements:1. You must be an ‘interested party’. In this case, that means a Proposer who submitted a Proposal in this procurement, and is the recipient of a Notification of Intention to Award.
2. The complaint can only challenge the decision to award the contract.
3. You must submit the complaint within the deadline stated above.
4. You must include, in your complaint, all of the information required by the Procurement Regulations (as described in Annex III).
 |

1. **Standstill Period**

|  |
| --- |
| **DEADLINE: The Standstill Period is due to end at midnight on *[insert date]* (local time).**The Standstill Period lasts ten (10) Business Days after the date of transmission of this Notification of Intention to Award.The Standstill Period may be extended. This may happen where we are unable to provide a debriefing within the five (5) Business Day deadline. If this happens we will notify you of the extension.  |

If you have any questions regarding this Notification, please do not hesitate to contact us.

On behalf of the Employer:

**Signature:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Name:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Title/position:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Telephone:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Email:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Beneficial Ownership Disclosure Form

*INSTRUCTIONS TO PROPOSERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM*

*This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the successful Proposer. In case of joint venture, the Proposer must submit a separate Form for each member. The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.*

*For the purposes of this Form, a Beneficial Owner of a Proposer is any natural person who ultimately owns or controls the Proposer by meeting one or more of the following conditions:*

* *directly or indirectly holding 25% or more of the shares*
* *directly or indirectly holding 25% or more of the voting rights*
* *directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Proposer*

**RFP No.:** [*insert number of RFP process*]

**Request for Proposal No**.: [*insert identification*]

To: **[*insert complete name of Employer*]**

In response to your request in the Letter of Acceptance *dated [insert date of letter of Acceptance]* to furnish additional information on beneficial ownership: *[select one option as applicable and delete the options that are not applicable]*

(i) we hereby provide the following beneficial ownership information.

**Details of beneficial ownership**

|  |  |  |  |
| --- | --- | --- | --- |
| Identity of Beneficial Owner | Directly or indirectly holding 25% or more of the shares(Yes / No) | Directly or indirectly holding 25 % or more of the Voting Rights(Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Proposer(Yes / No) |
| *[include full name (last, middle, first), nationality, country of residence]* |  |  |  |

***OR***

(ii) *We declare that there is no Beneficial Owner meeting one or more of the following conditions:*

* directly or indirectly holding 25% or more of the shares
* directly or indirectly holding 25% or more of the voting rights
* directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Proposer

**OR**

*(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Proposer shall provide explanation on why it is unable to identify any Beneficial Owner]*

* directly or indirectly holding 25% or more of the shares
* directly or indirectly holding 25% or more of the voting rights
* directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Proposer]”

**Name of the Proposer**: \*[*insert complete name of the Proposer*]\_\_\_\_\_\_\_\_\_

**Name of the person duly authorized to sign the Proposal on behalf of the Proposer**: \*\*[*insert complete name of person duly authorized to sign the Proposal*]\_\_\_\_\_\_\_\_\_\_\_

**Title of the person signing the Proposal**: [*insert complete title of the person signing the Proposal*]\_\_\_\_\_\_

**Signature of the person named above**: [*insert signature of person whose name and capacity are shown above*]\_\_\_\_\_

**Date signed** [*insert date of signing*] **day of** [*insert month*], [*insert year*]\_\_\_\_\_

\* In the case of the Proposal submitted by a Joint Venture specify the name of the Joint Venture as Proposer. In the event that the Proposer is a joint venture, each reference to “Proposer” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

\*\* Person signing the Proposal shall have the power of attorney given by the Proposer. The power of attorney shall be attached with the Proposal Schedules.

Letter of Acceptance

*[letterhead paper of the Employer]*

*[date]*

To: *[name and address of the Contractor]*

This is to notify you that your Proposal dated *[date]* for execution of the *[name of the Contract and identification number, as given in the Contract Data]* for the Accepted Contract Amount *[amount in numbers and words] [name of currency]*, as corrected and modified in accordance with the Instructions to Proposers, is hereby accepted by our Agency.

The amount is made up of the following components:

|  |  |
| --- | --- |
| The Accepted Contract Amount for the Design-Build of: | ………………………………………*(currency and amount in figures)* |
| The Accepted Contract Amount for the Operation Service\* of: | ………………………………………*(currency and amount in figures)* |

*\*Insert value including amounts for asset replacement*

You are requested to furnish (i) the Performance Security and an Environmental and Social Performance Security ***[Delete ES Performance Security if it is not required under the contract]*** within 28 days in accordance with the Conditions of Contract, using for that purpose one of the Performance Security and an Environmental and Social Performance Security Forms ***[Delete ES Performance Security if it is not required under the contract]*** and (ii) the additional information on beneficial ownership in accordance with ITP 53.1, within eight (8) Business days using the Beneficial Ownership Disclosure Form, included in Section X, Contract Forms, of the request for proposals document.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

**Attachment: Contract Agreement**

Contract Agreement

THIS AGREEMENT made the \_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_, between \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter “the Employer”), of the one part, and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ should be designed, executed and operated by the Contractor, and has accepted a Proposal by the Contractor for the design, execution, completion and operation and maintenance of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1. In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2. The following documents shall be deemed to form and be read and construed as part of this Agreement. This Agreement shall prevail over all other Contract documents.

1. the Letter of Acceptance
2. the Letter of Proposal
3. the addenda Nos \_\_\_\_\_\_\_(if any)
4. the Particular Conditions
5. the General Conditions
6. the Employer’s Requirements
7. the completed Schedules,
8. the Operating License and
9. the Contractor’s Proposal and any other documents forming part of the Contract

including, but not limited to:

* + 1. Code of Conduct for Contractor’s Personnel (ES); and
		2. Sexual Exploitation and Abuse (SEA), and/or Sexual Harassment (SH) Declaration.

3. In consideration of the payments to be made by the Employer to the Contractor as specified in this Agreement, the Contractor hereby covenants with the Employer to design, execute, complete, operate and maintain the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract and Operating License.

4. The Employer hereby covenants to pay the Contractor in consideration of the design, execution, completion operation and maintenance of the Works and the remedying of defects therein, the Contract Price, or such other sum as may become payable under the provisions of the Contract, at the times and in the manner prescribed by the Contract and to grant the Contractor (or cause the Contractor to be granted) a royalty-free license to enable him to operate and maintain the Works during the Operation Service Period

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ on the day, month and year specified above.

Signed by \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (for the Employer)

Signed by \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (for the Contractor)

**Appendices to the Contract Agreement:**

Appendix 1: Schedule of Payments

Appendix 2: Schedule of Cost Indexation

Appendix 3: Schedule of Performance Standards

Appendix 4: Schedule of Performance Damages

Appendix 1 – Schedule of Payments

1. **Procedures for payment of the Design-Build**

*[If payment for the Design-Build are to be made in instalments pursuant to GC Sub-Clause 14.4 then the Employer shall include a table of instalments here. If not already stated in the Contract Data, this section should include:*

* *Table of Instalments*
* *Currencies of payment,*
* *Exchange rates,*
* *Payment of taxes and duties,*
* *Procedures for certification of amounts due*
* *Documentation to be provided*
* *]*
1. **Procedures for the payment of the Operation Service (Excluding Asset Replacement)**

*[the Employer shall set out the terms and procedures for payment during the Operation Service Period. Unless already stated in the Contract Data, this section should include:*

* *Frequency of payment (normally Monthly in arrears)*
* *Currencies of payment*
* *Treatment of VAT and other taxes and duties*
* *Formulae and procedures for calculating and validating variable payments*
* *Arrangements for payment of electricity costs (where applicable)*
* *Deductions and adjustments (e.g. for use of standby generation)*
* *Documentation to be provided*
* *]*
1. **Procedures for the payment of assets replaced under the Asset Replacement Fund**

*[insert procedures for payment if different from the contract]*

Appendix 2 – Schedule of Cost Indexation

**1. General requirements**

To the extent, that the Contract Data allows for price adjustment, the amounts payable to the Contractor shall be adjusted for rises or falls in the cost of labour, goods and other inputs to the Works or Operation Service by the addition or deduction of the amounts determined by the formulae prescribed in this Appendix. To the extent that full compensation for any rise or fall in costs is not covered by the provisions of this or other Clauses, the Accepted Contract Amount shall be deemed to have included amounts to cover the contingency of other rises and falls in costs.

The adjustment to be applied to the amount otherwise payable to the Contractor, as valued in accordance with the appropriate Schedule and certified in Payment Certificates, shall be determined from formulae for each of the currencies in which the Contract Price is payable. No adjustment is to be applied to work valued on the basis of Cost or current prices.

**2. Adjustment of Design-Build Prices**

If the contract data allows for price adjustment of design-build amounts, the formulae shall be of the following general type:

**Pn= a + b Ln / Lo + c En/ Eo + d Mn/Mo + ........**

*where:*

 “Pn” is the adjustment multiplier to be applied to the estimated contract value in the relevant currency of the work carried out in period “n”, this period being a month unless otherwise stated in the Appendix to Proposal;

“a” is a fixed coefficient, stated in the relevant table of adjustment data, representing the non-adjustable portion in contractual payments;

“b”, “c”, “d”, ... are coefficients representing the estimated proportion of each cost element related to the execution of the Works as stated in the relevant table of adjustment data; such tabulated cost elements may be indicative of resources such as labour, equipment and materials;

“Ln”, “En”, “Mn”, ... are the current cost indices or reference prices for period “n”, expressed in the relevant currency of payment, each of which is applicable to the relevant tabulated cost element on the date 49 days prior to the last day of the period (to which the particular Payment Certificate relates); and

“Lo”, “Eo”, “Mo”, ... are the base cost indices or reference prices, expressed In the relevant currency of payment, each of which is applicable to the relevant tabulated cost element on the Base Date.

The cost indices or reference prices stated in the table of adjustment data shall be used. If their source is in doubt, it shall be determined by the Employer’s Representative. For this purpose, reference shall be made to the values of the indices at stated dates (quoted in the fourth and fifth columns respectively of the table) for the purposes of clarification of the source; although these dates (and thus these values) may not correspond to the base cost indices.

In cases where the “currency of index” (stated in the table) is not the relevant currency of payment, each index shall be converted into the relevant currency of payment at the selling rate, established by the central bank of the Country, of this relevant currency on the above date for which the index is required to be applicable.

Until such time as each current cost index is available, the Employer’s Representative shall determine a provisional index for the Issue of Interim Payment Certificates. When a current cost index is available, the adjustment shall be recalculated accordingly.

If the Contractor fails to complete the within the Time for Completion, adjustment of prices thereafter shall be made using either (i) each index or price applicable on the date 49 days prior to the expiry of the Time for Completion of the Works, or (ii) the current index or price: whichever is more favourable to the Employer.

**3. Adjustment of Operation Service amounts (excluding Asset Replacement)**

*[In most cases the operation service fees will be paid in local currency and the general type of formula indicated below can be adopted. The formula and associated schedules will require adjustment if the Employer intends to allow payment in foreign currency or allow more than one index per foreign currency. Separate indexation provisions may be required for each component of the operation service fee.]*

If the Contract Data allows for price adjustment of Operation Service amounts, the formulae shall be of the following general type:

**Pn= b Ln/lo + c En/Eo + d Mn/Mo + ......**

**+ w [Rate(Fc1)n/ Rate(Fc1)o] x [ Ind(Fc1)n / Ind(Fc1)o]**

**+ y [Rate(Fc2)n/ Rate(Fc2)o] x [ Ind(Fc2)n / Ind(Fc2)o]**

**+ z ……**

*where:*

“Pn” is the adjustment multiplier to be applied to the local currency amount in period “n”, this period being a month unless otherwise stated in the Appendix to Proposal;

“b”, “c”, “d”, ... are coefficients representing the estimated proportion of each cost element related to **local currency** in the relevant table of adjustment data; such tabulated cost elements may be indicative of resources such as labour, equipment and materials;

“Ln”, “En”, “Mn”, ... are the **local currency** current cost indices or reference prices for period “n”, each of which is applicable to the relevant tabulated cost element on the date 49 days prior to the last day of the period to which the particular Payment Certificate relates;

“Lo”, “Eo”, “Mo”, ... are the **local currency** base cost indices or reference prices, each of which is applicable to the relevant tabulated cost element on the Base Date.

“w”, “y”, “z” ... are coefficients representing the estimated proportion of each cost element related to **foreign currencies** as stated in the relevant table of adjustment data; such tabulated cost elements may be indicative of resources such as labour, equipment and materials;

“Rate(Fc1)n”, “Rate (Fc2)n” are the **foreign currency** exchange rates which are applicable to the relevant tabulated cost element on the date 49 days prior to the last day of the period to which the particular Payment Certificate relates;

“Rate (Fc1)o”, “Rate (Fc2)o” ….. are the **foreign currency** exchange rates on the base date;

“Ind(Fc1)n” “Ind(Fc2)n” …. are the **foreign currency** current cost indices for period “n” on the date 49 days prior to the last day of the period to which the particular Payment Certificate relates;

“Ind(Fc1)o” “Ind(Fc2)o” …… are the **foreign currency** cost indices on the base date.

Exchange rates in the above formulae shall be the selling rate, established by the central bank of the Country of the currency under consideration, on the date for which the index is required to be applicable.

**4. Adjustment of Asset Replacement amounts**

*[In most cases the asset replacement amounts will be paid in local currency. The formula will require adjustment if the Employer intends to allow payment in foreign currency or allow more than one index per foreign currency.]*

If the contract data allows for price adjustment of asset replacement amounts, the formulae shall be of the following general type:

**Pn= q [Ind(LC)n/ Ind(LC)o] + r [Rate(Fc1)n/ Rate(Fc1)o] x [Ind(Fc1)n/Ind(Fc1)o] +**

 **+ s [ etc…….**

*where:*

“Pn” is the adjustment multiplier to be applied to the total (in local currency) indicated in column [d] of the Asset Replacement schedule.

“q”, “r”, “s”, ... are coefficients representing the estimated proportion of each cost element related to different currencies of payment indicated in the Asset Replacement Schedule; such tabulated cost elements may be indicative of resources such as labour, equipment and materials;

Ind(LC)n is the local currency cost index for period “n” on the date 49 days prior to the last day of the period to which the particular Payment Certificate relates;

Ind(LC)o is the local currency cost index on the base date;

Rate(Fc1)n , Rate(Fc1)o, Ind(Fc1)n and Ind(Fc1)o ….etc. have the meanings ascribed above in sub-section 3 of this schedule of adjustment data [adjustment of Operation Service amounts].

Appendix 3 - Schedule of Performance Standards

***Examples:***

**1. Capacity Standard (s)**

|  |  |  |  |
| --- | --- | --- | --- |
| **No** | **Item** | **Unit** | **Minimum Capacity** |
|  |  |  |  |
|  |  |  |  |

Allowable Exclusions (if any):

1. *[list]*

**2. Reliability Standards (unscheduled interruptions/downtime)**

|  |  |  |  |
| --- | --- | --- | --- |
| **No** | **Item** | **Unit** | **Value** |
|  |  |  |  |
|  |  |  |  |

Allowable Exclusions (if any):

1. *[list – e.g. interruptions caused by third parties]*

**3. Water Quality / Effluent Discharge Standards** (delete as applicable)

|  |  |  |  |
| --- | --- | --- | --- |
| **No** | **Parameter** | **Unit** | **Maximum Concentration or Limit** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Allowable Exclusions (if any):

1. *[list – e.g. [x%] failure rate permitted per Month]*

**4. Sludge standards**

|  |  |  |  |
| --- | --- | --- | --- |
| **No** | **Parameter** | **Unit** | **Value / Limit** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Allowable Exclusions (if any):

1. *[list- e.g. up to [ ] percent failure permitted per Month]*

**5. Smell and Noise Standards**

|  |  |  |  |
| --- | --- | --- | --- |
| **No** | **Item** | **Unit** | **Limit** |
|  |  |  |  |
|  |  |  |  |

Allowable Exclusions (if any):

1. *[list]*

**6. Monitoring and testing standards**

|  |  |  |  |
| --- | --- | --- | --- |
| **No** | **Parameter** | **Type of test** | **Frequency of testing** |
|  |  |  |  |
|  |  |  |  |

Allowable exclusions (if any):

1. *[list]*

**7. Energy efficiency standards** (required for short and medium term DBOs)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **No** | **Efficiency item** | **Unit** | **Limit Value (maximum permitted average energy use during evaluation period)** | **Efficiency evaluation period** |
|  | *[consider providing multiple efficiency standards for various conditions – e.g. high/low flow, high/low turbidity etc.]* | *[e.g. KwHr per M3 produced]* |  | *[state whether:** *years of Operation Service Period,*
* *calendar years, or*
* *calendar Months]*
 |

*(required for shorter term DBOs)*

Allowable exclusions (if any):

1. *[list]*

**8. Chemical efficiency standards** (required for short and medium term DBOs)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **No** | **Efficiency item** | **Unit** | **Limit Value(maximum permitted average chemical use during evaluation period)** | **Efficiency evaluation period** |
|  | *[Specify chemical and consider providing multiple efficiency standards for various conditions – e.g. high/low flow, high/low turbidity etc.]* | *[e.g. Kg per M3 produced]* |  | *[state whether:** *years of Operation Service Period,*
* *calendar years, or*
* *Calendar Months]*
 |

*(required for shorter term DBOs)*

Allowable exclusions (if any):

1. *[list]*

Appendix 4 - Schedule of Performance Damages

The Contractor shall pay to the Employer performance damages in accordance with GC Sub-Clauses 10.6 and 10.7 in the amounts specified below.

**Performance Damages for Delay and Interruptions**

|  |  |  |  |
| --- | --- | --- | --- |
| **Ref:** | **Item** | **Unit***[e.g. amount per day, per incident etc.]* | **Insert amount*****[****either as an amount in currency or as percentage of Accepted Contract Amount for Design-Build****]*** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

**Performance Damages for failure to meet Performance Standards**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Ref:** | **Item** | **Unit***[e.g. amount per day, per incident, per cubic meter, etc.]* | **Insert amount*****[****either as an amount in currency or as percentage of Accepted Contract Amount for Design-Build****]*** | **Exclusions****(if any)** |
|  |  |  |  | *[e.g. first failure in Calendar Month]*  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

The performance damages listed above shall be payable in currencies indicated in the Contract Data, or, if no currencies are listed, then the damages shall be payable in the currencies and in the proportions of the Accepted Contract Amount.

The performance damages above shall be in addition to any fines that may be imposed on the Contractor by the courts in respect of pollution of the environment and/or breach of the terms of the applicable permits, licenses or consents.

Performance Security - Option 1: Demand Guarantee

*[Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** *[insert name and Address of Employer]*

**Date:** *[Insert date of issue]*

**PERFORMANCE GUARANTEE No.:** *[Insert guarantee reference number]*

Guarantor**:***[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Applicant”) has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ dated \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ ( ),[[18]](#footnote-18)1 such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its obligation(s) under the Contract, without the Beneficiary needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the …. Day of ……, 2… [[19]](#footnote-19)2, and any demand for payment under it must be received by us at this office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

Performance Security - Option 2: Performance Bond

By this Bond\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ as Principal (hereinafter called “the Contractor”) and\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_] as Surety (hereinafter called “the Surety”), are held and firmly bound unto\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_] as Obligee (hereinafter called “the Employer”) in the amount of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, for the payment of which sum well and truly to be made in the types and proportions of currencies in which the Contract Price is payable, the Contractor and the Surety bind themselves, their heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Contractor has entered into a written Agreement with the Employer dated the day of , 20 , for \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ in accordance with the documents, plans, specifications, and amendments thereto, which to the extent herein provided for, are by reference made part hereof and are hereinafter referred to as the Contract.

NOW, THEREFORE, the Condition of this Obligation is such that, if the Contractor shall promptly and faithfully perform the said Contract (including any amendments thereto), then this obligation shall be null and void; otherwise, it shall remain in full force and effect. Whenever the Contractor shall be, and declared by the Employer to be, in default under the Contract, the Employer having performed the Employer’s obligations thereunder, the Surety may promptly remedy the default, or shall promptly:

(1) complete the Contract in accordance with its terms and conditions; or

(2) obtain a Proposal or Proposals from qualified Proposers for submission to the Employer for completing the Contract in accordance with its terms and conditions, and upon determination by the Employer and the Surety of the lowest responsive Proposer, arrange for a Contract between such Proposer and Employer and make available as work progresses (even though there should be a default or a succession of defaults under the Contract or Contracts of completion arranged under this paragraph) sufficient funds to pay the cost of completion less the Balance of the Contract Price; but not exceeding, including other costs and damages for which the Surety may be liable hereunder, the amount set forth in the first paragraph hereof. The term “Balance of the Contract Price,” as used in this paragraph, shall mean the total amount payable by Employer to Contractor under the Contract, less the amount properly paid by Employer to Contractor; or

(3) pay the Employer the amount required by Employer to complete the Contract in accordance with its terms and conditions up to a total not exceeding the amount of this Bond.

The Surety shall not be liable for a greater sum than the specified penalty of this Bond.

Any suit under this Bond must be instituted prior to the date of the issuing of the Contract Completion Certificate.

No right of action shall accrue on this Bond to or for the use of any person or corporation other than the Employer named herein or the heirs, executors, administrators, successors, and assigns of the Employer.

In testimony whereof, the Contractor has hereunto set his hand and affixed his seal, and the Surety has caused these presents to be sealed with his corporate seal duly attested by the signature of his legal representative, this day of 20 .

SIGNED ON on behalf of

By in the capacity of

In the presence of

SIGNED ON on behalf of

By in the capacity of

In the presence of

Environmental and Social (ES) Performance Security

ES Demand Guarantee

*[Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** *[Insert name and Address of Employer]*

**Date:** *[Insert date of issue]*

**ES PERFORMANCE GUARANTEE No.:** *[Insert guarantee reference number]*

**Guarantor:***[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Applicant”) has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ dated \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ ( ),[[20]](#footnote-20)1 such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its Environmental and/or Social, (ES) obligation(s) under the Contract, without the Beneficiary needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the …. Day of ……, 2… [[21]](#footnote-21)2, and any demand for payment under it must be received by us at this office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

Advance Payment Security

Demand Guarantee

*[Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** *[Insert name and Address of Employer]*

**Date:** *[Insert date of issue]*

**ADVANCE PAYMENT GUARANTEE No.:** *[Insert guarantee reference number]*

**Guarantor:***[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Applicant”) has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ *dated* \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum \_\_\_\_\_\_\_\_\_\_\_ ( )is to be made against an advance payment guarantee.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ ( ) *[[22]](#footnote-22)1* upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating either that the Applicant:

* + 1. has used the advance payment for purposes other than the costs of mobilization in respect of the Works; or
		2. has failed to repay the advance payment in accordance with the Contract conditions, specifying the amount which the Applicant has failed to repay.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the advance payment referred to above has been credited to the Applicant on its account number \_\_\_\_\_\_\_\_\_\_\_ at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_.

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Applicant as specified in copies of interim statements or payment certificates which shall be presented to us. This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that ninety (90) percent of the Accepted Contract Amount for Design Build, less provisional sums, has been certified for payment, or on the \_\_\_ day of \_\_\_\_\_, 2\_\_\_,[[23]](#footnote-23)2 whichever is earlier. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

Retention Money Security

Demand Guarantee

*[Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** *[Insert name and Address of Employer]*

**Date:** *[Insert date of issue]*

**RETENTION MONEY GUARANTEE No.:** *[Insert guarantee reference number]*

**Guarantor:***[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture]* (hereinafter called “the Applicant”) has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert reference number of the contract]* dated \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert name of contract and brief description of Works]* (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, the Beneficiary retains moneys up to the limit set forth in the Contract (“the Retention Money”), and that when the Commissioning Certificate has been issued under the Contract and the first half of the Retention Money has been certified for payment, payment of *[*insert the second half of the Retention Money *or* *if* *the amount guaranteed under the Performance Guarantee when the Commissioning Certificate is issued is less than half of the Retention Money,* the difference between half of the Retention Money and the amount guaranteed under the Performance Security and, if required, the ES Performance Security*]* is to be made against a Retention Money guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ *[insert amount in figures]* ( ) *[amount in words]*[[24]](#footnote-24)1 upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its obligation(s) under the Contract, without your needing to prove or show grounds for your demand or the sum specified therein.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the second half of the Retention Money as referred to above has been credited to the Applicant on its account number \_\_\_\_\_\_\_\_\_\_\_ at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert name and address of Applicant’s bank]*.

This guarantee shall expire no later than the …. Day of ……, 2… [[25]](#footnote-25)2, and any demand for payment under it must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

1. Substitute “contracts” where Proposals are called concurrently for multiple contracts. Add a new para. 3 and renumber paras 3 - 8 as follows: “Proposers may submit Proposal for one or several contracts, as further defined in the RFP Document.” [↑](#footnote-ref-1)
2. Insert if applicable: “This contract will be jointly financed by *[insert name of co-financing agency]*. Procurement process will be governed by the World Bank’s Procurement Regulations.” [↑](#footnote-ref-2)
3. A brief description of the type(s) of Works and Operation Service that should be provided, including location, Design and Build period and Operation Service Period, Functional/performance requirements and other information necessary to enable potential Proposers to decide whether or not to respond to the Request for Proposals. [↑](#footnote-ref-3)
4. If electronic procurement will be used, insert link or web site address and any additional relevant information, as appropriate. [↑](#footnote-ref-4)
5. The office for inquiry and issuance of RFP Document and that for Proposal submission may or may not be the same. [↑](#footnote-ref-5)
6. The fee chargeable should only be nominal to defray reproduction and mailing costs. An amount between US$50 and US$300 or equivalent is deemed appropriate. [↑](#footnote-ref-6)
7. For example, cashier’s check, direct deposit to specified account number, etc. [↑](#footnote-ref-7)
8. The delivery procedure is usually airmail for overseas delivery and surface mail or courier for local delivery. If urgency or security dictates, courier services may be required for overseas delivery. With the agreement of the World Bank, documents may be distributed by e-mail, downloading from authorized web site(s) or electronic procurement system. [↑](#footnote-ref-8)
9. Substitute the address for Proposal submission if it is different from address for inquiry and issuance of RFP Document. [↑](#footnote-ref-9)
10. If the RFP Documents allow for lots or slices that may be procured separately, the amounts of Proposal security have to be defined per lot or slice. The amount of security should not be set so high as to discourage Proposers. If no Proposal security is required, this paragraph should say so. [↑](#footnote-ref-10)
11. An individual firm is considered a domestic Proposer for purposes of the margin of preference if it is registered in the country of the Employer, has more than 50 percent ownership by nationals of the country of the Employer, and if it does not subcontract more than 10 percent of the contract price, excluding provisional sums, to foreign contractors. JVs are considered as domestic Proposer and eligible for domestic preference only if the individual member firms are registered in the country of the Employer or have more than 50 percent ownership by nationals of the country of the Employer, and the JV shall be registered in the country of the Borrower. The JV shall not subcontract more than 10 percent of the contract price, excluding provisional sums, to foreign firms. JVs between foreign and national firms will not be eligible for domestic preference. [↑](#footnote-ref-11)
12. For the avoidance of doubt, a sanctioned party’s ineligibility to be awarded a contract shall include, without limitation, (i) applying for pre-qualification, expressing interest in a consultancy, and bidding, either directly or as a nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider, in respect of such contract, and (ii) entering into an addendum or amendment introducing a material modification to any existing contract. [↑](#footnote-ref-12)
13. A nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider (different names are used depending on the particular bidding document) is one which has been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower. [↑](#footnote-ref-13)
14. Inspections in this context usually are investigative (i.e., forensic) in nature. They involve fact-finding activities undertaken by the Bank or persons appointed by the Bank to address specific matters related to investigations/audits, such as evaluating the veracity of an allegation of possible Fraud and Corruption, through the appropriate mechanisms. Such activity includes but is not limited to: accessing and examining a firm's or individual's financial records and information, and making copies thereof as relevant; accessing and examining any other documents, data and information (whether in hard copy or electronic format) deemed relevant for the investigation/audit, and making copies thereof as relevant; interviewing staff and other relevant individuals; performing physical inspections and site visits; and obtaining third party verification of information. [↑](#footnote-ref-14)
15. For the avoidance of doubt, a sanctioned party’s ineligibility to be awarded a contract shall include, without limitation, (i) applying for pre-qualification, expressing interest in a consultancy, and bidding, either directly or as a nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider, in respect of such contract, and (ii) entering into an addendum or amendment introducing a material modification to any existing contract. [↑](#footnote-ref-15)
16. A nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider (different names are used depending on the particular bidding document) is one which has been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower. [↑](#footnote-ref-16)
17. Inspections in this context usually are investigative (i.e., forensic) in nature. They involve fact-finding activities undertaken by the Bank or persons appointed by the Bank to address specific matters related to investigations/audits, such as evaluating the veracity of an allegation of possible Fraud and Corruption, through the appropriate mechanisms. Such activity includes but is not limited to: accessing and examining a firm's or individual's financial records and information, and making copies thereof as relevant; accessing and examining any other documents, data and information (whether in hard copy or electronic format) deemed relevant for the investigation/audit, and making copies thereof as relevant; interviewing staff and other relevant individuals; performing physical inspections and site visits; and obtaining third party verification of information. [↑](#footnote-ref-17)
18. 1 The Guarantor shall insert an amount representing the percentage of the Accepted Contract Amount specified in the Letter of Acceptance, less provisional sums, if any, and denominated either in the currency (cies) of the Contract or a freely convertible currency acceptable to the Beneficiary. [↑](#footnote-ref-18)
19. 2 Insert the date twenty-eight days after the expected completion date as described in GC Clause 8.6. The Employer should note that in the event of an extension of this date for completion of the Contract, the Contractor would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months] [one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.” [↑](#footnote-ref-19)
20. 1 The Guarantor shall insert an amount representing the percentage of the Accepted Contract Amount specified in the Letter of Acceptance, less provisional sums, if any, and denominated either in the currency (cies) of the Contract or a freely convertible currency acceptable to the Beneficiary. [↑](#footnote-ref-20)
21. 2 Insert the date twenty-eight days after the expected completion date of design-build as described in GC Clause 9.12. The Employer should note that in the event of an extension of this date for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months] [one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.” [↑](#footnote-ref-21)
22. 1 The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency (ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer. [↑](#footnote-ref-22)
23. 2 Insert the expected Time for Completion of Design Build. The Employer should note that in the event of an extension of the time for completion of design build, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months] [one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.” [↑](#footnote-ref-23)
24. 1 The Guarantor shall insert an amount representing the amount of the second half of the Retention Money or if the amount guaranteed under the Performance Guarantee when the Commissioning Certificate is issued is less than half of the Retention Money, the difference between half of the Retention Money and the amount guaranteed under the Performance Security and denominated either in the currency(ies) of the second half of the Retention Money as specified in the Contract, or in a freely convertible currency acceptable to the Beneficiary. [↑](#footnote-ref-24)
25. 2 Insert the date twenty-eight days after the Retention Period described in GC Clause 1.1.66. The Employer should note that in the event of an extension of this date for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months] [one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.” [↑](#footnote-ref-25)