## Slide 1
3rd Meeting of the ICP
Governing Board
October 25, 2018
Dubai, UAE

## Slide 2: Welcome Address
UAE Federal Competitiveness
And Statistics Authority

## Slide 3: Opening Remarks and Adoption of the Agenda
Meeting Chair

## Slide 4: Introducing the Governing Board Co-Chair
Mr. Pravin Srivastava
  Chief Statistician of India
  Secretary of the Ministry of Statistics and Programme Implementation, Government of India

## Slide 5: Meeting Agenda
Welcome address
Opening remarks and adoption of the agenda
Overall progress in the implementation of ICP 2017 cycle
Regional progress reports
Outstanding risks and mitigation measures
Beyond the ICP 2017 cycle: Preparations for the ICP 2020 cycle
Date and venue of the next meeting and any other business
Closing remarks

## Slide 6: Overall Progress in the Implementation of ICP 2017 Cycle
Global ICP Unit, World Bank

## Slide 7: Progress Summary (1)
  175 countries participating
  Argentina, Iran, Georgia, Ukraine and 22 Caribbean islands
Country Participation
  Household consumption data from 165/175 countries
  Gross capital formation data from 130/175 countries
Data Submission
  Regional data validation underway in all regions
  Global data validation launched in September 2018
  Quality of input price data promising
Quality

## Slide 8: Progress Summary (2)
  GB/TAG/IACG convening per work plan
  GB Co-Chairs letter to all countries in May 2018 to support the ICP 2017 cycle
  Permanent Global ICP Unit at the WB
Governance
  Increase in capacity-building workshops and technical assistance in all regions
  Global ICP Unit providing specialized technical support, where needed
Capacity Building
  4 Task Forces/Teams working on 6/13 research agenda items
  TAG examined 3 technical proposals and recommended additional work
Research Agenda

## Slide 9: Progress Summary (3)
  eLearning course released – good uptake
  ICP Blog series launched
Knowledge
  Increased visibility – 50th anniversary events
  Newsletter – wider distribution
  Comprehensive website
Outreach
  WB Dynamic Quota Formula
  Indicators for 5/17 SDG goals
  Use in competitiveness, climate, energy, productivity, etc.
Uses

## Slide 10: Progress Summary (4)
  Streamlined data sharing among IACG
  IACG criteria for extending the ICP publication level beyond ICP 2011, where appropriate
Openness
  IACG tentative plan for the 2020 cycle
2020 Cycle Preparations
  New contribution from AFESD
  Contribution from the WB capital budget
  Initial discussions with the IADB
Funding

## Slide 11: ICP 2017 Cycle Outputs
2017 Results
Revised 2011 Results
Interpolate between 2011 and 2017 results
Incorporate interim regional results
Global PPP Time Series for 2011-2017

## Slide 12
Region | Interim [Years] | 2017 Cycle
Africa | 47 [2015-16] 1 | 50
Asia | 20 [2016] | 22
CIS | 8 [2014] | 8
LAC | - | 35 4
Western Asia | 12 [2012-16] | 12
Eurostat-OECD | 47 [Annual] | 49 5
Special participation 2 | - | 3
Dual participation 3 | (4) | (4)
Total | 130 | 175
Participating Countries
1 Household consumption only
2 Iran [linked through Western Asia], and Georgia and Ukraine [linked through Eurostat]
3 Includes Egypt, Morocco, Russia and Sudan
4 Does not include Guatemala and Sint Maarten, whose participation status is still unclear
5 Includes Costa Rica and Colombia in the OECD comparison

## Slide 13: ICP 2017 Timetable (1)
Activity | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  | 
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Governance Meetings and Reports |  |  |  |  |  |  |  |  |  |  |  | 
GB meetings |  |  | Sep |  |  |  |  | Oct | Mar |  |  | Oct
IACG meetings | Mar |  |  | Oct | Mar |  | Sep |  |  | Apr | Sep | 
TAG meetings |  | May |  |  |  | May |  |  |  | May |  | Oct
TF01-03 meetings |  |  |  | Oct | Mar |  | Sep |  |  | May |  | Oct
TF04-05 meetings |  |  |  |  |  |  |  |  |  | Jun |  | 
TT DQ meetings |  |  |  |  |  | Jun | Sep |  | Feb |  | Sep | 
Reports to UNSC |  |  |  | Nov |  |  |  | Nov |  |  |  | Nov
Acronyms: Governing Board (GB), Inter-Agency Coordination Group (IACG), Technical Advisory Group (TAG), Task Force (TF), Task Team on Data Quality (TT DQ), United Nations Statistical Commission (UNSC)

## Slide 14: ICP 2017 Timetable (2)
Regions | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  | 
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Price surveys |  |  |  |  |  |  |  |  |  |  |  | 
Western Asia | H | H | H | H |  | H+R +G | C | H+R +M |  | R |  | 
Eurostat-OECD |  | H |  | H |  | H+R | M+C | H+G |  | H+R |  | H
Asia |  |  |  |  |  | H | H | H+M | H+M+C | H+R+M+C | H+R+G | G
CIS |  |  |  |  |  | H | H+M +C | H+M +C |  |  |  | R+G
Africa |  |  |  |  |  |  | H | H | H | H | H+R+M+C | H+R+G+M+C
LAC |  |  |  |  |  |  | H | H | H | H | H+R+G+M+C | H+R+G+M+C
Acronyms: Household consumption (H), Housing (R), Government (G), Machinery and Equipment (M), Construction (C)

## Slide 15: ICP 2017 Timetable (3)
Activity | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  | 
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
National account expenditures |  |  |  |  |  |  |  |  |  |  |  | 
GDP Expenditures |  |  |  |  |  |  |  |  |  |  |  | 
Data submission and validation |  |  |  |  |  |  |  |  |  |  |  | 
Data & Metadata to GIU |  |  |  |  |  |  | Jul |  | Jan |  | Jul | 
Global validation |  |  |  |  |  |  |  |  |  |  |  | 
Results and publication |  |  |  |  |  |  |  |  |  |  |  | 
Regional 2017 results |  |  |  |  |  |  |  |  |  |  |  | FR+P
Global 2017 results |  |  |  |  |  |  |  |  |  |  |  | FR+P
PPP time series (2011-2017) |  |  |  |  |  |  |  |  |  |  |  | FR+P
Acronyms: Global ICP Unit (GIU), Final Results (FR), Publication (P)

## Slide 16
ICP 2017 Data Submission Status
Region | Years | HHC | HOU 1 | GOV | GFCF | EXP | POP/ XR
AFR [50] | 2017-18 | 40 2 | 10 |  | 48 (M) 50 (C) |  | 
ASI [22] | 2017-18 | 22 |  |  | 22 |  | 22/22
CIS [8] | 2017 | 8 |  |  |  |  | 8/8
LAC [35] 3 | 2017-18 | 35 |  |  |  |  | 35/35
WAS [12] | 2017 | 12 | 11 | 11 | 12 |  | 10/10
EUO [49] | 2017 | 47 4 |  |  | 49 (M) |  | 49/49
SP [3] 5 | 2017 | 1 | 1 | 1 | 1 |  | 
1 Housing rentals, not covering housing volume
2 Does not include Angola, Burkina Faso, Cape Verde, Equatorial Guinea, Gabon, Ghana, Guinea, Liberia, Madagascar and Nigeria
3 Does not include Guatemala and Sint Maarten
4 Does not include Colombia and Costa Rica (OECD)
5 Special Participation: Iran, Georgia and Ukraine

## Slide 17: Capacity-Building Activities
ICP Region | Regional/ Sub-Regional Workshops | Country Workshops/ TA Missions | Forthcoming Activities
Africa | 4 | 6 | Q1/Q2 2019 – RW
Asia | 5 | 1 | Dec 2018 – RW
CIS | 2 | 1 | Dec 2018 – RW Apr 2019 – RW
LAC | 2 | 2 | Dec 2018 – RW
Western Asia | 5 | 2 | Q4 2018 – RW Q4 2018 – SRW Q4 2018 – Libya
Eurostat-OECD | 4 |  | 
SP* |  | 7 | May 2019 – Iran
* Special Participation: Iran, Georgia and Ukraine

## Slide 18
Governance Activities
Meetings Conducted (2018)
  IACG Principles Meeting, NY, Mar 2018
  5th IACG & 2nd Task Forces Meetings, DC, Mar 2018
  Prep Meeting for the Poverty and PPPs Task Force, DC, May 2018
  2nd TAG Meeting, DC, May 2018
  1st Task Team on Data Quality Meeting, DC, Jun 2018
  6th IACG, 3rd Task Forces, & 2nd Task Team Meetings, DC, Sept 2018
  3rd GB Meeting, Dubai, Oct 2018
Upcoming Meetings (2019)
  3rd Task Team Meeting, DC, Feb 2019
  4th GB Meeting & ICP Session at the 50th UNSC, NY, Mar 2019
  7th IACG Meeting, DC, Apr 2019
  3rd TAG & 4th Task Forces Meetings, Paris, May 2019
  8th IACG & 4th Task Team Meetings, DC, Sept 2019
  4th TAG & 5th Task Forces Meetings, DC, Oct 2019
  5th GB Meeting, DC, Oct 2019

## Slide 19
Progress Reports
Governance Reporting
  Report to the 50th UNSC session - for discussion
  Deadline: Nov 2018
Donor Reporting
  Report to Donors
  Deadline: Mar 2019

## Slide 20
Research Agenda Activities (1)
TF_01 PPP Compilation and Computation (Ongoing) | 
Linking interim regional updates into a global comparison | Proposal to incorporate interim regional results into global PPP time series underway
Building PPP time series for the interim period | Proposal to interpolate between 2011 and 2017 underway
Fine tuning global linking procedures | 
Productivity adjustment for government and construction labor | Proposal to improve data sources underway
TF_02 Housing (Ongoing) | 
PPPs and real expenditures for dwelling services | Proposal to improve data sources underway

## Slide 21
Research Agenda Activities (2)
TF_03 Country Operational Guidelines and Procedures (Ongoing) | 
Moving towards rolling price surveys | Guidelines underway
CPI-ICP synergies to improve spatial and temporal price consistency | Guidelines underway
Sub-national PPPs | Guidelines underway
TF_04 PPP Uses (upcoming) | 
Uses of PPPs and ICP data for policy making | Background research conducted
TF_05 PPPs and Poverty (upcoming) | 
ICP PPPs and global poverty measurement | Prep meeting with the WB’s global poverty measurement team

## Slide 22
Research Agenda Activities (3)
TF_06 PPP Quality and Reliability | 
Quality of data and results | Task Team on Data Quality; TAG to review quality of results
Reliability measures for PPPs | 
TF_07 New Data Sources | 
Exploring innovations in technology and data sources | Background research conducted
TF_08 Exports and Imports | 
PPPs for exports and imports | 
TF_09 Non-Market Services | 
PPPs for health and education | 
TF_10 Construction | 
PPPs for construction | 

## Slide 23: Publication Objective
Objective
increase the ICP value proposition
Data derived from the ICP should be utilized to the maximum extent possible for statistical, research, and analytical purposes
Extend publication level beyond what was published through ICP 2005 and 2011
ICP 2005 and ICP 2011: 24/26 headings covering main aggregates and categories, and additional aggregates (e.g. actual individual consumption, domestic absorption)
Eurostat, OECD and CIS currently publish their results at a finer level of detail, covering 61, 50 and 50 headings, respectively
ICP should follow suit and extend the publication of its results to more detailed levels, where appropriate

## Slide 24: Publication Criteria
The proposed criteria for extending the publication of ICP results comprises three data quality and reliability elements
#01
Assessment of the quality and reliability of the expenditure data for the aggregates to publish
#02
Assessment of the quality and reliability of the PPPs for the aggregates to publish
#03
Assessment of potential differences in approaches/ classifications across regions that could impact the aggregates to publish

## Slide 25
Dissemination Plans
2011 PPP results available through…
World Bank DataBank
World Development Indicators
Capitalize on new dissemination tools…
Country and topic-specific profiles
Visual analyses
Dashboards and portals
ICP website
ICP Reports

## Slide 26
Knowledge Activities
Launched in March 2018
Around 300 trainees enrolled online
Used as well in regional and national workshops
PPP eLearning
ICP Blog series
ICP branded, within World Bank Data Blog series
Wide audience through social media
Invites authors: research, methodology, uses etc.

## Slide 27
Outreach Activities
Quarterly newsletter
1,500 recipients worldwide
National, regional and global activities
PPP uses
ICP Highlights
50th Anniversary
Events at the United Nations and the World Bank
Posters, video and blogs
Wide audience on social media - #ICP50th

## Slide 28
International Conferences
ICP at the World Bank Booth at the UN World Data Forum, Dubai, Oct 2018
Conference “Fifty Years of International Comparison Program: Achievements and Moving Forward”, Beijing, Oct 2018
Intra-country comparisons of poverty and living conditions: Measuring well-being at local level for public policy with focus on China, Beijing, Dec 2018
International Comparisons Conference, Groningen, May 2019
Session on PPP/CPI Synergies at the Ottawa Group meeting, Rio de Janeiro, May 2019
Session on PPP-based comparisons at the IARIW special conference, Moscow, Sept 2019

## Slide 29
A month of PPPs - 500+ articles via Factiva
India, China and the USA dominate coverage ..but 80 other countries are featured
70 major media news outlets ran 115 PPP articles

## Slide 30
PPPs feature in…
….blogs
….research papers
…media articles
….development reports
…. analyses

## Slide 31
PPPs inform development by…
..comparing growth rates of electrical and electronic equipment
..calculating poverty rates and spending on social safety nets
…measuring productivity by comparing GDP per capita (PPP) with nighttime lights data
…estimating the impact on GDP per capita (PPP) of dire climate scenarios
….valuing unpaid care work as a share of GDP (PPP)
…analyzing FDI inflows, migration and travel patterns into ECA.

## Slide 32
..and are crucial to data analyses
ADB’s “Key Indicators” uses PPPs in SDGs 1, 7 and 9
43 indicators in WDI rely on PPPs
AfDB uses PPPs to establish poverty headcounts
SDG target 7.3 measures energy intensity with PPPs
WHO and WBG assess health cost impacts using PPPs
The Global Competitiveness Index uses PPPs in its 10th pillar measure – market size

## Slide 33: Regional Progress Reports
Regional Implementing Agencies

## Slide 34: Regional Progress Reports
Africa [African Development Bank]
Asia [Asian Development Bank]
Eurostat–OECD PPP program [Eurostat and OECD]
Commonwealth of Independent States [CIS-STAT]
Latin America and the Caribbean [UN-ECLAC]
Western Asia [UN-ESCWA]

## Slide 35: Outstanding Risks and Mitigation Measures
ICP Global Unit, World Bank

## Slide 36: Outstanding Risks (1)
Timeliness Risks
  Delay in initiating ICP 2017 survey activities and data submission for selected regions/countries
  Outstanding ICP 2017 activities – non-household surveys, backcasting and annualizing, regional and global validation, and results calculation and assessment – require time
  What can be published by end of 2019?
Participation Risks
  Uncertainty regarding 10 outstanding countries that are yet to submit data
  Difficulties in securing the full participation of some fragile states; however, they participate in capacity-building activities where possible

## Slide 37: Outstanding Risks (2)
Quality and Comparability Risks
  Regional data quality still needs improvement; more validation workshops and technical assistance needed
  Delay in initiating global data validation; however, quality of initial data is promising
  Comparability over time is crucial; impact of countries migrating from LAC to OECD
Openness Risks
  Need to demonstrate more openness and transparency than ICP 2011, while respecting country confidentiality laws

## Slide 38: Outstanding Risks (3)
Sustainable Funding Risks
  Sustainable funding for the permanent ICP hinges upon countries and multilateral agencies incorporating ICP into their regular work programs/budgets
Sustainable Institutional Risks
  Need permanent teams at country and regional level
  Strenuous processes in many agencies for channeling funding and organizing activities

## Slide 39: Governing Board Asks
Political Support
Continue to advocate with countries and multilateral agencies to:
Funding Support
  Advocate with regional development banks/donors to support the ICP in your region
Openness Support
Advocate for more openness and transperancy
incorporate ICP into their regular work programs/budgets
meet the ICP 2017 cycle deadlines and gear up for the 2020 cycle

## Slide 40: Beyond the ICP 2017 cycle
Global ICP Unit, World Bank

## Slide 41: ICP 2020 Preparations
Technical Preparations
The IACG discussed the plan for the ICP 2020 cycle
Institutional Preparations
Funding Preparations
ICP 2020 cycle budget underway
The ICP Global Core List will be updated in early 2019; regional item lists will be subsequently updated
  National, regional and global agencies to include the ICP in their work programs for 2019-2022
Need to multiply our collective fund-raising efforts in 2019

## Slide 42
AFRICA* | ICP 2020 CYCLE |  |  | 
 | 2019 | 2020 | 2021 | 2022
Household Consumption (H) |  | H |  | PUBLICATION OF 2020 RESULTS
Housing Rentals (R) and Volume (V) |  | R | V (2020) | 
Government Compensation (G) |  |  | G (2020) | 
Construction (C) and Machinery (M) |  | C & M |  | 
National Account Expenditures (E) | E | E | E | 
CPIs, Deflators, Population and XRs | X | X | X | 
* Africa is planning to produce results every 3 years
ICP 2020 Plan (1)

## Slide 43
ASIA* | ICP 2020 CYCLE |  |  | 
 | 2019 | 2020 | 2021 | 2022
Household Consumption (H) |  | H |  | PUBLICATION OF 2020 RESULTS
Housing Rentals (R) and Volume (V) |  | R | V (2020) | 
Government Compensation (G) |  |  | G (2020) | 
Construction (C) and Machinery (M) |  | C & M |  | 
National Account Expenditures (E) | E | E | E | 
CPIs, Deflators, Population and XRs | X | X | X | 
* Asia is planning to produce results every 3 years
ICP 2020 Plan (2)

## Slide 44
COMMONWEALTH OF INDEPENDENT STATES* | ICP 2020 CYCLE |  |  | 
 | 2019 | 2020 | 2021 | 2022
Household Consumption (H) |  | H |  | PUBLICATION OF 2020 RESULTS
Housing Rentals (R) and Volume (V) |  | R | V (2020) | 
Government Compensation (G) |  |  | G (2020) | 
Construction (C) and Machinery (M) |  | C & M |  | 
National Account Expenditures (E) | E | E | E | 
CPIs, Deflators, Population and XRs | X | X | X | 
* The Commonwealth of Independent States is planning to produce results every 3 years
ICP 2020 Plan (3)

## Slide 45
LATIN AMERICA AND THE CARRIBEAN* | ICP 2020 CYCLE |  |  | 
 | 2019 | 2020 | 2021 | 2022
Household Consumption (H) | H (1/3) | H (1/3) | H (1/3) | PUBLICATION OF 2020 RESULTS
Housing Rentals (R) and Volume (V) |  | R | V (2020) | 
Government Compensation (G) |  |  | G (2020) | 
Construction (C) and Machinery (M) |  | C & M |  | 
National Account Expenditures (E) | E | E | E | 
CPIs, Deflators, Population and XRs | X | X | X | 
* Latin America and the Caribbean is planning to produce results every 3 years
ICP 2020 Plan (4)

## Slide 46
WESTERN ASIA* | ICP 2020 CYCLE |  |  | 
 | 2019 | 2020 | 2021 | 2022
Household Consumption (H) |  | H |  | PUBLICATION OF 2020 RESULTS
Housing Rentals (R) and Volume (V) | R | R | R & V (2020) | 
Government Compensation (G) | G | G | G | 
Construction (C) and Machinery (M) | C & M | C & M | C & M | 
National Account Expenditures (E) | E | E | E | 
CPIs, Deflators, Population and XRs | X | X | X | 
* Western Asia is planning to produce annual results
ICP 2020 Plan (5)

## Slide 47
EUROSTAT-OECD* | ICP 2020 CYCLE |  |  | 
 | 2019 | 2020 | 2021 | 2022
Household Consumption (H) | H (1/3) | H (1/3) | H (1/3) | PUBLICATION OF 2020 RESULTS
Housing Rentals (R) and Volume (V) | R & V | R & V | R & V | 
Government Compensation (G) | G | G | G | 
Construction (C) and Machinery (M) | C & M | C & M | C & M | 
National Account Expenditures (E) | E | E | E | 
CPIs, Deflators, Population and XRs | X | X | X | 
* Eurostat and OECD are producing annual results
ICP 2020 Plan (6)

## Slide 48: Looking Ahead
Incorporate disruptive technology
Make use of new data sources
Form new partnerships
Develop new methods
Survey data
Admin/Census data
Scanner data
Web scaping
Private sector (E-commerce, sharing economy)
Capitalizing on the potential of data integration
Embracing the benefits of the digital revolution
Building national capacity and infrastructure

## Slide 49: Innovations – In Practice (1)
Web scraping
  Collection of web scraped rents and prices (ECLAC and various countries)
  PPPs from the Billion Prices Project (Academia)
Scanner data
  Use in CPIs & PPPs (Various countries)
  Methods for scanner data in CPIs & PPPs (Ottawa Group, UN, Academia)
Crowdsourcing
  Pilot studies (World Bank)
Admin/Census data
  Government salaries (ICP)
  Housing stock data (ICP)
  Public utility prices (World Bank)

## Slide 50: Innovations – In Practice (2)
Private sector data
  GFCF data (AFDB)
  Data collaboratives with e-commerce and sharing economy firms (World Bank)
AI/Machine Learning
Intl. Databases
  Housing quality indicators from WASH database (ADB)
  Education quality indicators database (World Bank)
  Image recognition for housing quality (Academia)
Visualization tools
  Improve data quality assurance processes (World Bank)

## Slide 51: Date and venue of the next meeting and any other business
Meeting Chair

## Slide 52: 4th ICP GB meeting
Proposed Date and Venue:
  Around the UNSC 50th Session
  Sunday March 3, 2019
  New York
Proposed Agenda:
  Progress Updates:
    ICP 2017 cycle
    ICP 2020 cycle prep
  ICP 2017 results
    Release timetable
    Communication and dissemination strategy
    Data access policy

## Slide 53: Closing Remarks
Governing Board Co-Chairs
World Bank

## Slide 54
Thank you